## Slide 1
Project Kick off
Date: April 28, 2020
Personal & Motive DCO Project
Digital Client Onboarding Stream

## Slide 2
Project Background
Benefits
Project Scope Overview
Measures of Success
Constraints/Dependencies
Assumptions/Risks
High Level Timeline
Project Team
Issue Management and Escalation
Project Management Methodology
Thank You
Kick Off

## Slide 3
Welcome to the Digital Program
Personal & Motive Digital Client Onboarding Project
Under the Digital Client Onboarding Stream

## Slide 4
Project Background
The Personal & Motive Digital Client Onboarding Project is part of the overall Digital Program and the Digital Client Onboarding (DCO) Program stream. The DCO Program stream includes the following Projects:
Motive DCO Minimal Viable Product (MVP)
Motive Full/Personal/In Branch DCO
Small Business DCO
Small Business Lending
The purpose of this Program stream is to enhance and implement the Temenos digital client onboarding platform called Infinity.
Problem Statement: The current digital client onboarding service is manual and needs to be conducted in/by a branch. There is no current functionality for a client to open an account online independently except for Motive.

## Slide 5
High Level Benefits
The following high level benefits have been identified:
  Reduce manual efforts that are currently required to open new accounts, and improve compliance and data integrity.
  Digital Client Onboarding will offer personal and small business clients a much faster way to open deposit and lending products remotely, which will benefits prospective new clients who are outside of CWB’s current geographic branch footprint.
  Reducing manual efforts required by CWB staff will improve the employee experience and allow them to focus on more value-add activities.

## Slide 6
The scope of the Digital Client Onboarding program stream includes the Motive MVP, Motive Full/Personal/In Branch DCO, Small Business DCO and Small Business Lending projects. Each project will entail:
Requirements Definition/Current State Assessment/Gap Analysis
Solution design
Development
Testing
Training
Deployment
Project Scope Overview

## Slide 7
Measures of Success
Scope
The scope of the project aligns to the Project Charter and managed within the PMO framework.
Time
Delivery of the project within the planned schedule.
Budget
The project is completed within budget.
Quality
The digital client onboarding service is implemented per the agreed to requirements.
Benefits
Achieve the benefits identified in the Program Charter.

## Slide 8
Constraints
The project will be using the Agile methodology with two week sprints, therefore work will be broken into multiple, two-week intervals.
Dependencies
Digital Online Banking Project for Small Business and Personal;
CWB Mulesoft and Infrastructure Implementation Project;
AML Financial Crimes Project;
T24 Virtualization;
Sitecore Upgrade; and
Identity and Access Management.
Constraints/
Dependencies

## Slide 9
Risks/Assumptions
RISKS | MITIGATION STRATEGY
Solution does not meet business needs | Define business requirements and assess against products.
Resistance to change by stakeholders. | Engage the Organizational Change Management team to address change and training requirements.
Inadequate testing due to complexities and dependencies of systems | Establish a formal test plan with dedicated test lead to facilitate each of the testing cycles.
Application may not function as expected | Testing will be performed on applications to ensure they function as expected. Any issues identified will be addressed prior to deployment.
Resource Constraints with same team members on DCO and Digital Banking. | Will work with the schedule to align resources as best as possible to minimize project impacts.

## Slide 10
Note: Dates may shift over 2020/21 as the team iterates
Digital Program – Roadmap Summary
2019
2021
Today
Nov
Jan
Mar
May
Jul
Sep
Nov
Jan
Mar
May
2019
2020
2021
Small Business Banking Launch
(Initial Focused Launch)
Jan 29
75 days
Nov 18, 2019
Program Setup + Governance Established
Feb 28, 2020
116 days
Dec 9, 2019
Motive DCO Project – Initial Implementation
July 13, 2020
201 days
Dec 9, 2019
Personal Online DCO Project & Motive DCO Project – Full Implementation
Sep 14, 2020
130 days
Jun 1, 2020
Small Business DCO Project (Go Live Ready)
Nov 2020
129 days
Sep 23, 2020
Small Business Lending Project (Go Live Ready)
Mar 2021
54 days
Jan 6, 2020
Small Business + Personal Banking Pre-Planning
Mar 19, 2020
225 days
Mar 20, 2020
Small Business Banking Implementation
Jan 2021
246 days
Mar 20, 2020
Personal Banking Implementation (Go Live Ready)
Feb 2021
192 days
Oct 5, 2020
Corporate Banking Implementation (Go Live Ready)
Jun 2021
Program Stream 1
Program Stream 2
Oct 2020 - TBC
Personal In Branch DCO Project - Full Implementation
May 2020
Digital Client Onboarding (DCO)
Digital Banking (DB)
Motive DCO - Friends & Family Launch
Motive DCO - Full Launch
June 22, 2020
Personal DCO - Friends & Family Launch
Personal Online DCO – Full Launch
Aug 17, 2020

## Slide 11
High Level Estimated Timeline – Motive MVP

## Slide 12
High Level Estimated Timeline – Motive Full/Personal/In Branch DCO

## Slide 13
High Level Estimated Timeline – Small Business DCO

## Slide 14
High Level Timeline – Small Business Lending

## Slide 15
Project Organization

## Slide 16
Issue Management and Escalation Process

## Slide 17
Project Management Project Delivery Lifecycle
Monitoring and Controlling ensuring controls are in place to manage the project work
Performing Integrated Change Control
Initiation Phase
Planning Phase
Execution Phase
Closure Phase
Project Kick off
Project Charter
New Initiative/Change Risk Assessment Tool
Project Management Plan
Develop project schedule and plans
SDLC: Requirements Gathering
Monitoring and Controlling Phase
Direct and manage the work
Manage Communications
Perform quality assurance
Conduct procurement
SDLC: Design, Build, Test, Go Live
Close of project or phase
Lessons Learned Report
Closure Report

## Slide 18
Thank You