## Slide 1: Motive MVP DCO Timeline
2019
2020
Today
Nov
Dec
2020
Feb
Mar
Apr
May
Jun
Start
Nov 1
Motive MVP Friends and Family Launch
Jun 8
Motive MVP Launch
135 days
0%
Dec 16 - Jun 19
Motive MVP DCO
15 days
0%
Dec 16 - Jan 3
Sprint 0 - Planning
75 days
0%
Jan 6 - Apr 17
Sprint Builds/Testing
15 days
Apr 20 - May 8
UAT Testing
30 days
0%
May 11 - Jun 19
Deploy