## Slide 1: Small Business Lending Timeline
2020
2021
Today
Jul
Aug
Sep
Oct
Nov
Dec
2021
Feb
Mar
Apr
Start
Jul 1
Small Business Soft Launch
Mar 22
Small Business Launch
Apr 12
180 days
0%
Aug 10 - Apr 16
Small Business Lending
30 days
0%
Aug 10 - Sep 18
Sprint 0 - Planning
110 days
0%
Sep 21 - Feb 19
Sprint Builds/Testing
15 days
Feb 22 - Mar 12
UAT Testing
10 days
0%
Mar 15 - Mar 26
Deploy