## Sheet1
Benefit Summary | Tangible / Intangible | Key Organization Goals | Target Metric to be Achieved | Report Date on Target Metric | Benefit Owner | Action
Offer personal and small business clients a more efficient way to open a new account separate small business to its own line | Tangible | Improves client experience | Improve the time for clients to open an account. Measure the current time it takes to open an account vs the time it takes after implementation of DCO. | immediately after DCO implementation. |  | Sarah - current times to open an account vs future times to open an account.
Offer personal and small business clients a better client experience separate small business to its own line | Intangible | Improves client experience | Implement digital client onboarding services. | immediately after program completion. |  | no action required, implementation of tools satisfies.
Enable new clients to CWB who are outside of CWB’s current geographic branch footprint | Tangible | Diversifies our presence geographically | Acquire new clients in geographic areas where we currently do not have. Report of current geographic client data compared to new data. | 6 months after DCO implementation |  | Kate to followup with Lisa/Corey - Report of current geographic client data compared to new data after implementation of DCO.
Reduce staff time in Motive for responding to manual request of client onboarding that will be now be offered online | Intangible | Makes CWB more efficient and/or more productive | It is estimated to reduce the Motive staff time as clients will now have the capability to open accounts online themselves from xxx to xx Measure the current time it takes Motive staff to open an account vs the time it takes after implementation of DCO. | 6 months after Full Motive DCO. |  | Stacy /Sarah/Michael White - capture metrics of Motive staff times for services
Reduce staff levels in Motive for digital client onboarding | Tangible |  | Reduce account opening staff (temporary employees) count by xx and $999 |  |  | Stacy/Michael - confirm staff allocations and potential reduction
Reduce staff time in CWB branches for onboarding personal customers repeat for small business | Intangible | Makes CWB more efficient and/or more productive | It is estimated to reduce the branch staff time as clients will now have the capability to open accounts online themselves xxx-xxx. Measure the current time it takes branch staff to open an account vs the time it takes after implementation of DCO. | 6 months after DCO implementation. |  | Sarah - current times to open an account vs future times to open an account.
Do we also want to measure how many the branch opens vs how many the client opens online themselves, would we have that data? repeat for small business |  |  | amount of clients onboarded by themselves
Standardizing the process to deliver a consistent experience for personal clients repeat for small business | Intangible | Improves employee effectiveness | Improve the time across branches for onboarding client. Review the current process maps vs future process maps, standard time measurements across branches today vs future. |  |  | Sarah - process maps, standard time measurements across branches, review variance today and tomorrow
Improving team members satisfaction for personal and small business DCO | Intangible | Improves the employee experience | Improve staff engagement. Xxx% of staff provide a response greater than "meet" Survey after DCO implementation |  |  | Sarah/Chantal - look at existing sources and surveys and future. OCM has a quarterly pulse survey that may be leveraged.