## Slide 1: Digital Client Onboarding Timeline
2019
2021
Today
Dec
Feb
Apr
Jun
Aug
Oct
Dec
Feb
Apr
125 days
0%
Dec 9 - Jul 24
Motive DCO
30 days
0%
Dec 16 - May 8
Sprint Planning
76 days
0%
Jan 6 - May 22
Sprint Builds/Testing
6 days
Jun 8 - Jun 12
BAT Testing
28 days
0%
May 17 - Jul 24
Deploy
170 days
0%
Mar 3 - Oct 26
Personal/Motive Full/In Branch DCO
35 days
0%
Mar 3 - Apr 20
Sprint Planning
56 days
0%
Apr 27 - Jul 13
Sprint Builds/Testing
10 days
Jul 20 - Jul 31
BAT Testing
6 days
Aug 10 - Oct 26
Deploy
146 days
0%
May 11 - Dec 11
Small Business DCO
26 days
0%
May 11 - Jun 15
Sprint Planning
86 days
0%
Jun 22 - Oct 19
Sprint Builds/Testing
10 days
Oct 26 - Nov 6
BAT Testing
21 days
0%
Nov 2 - Dec 11
Deploy
167 days
Aug 10 - Mar 31
Small Business Lending
25 days
Aug 10 - Sep 14
Sprint Planning
105 days
Sep 21 - Feb 15
Sprint Builds/Testing
10 days
Feb 22 - Mar 5
BAT Testing
17 days
Mar 8 - Mar 31
Deploy
10 days
0%
Apr 1 - Apr 14
Closure
Motive Friends and Family Launch
Jun 22
Motive MVP Public Launch
Jul 13
Personal Soft Launch
Aug 17
Personal DCO Launch
Sep 14
Personal In-Branch Launch
Oct 19
Small Business Go Live Ready
Nov 23
Small Business Launch
Jan 31
Small Business Lending Launch
Mar 22
Motive Full Launch
Aug 17