# CAPE Statement of Work

## Project: Digital Client Onboarding - Benefits Assessment

### Date: March 20, 2020

### Sponsoring Organization: Digital & Alternative Channels

## Objectives

The objectives of the benefits assessment are to understand the time savings (and full-time equivalent) and corresponding efficiency and staff engagement through standardization gained through implementation of a digital client onboarding (DCO) tool.

## Scope

The scope of this benefits assessment includes:

- In-branch personal account opening – new

- Motive personal account opening – new

- Motive personal account maintenance

For the purposes of this assessment, small business account opening will be considered as the same as personal (1-2 account holders). The impact of the DCO tool will be measured for both client self-serve and in-branch channels as compared to the current state in-branch.

The process of issuing a debit card will not be included at this time, as it is currently undergoing changes.

NOTE: Any items not listed here are considered out of scope for this project; the addition of out of scope items to the Project will not be made without prior approval and authorization from CAPE and will be handled through Change Requests or as separate SOWs.

## Approach and Detailed Activities

### Current State

- As there was some work conducted on account opening in 2019, any information that was gathered at that time will be leveraged.  This includes time data as well as process maps and narratives for the current state in-branch personal account opening process.

- In order to close the remaining gaps, CAPE will conduct a time study of the Motive account opening process by preparing self-tracking tools to be used by participants. As tracking will occur at the activity level (process step or group of steps), a walkthrough of Motive’s process will be required.

- Participants will receive training on how to use the tracker, as well as support during the tracking period. As current volumes and capacity to track are unknown due to the impact of covid-19, we will assume a tracking period of two weeks, with a check in after the first week to see if sufficient data has been collected and tracking stopped.

### Future State

Approximately six months after each rollout of the DCO product – Motive, CWB (client self-serve), and in-branch – measurements will be taken to assess the time required to open a personal account to compare to the current state:

- Motive account opening – self tracking time study using the same approach as noted above

- CWB account opening (client self-serve) – self tracking time

- In-branch account opening – self tracking time study using the same approach as noted above. The branch and participants will be selected at that time but it is recommended to use Edmonton Main, as they have participated in activities of this nature.

This information will be used to complete the benefits assessment and validate the benefits model.

## Deliverables

The deliverable (s) for this project are as follows:

- Process maps for current state in-branch and Motive personal account opening

- Pre Implementation - benefits model based on time and volume information gathered, including forecasted FTE impact for Motive and branch

- Post Implementation – validated benefits model based on time and volume/demographic data to validate FTE impact for Motive and branch and assess benefits realization

## Resource Requirements

The following resources are required to complete the activities outlined for the Current State. As we approach Future State information gathering activities, relevant resources will be identified.

| Name | Role | Function |
| --- | --- | --- |
| Sarah Barbour | CAPE Lead | Oversight, model development |
| Teresa Holwell | CAPE Analyst | Prep, administer, and support time tracking activities |
| Adam Skoreyko | Motive Process Advisor | Advise CAPE Analyst on Motive account opening processes for tracking activities |
| Participants (2-3) as identified by Julie Sturgeon | Motive Time Trackers | Complete self-tracking activities |

## Term and Estimated Project Timeline

The following table outlines the estimated start and end dates for the Current State. As we approach Future State activities, timelines will be agreed to.

| Activity | Start Date | End Date |
| --- | --- | --- |
| Develop current state process map for Motive and as a basis for self-tracking tool | Mar 25, 2020 | Mar 27, 2020 |
| Develop and validate self-tracking tool for Motive team | Mar 30, 2020 | Apr 3, 2020 |
| Kick off self tracking with Motive team (including training/orientation **check in Apr 13 to determine if tracking can be stopped. If so, all dates will be moved up a week. | Apr 6, 2020 | Apr 17, 2020 |
| Build model and forecast benefits | Apr 20, 2020 | Apr 24, 2020 |
| Present findings to Digital team | Apr 25, 2020 | Apr 25, 2020 |

The above timelines are estimates only and are dependent upon the final approved project plan, covid-19 business continuity activities and requirements, availability of project resources and timely decision-making on key documents, phases and/or deliverables.