## Slide 1
Project Kick off
Date: August 2020
Small Business Lending Project
Digital Client Onboarding Stream

## Slide 2
Project Background
Benefits
Project Scope Overview
Measures of Success
Constraints/Dependencies
Assumptions/Risks
High Level Timeline
Project Team
Thank You
Appendix
  Issue Management and Escalation
  Project Management Methodology
Kick Off

## Slide 3
Welcome to the Digital Program
Small Business Lending Project

## Slide 4
Project Background
The Small Business Lending Project is part of the overall Digital Program and the Digital Client Onboarding (DCO) Program stream. The DCO Program stream includes the following Projects:
Motive/Personal/In Branch DCO
Small Business DCO
    Small Business/Personal/Commercial Digital Banking
Small Business Lending
The purpose of this Program stream is to enhance and implement the Temenos digital client onboarding and digital banking platform called Infinity.
Problem Statement: The current Small Business Lending service is manual and needs to be conducted in/by a branch. There is no current functionality for a client to apply for a loan online independently.

## Slide 5
High Level Benefits
The following high level benefits have been identified:
  Providing our clients value proposition in acquiring small loan business capital (<250k)
  Additional benefits will be defined once the lending partner is chosen

## Slide 6
The scope of the Small Business Lending project will be to integrate the selected loan partner into the DCO and Digital Banking streams. This will entail:
It is expected that the lending partner will have responsibility for setup and adjudication of the SB client (To be confirmed in RFP selection). A redirect will be provided to the lending partner from the SB DCO application flow, which may include passing of some client data and information (dependent on partner capabilities);
Integration of the loan partner into the Digital Banking stream to provide clients the ability to view attributes relating to their loan e.g. loan amount, balance, payment, etc.;
Requirements Definition;
Solution design;
Development including APIs to integrate into the Infinity platform and T24 as required;
Testing
Training
Deployment
Project Scope Overview

## Slide 7
Measures of Success
Scope
The scope of the project aligns to the Project Statement and managed within the PMO framework.
Time
Delivery of the project within the planned schedule.
Budget
The project is completed within budget.
Quality
The small business lending service is implemented per the agreed to requirements.
Benefits
Achieve the benefits identified in the Project Statement.
Success rate with clients utilizing new Partner platform.

## Slide 8
Constraints
To be implemented with the Small Business DCO and small Business Digital Banking.
Dependencies
Digital Banking Project for Small Business; and
Digital Client Onboarding project for Small Business.
Constraints/
Dependencies

## Slide 9
Risks/Assumptions
RISKS | MITIGATION STRATEGY
Solution does not meet business needs | Define business requirements and assess against product.
Inadequate testing due to complexities and dependencies of systems | Establish a formal test plan with dedicated test lead to facilitate each of the testing cycles.
Application may not function as expected | Testing will be performed on applications to ensure they function as expected. Any issues identified will be addressed prior to deployment.
Resource Constraints with same team members on DCO and Digital Banking. | Will work with the schedule to align resources as best as possible to minimize project impacts.
Fulfilment of lender to provide our clients satisfactory service | Put in place SLAs and monitor.

## Slide 10
Note: Dates may shift over 2020/21 as the team iterates
Digital Program – Roadmap Summary
2019
2021
Today
Nov
Jan
Mar
May
Jul
Sep
Nov
Jan
Mar
May
2019
2020
2021
Small Business Banking Launch
(Initial Focused Launch)
Jan 29
75 days
116 days
Dec 9, 2019
Motive DCO Project – Initial Implementation
July 13, 2020
201 days
Dec 9, 2019
Personal Online DCO Project & Motive DCO Project – Full Implementation
Sep 14, 2020
130 days
Jun 1, 2020
Small Business DCO Project (Go Live Ready)
Nov 2020
129 days
Aug 18, 2020
Small Business Lending Project (Go Live Ready)
December 2020
54 days
Jan 6, 2020
Small Business + Personal Banking Pre-Planning
Mar 19, 2020
225 days
Mar 20, 2020
Small Business Banking Implementation
Jan 2021
246 days
Mar 20, 2020
Personal Banking Implementation (Go Live Ready)
Feb 2021
192 days
Oct 5, 2020
Corporate Banking Implementation (Go Live Ready)
Jun 2021
Program Stream 1
Program Stream 2
Oct 2020 - TBC
Personal In Branch DCO Project - Full Implementation
May 2020
Digital Client Onboarding (DCO)
Digital Banking (DB)
Motive DCO - Friends & Family Launch
Motive DCO - Full Launch
June 22, 2020
Personal DCO - Friends & Family Launch
Personal Online DCO – Full Launch
Aug 17, 2020

## Slide 11
High Level Estimated Timeline – Small Business Lending

## Slide 12
Project Organization

## Slide 13
Thank You

## Slide 14
Issue Management and Escalation Process

## Slide 15
Project Management Project Delivery Lifecycle
Monitoring and Controlling ensuring controls are in place to manage the project work
Performing Integrated Change Control
Initiation Phase
Planning Phase
Execution Phase
Closure Phase
Project Kick off
Project Statement
New Initiative/Change Risk Assessment Tool
Project Management Plan
Develop project schedule and plans
SDLC: Requirements Gathering
Monitoring and Controlling Phase
Direct and manage the work
Manage Communications
Perform quality assurance
Conduct procurement
SDLC: Design, Build, Test, Go Live
Close of project or phase
Lessons Learned Report
Closure Report