## Sheet1
CWB Personal & In-Branch Outstanding Deliverables
Program Stream | Deliverable | Dependencies | Status | Progress | ETA | Assigned To | Notes
CWB Personal DCO | Business Requirements | none | Complete | 100% | n/a | Steve Kelcher
CWB Personal DCO | Conceptual Design | none | Complete | 100% | n/a | Steve Kelcher | No changes to Motive DCO conceptual design
CWB Personal DCO | Journey Map | A) Business Requirements B) Conceptual Design | In Progress | 95% |  | Dean Poole Supported by Steve Kelcher | - No significant changes to Motive DCO Journey Maps. - Revisions required for SAS AML and Funding form
CWB Personal DCO | Field Specifications (3) | A) Business Requirements B) Journey Map | Complete | 100% | n/a | Steve Kelcher
CWB Personal DCO | Email Specification | A) Business Requirements B) Journey Map | In Progress | 75% | 2020-09-25 | Steve Kelcher
CWB Personal DCO | Product Catalogue Field Matrix | Business Requirements | In Progress | 50% | 2020-09-21 | Steve Kelcher
CWB Personal DCO | Product Specification | A) Business Requirements B) Product Catalogue Field Matrix | In Progress | 20% | 2020-09-23 | Steve Kelcher Supported by Candyse Watkinson
CWB Personal DCO | Spec revisions for support contact info | Availability of information | Not Started | 0% | TBD | Steve Kelcher Supported by Francis Ho | - Revise field specs - Revise email spec
CWB Personal DCO | Decision Logic Matrix | Journey Map | Not Started | 0% | 2020-09-29 | Steve Kelcher | Perform gap analysis on Motive DCO decision rules. Update for CWB Personal as required (add SAS AML logic).
CWB Personal DCO | Analytics Milestone Matrix | A) Journey Map B) Field Specifications C) Decision Logic Matrix | Not Started | 0% | 2020-09-30 | Steve Kelcher | Perform gap analysis on Motive DCO milestones. Update for CWB Personal as required.
CWB Personal DCO | Transition to Operations | A) Client Support Model B) Branch Support Model | Not Started | 0% | 2020-10-16 | Ian Hicks | Can leverage some of the Motive one
CWB In-Branch Personal DCO | Business Requirements | none | Not Started |  |  | Steve Kelcher | Use CWB Personal requirements as baseline
CWB In-Branch Personal DCO | Conceptual Design | none | Complete | 100% | n/a | Roland Matsuba
CWB In-Branch Personal DCO | Journey Map | A) Business Requirements B) Conceptual Design | In Progress | 80% | 2020-09-24 | Dean Poole Supported by Roland Matsuba
CWB In-Branch Personal DCO | Field Specification | A) Business Requirements B) Journey Map | In Progress | 30% |  | Roland Matsuba | Use CWB Personal field specifications as baseline
CWB In-Branch Personal DCO | Email Specification | A) Business Requirements B) Journey Map | Cancelled | n/a | n/a | n/a | No emails required for in-branch personal DCO
CWB In-Branch Personal DCO | Product Catalogue Field Matrix | A) Business Requirements B) Baseline Product Catalogue Field Matrix (from CWB Personal) |  |  |  |  | Perform gap analysis on existing catalogue fields. Update for in-branch if required.
CWB In-Branch Personal DCO | Product Specification | A) Business Requirements B) Product Catalogue Field Matrix C) CWB Personal Product Spec | In Progress | 10% |  |  | Perform gap analysis on existing product spec. Update for in-branch if required.
CWB In-Branch Personal DCO | Decision Logic Matrix | Journey Map
CWB In-Branch Personal DCO | Analytics Milestone Matrix | A) Journey Map B) Field Specification C) Decision Logic Matrix
CWB In-Branch Personal DCO | Transition to Operations | A) Client Support Model B) Branch Support Model | Not Started | 0% | 2020-10-16 | Ian Hicks | Determine if we just need one TTO doc for both Personal and Personal In-Branch?