## RAID_List
[10 empty] | DAY | MON | YEAR
[10 empty] | 4 | 2 | 2021
2021-02-04
RISK | [5 empty] | ISSUE | [5 empty] | IMPEDIMENTS | [6 empty] | DECISIONS |  |  |  | ACTIONS
Risk Number | Project Name | Title | Category | Severity | Duration | Issue Number | Project Name | Title | Severity | Duration |  | Impediment Number | Project Name | Title | Category | Status | Due Date | Duration | Decision Number | Project Name | Title | Status | Task Number | Project Name | Title | Status
1787 | Small Business DCO | Temenos' capacity for sprint completion may impact the overall delivery date. | Vendor | High | 17 | 1 | Small Business DCO | Continually late with the requirements, and consequently Temenos will need to do the T24 review process for the services mid-sprint. | Moderate | 0 |  | 1 | Small Business DCO | Blocked items in Sprint 6 | Requirements | In Progress | Fri, Jan 29, 2021 | 30 | 1 | Small Business DCO | Shifting story CWBSB-227 to Sprint 8 | In Review | 4 | Small Business DCO | Complete: Create Business CIF | In Progress
1775 | Small Business DCO | Defect Prioritization Plan yet to be received | Vendor | Moderate | 24 | 2 | Small Business DCO | As requirements are late, they are constantly behind in developing the test cases, to be | 0 | 0 |  | 2 | Small Business DCO | Blocked items for Sprint 7 | Requirements | Closed | Tue, Feb 02, 2021 | 16 | 1 | Small Business DCO | Me-to-Me Funding | In Review | 5 | Small Business DCO | Complete: Create Personal CIF | Closed
1780 | Small Business DCO | Risk event: high volume of defects resulting in rework. | Quality | Very High | 31 | [6 empty] | 3 | Small Business DCO | Create Business CIF not working | Integration | In Progress | Fri, Jan 29, 2021 | 8 | 1 | Small Business DCO | XML File for product selector | 0 | 6 | Small Business DCO | Update about service availability | In Progress
0 | Small Business DCO | Ring-Fence unable to access CWB QADIG | Integration | Moderate | 8 | [17 empty] | 9 | Small Business DCO | Custom Navigation use cases | In Progress
0 | Small Business DCO | Unable to complete stories in Sprint 6 | Scope | High | 8 | [17 empty] | 11 | Small Business DCO | Happy Path Test Users | In Progress
0 | Small Business DCO | Unable to complete stories in Sprint 7 | Scope | High | 8 | [17 empty] | 12 | Small Business DCO | Non-Happy Path Test Users | Open
0 | Small Business DCO | Schedule impacts due to selected delivery methodology | Schedule | 0 | 7 | [17 empty] | 13 | Small Business DCO | Okta Integration | Pending
0 | Small Business DCO | Additional Scope items impacting delivery timelines | Scope | 0 | 7 | [17 empty] | 14 | Small Business DCO | Sprint 7 blockers: Requirements | Closed
0 | Small Business DCO | Reporting requirements | Scope | 0 | 7 | [17 empty] | 16 | Small Business DCO | Sprint 7 Blockers: UX | Closed
0 | Small Business DCO | Small Business Lending Scope | Scope | 0 | 7 | [17 empty] | 17 | Small Business DCO | Field Spec to Mule API mapping | Open
0 | Small Business DCO | OCM Resourcing | OCM | 0 | 3 | [17 empty] | 18 | Small Business DCO | Codat Integration Meeting | 0
0 | Small Business DCO | QA Resourcing | 0 | 0 | 23 | [17 empty] | 19 | Small Business DCO | Avoka Mapping Questions | In Progress
0 | Small Business DCO | PM resourcing | 0 | 0 | 20 | [17 empty] | 20 | Small Business DCO | Supporting BIG on SBDCO service questions | 0
0 | Small Business DCO | Timeline | 0 | 0 | 0 | [17 empty] | 22 | Small Business DCO | Create Business Account | 0
[23 empty] | 23 | Small Business DCO | Product Selector landing page | 0
[23 empty] | 24 | Small Business DCO | Wireframes for guided experience for Product Selector (questions asked to clients to offer a product) | 0
[23 empty] | 25 | Small Business DCO | Lessons Learned sessions | 0

## RAID_Counts
[5 empty] | DAY | MONTH | YEAR
[5 empty] | 29 | 1 | 2021
2021-01-29
RISK | Severity | Open Risks | Vendor | OCM | Communication | Cost | Deployment | Facilities | Infrastructure | Integration | Benefits | Quality | Resources | Schedule | Scope | Technical | Training | Objectives
| Very Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Moderate | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| High | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
| Very High | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0
ISSUES | Severity | Outstanding Issues | New | Open | In Progress | Pending | Escalated
| Very Low | 0 | 0 | 0 | 0 | 0 | 0
| Low | 0 | 0 | 0 | 0 | 0 | 0
| Moderate | 0 | 0 | 0 | 0 | 0 | 0
| High | 0 | 0 | 0 | 0 | 0 | 0
| Very High | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 0 | 0 | 0 | 0 | 0 | 0
IMPEDIMENTS | Severity | Open Risks | Vendor | OCM | Communication | Cost | Deployment | Requirements | Infrastructure | Integration | UX / UI | Quality | Resources | Schedule | Scope | Benefits / Objectives | Training | Business Approval
| Very Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Moderate | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| High | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Very High | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 3 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DECISIONS | Status | Count
| New | 0
| Open | 0
| In Progress | 2
| Pending | 0
| In Review | 6
| Escalated | 0
| Closed | 0
| Revoked | 0
| Cancelled | 0
| Total | 8
ACTIONS | Priority | Open Action Items | New | Open | In Progress | Pending | Escalated
| Low | 0 | 0 | 0 | 0 | 0 | 0
| Medium | 3 | 0 | 1 | 2 | 0 | 0
| High | 5 | 0 | 0 | 1 | 1 | 0
| Critical | 1 | 0 | 0 | 1 | 0 | 0
| TOTAL | 9 | 0 | 1 | 4 | 1 | 0

## Risk Tracking and Mitigation
Risk Number | Project Name | Date Reported | Category | Visibility | Title | Description | Risk Cause | Risk Consequence | Risk Owner | Status | Severity | Probability | Strategy | Strategy Details | Closed Date | Duration (Days) | Additional Notes | Helper | Helper1
1787 | Small Business DCO | 2021-01-18 | Vendor | External | Temenos' capacity for sprint completion may impact the overall delivery date. | Reviewing the burndown charts for Temeno's progress on the DCO sprints showcases that they are consistently behind 50-75% of the total story points. | As missed work results in user stories moving to future sprints, there is no remediation plan to address how Temenos will address the remaining items before the small business DCO launch. | Delay in deployment | Temenos: Kendyl CWB: Sarah-Mae | Monitoring | High | Moderate | Mitigate | 1) Temenos to revisit their delivery schedule and plan, providing a remediation plan for how they will get all the work completed on time. 2) Discussion to revisit the delivery methodology, timeline or resource capacity to meet the predetermined schedule. 3) Tracking the remediation plan in weekly status reports to ensure that Temenos' proposed plan is working and that we are on track. |  | 17 | Please note: at this time, Temenos has not flagged any issues with delivery or being behind; however, the sprint reports from their JIRA instance showcase this trend. | 1Y | 1Y
1775 | Small Business DCO | 2021-01-11 | Vendor | External | Defect Prioritization Plan yet to be received | We have yet to receive in-branch/motive defect plan and is currently past due. | Undefined releases can impact the usability of the currently launched product. | Unresolved defects from initial releases | Temenos: Kendyl CWB: Sarah-Mae | Mitigating | Moderate | Moderate | Mitigate | Continual communication with vendors to monitor defect plan progression. May extend windows for warranty releases to accommodate the back log of defects. |  | 24 | Jan 12 - Kendyl to provide prioritized accessibility defects with dates to implement within the plan by Friday, Jan 15. Jan 18 - The list updated list of warranty items and the proposed schedule has not been sent by Temenos. | 2Y | 2Y
1780 | Small Business DCO | 2021-01-04 | Quality | External | Risk event: high volume of defects resulting in rework. | The delivery methodology and schedule from Temenos is mismatched with their ability to provide high quality artifacts. The increase in defects jeopardizes the program's scope and schedule. | Tight timelines, resource availability and competencies are impacting the quality being delivered by Temenos. | - Delay in deployment - Rework required by team - Additional costs from delays | Temenos: Lauren CWB: Dilshad | Escalating | Very High | Very High | Mitigate | Formalized request for a quality improvement plan to address the ongoing issues with code quality, testing and resource allocations. Escalation to leadership to emphasize the importance of quality, to ensure the program can meet it's scope and delivery dates. |  | 31 | Quality improvement plan request commenced on Dec 09, 2020. Reiterated the request on Dec 22, 2020 - Lauren advised that it was completed and would be provided by Dec 29, 2020. Escalated to Lauren (Temenos) on Dec 31, 2020 - who advised Kendyl would be providing it on her return by EOD on Jan 05, 2021. Kendyl provided feedback on Jan 07, 2021 indicating that the Quality Improvement Plan has not been developed, asking to work collaboratively. Details for escalation provided to CWB program leadership team on Jan 13, 2021. Formally submitting escalation on Jan 18, for senior leadership level intervention with Temenos | 3Y | 3Y
| Small Business DCO | 2021-01-27 | Integration | External | Ring-Fence unable to access CWB QADIG | [5 empty] | Moderate | Moderate | Accept |  |  | 8 | << ensure that items that Brad, Lisa, Keith are aware in issues like this. SM to follow up Lisa offline. | 4Y | 4Y
| Small Business DCO | 2021-01-27 | Scope | External | Unable to complete stories in Sprint 6 | There are 3 blocked stories that are overdue for Sprint 6 which could impact Temenos' ability to complete the stories in the sprint. | Change in BA resource availbility and integration issues with Ring-Fence and the CWB QADIG have delayed resolution | There may be last minute changes to sprint items, or impact the overall delivery schedule. | Temenos: Kendyl CWB: Sarah-Mae BIG: Andy | Monitoring | High | High | Mitigate | All teams are working towards defining what will be provided before the end of the week, 01/29/2021. |  | 8 | Note: this item is already red, and by EOD on 01/29/2021 we should understand if we're trending back to amber or unable to mitigate this risk. Note: Kendyl to reorder the blocked items to ensure that the team is emphasizing. Kendyl to address the impacts if the information is delivered by EOD Jan 29. SM to TT Kendyl offline. | 5Y | 5Y
| Small Business DCO | 2021-01-27 | Scope | External | Unable to complete stories in Sprint 7 | There are 17 blocked stories that are overdue for Sprint 7 could impact the delivery dates for the project | Backlogged items and requirements have impeded Temenos' ability to prepare for the sprint | There may be last minute changes to sprint items, or impact the overall delivery schedule | Temenos: Kendyl CWB: Sarah-Mae BIG: Andy | Monitoring | High | Moderate | Mitigate | All teams are working towards defining what will be provided before the commencement of Sprint 7, as well as a go-to-green plan to get on track. |  | 8 | Note: this item is already amber, and by EOD on 01/29/2021 we should understand if we're trending red or able to mitigate this risk. | 6Y | 6Y
| Small Business DCO | 2021-01-28 | Schedule | External | Schedule impacts due to selected delivery methodology | Temenos Small biz DCO backlog is based on estimated effort of placeholder stories while requirements continue to be defined on a sprint-by-sprint basis. Due to this more agile approach, as requirements are defined, effort may be deviate from the original estimated effort. | [7 empty] | This is expected due to the requirements approach and will be handled on a case-by-case basis, amending schedule or scope as needed to accommodate these deviations. Where possible, Temenos will provide recommendations and alternatives that will help resolve for the increase in effort. |  | 7 |  | 7Y | 7Y
| Small Business DCO | 2021-01-28 | Scope | External | Additional Scope items impacting delivery timelines | Custom Navigation, not in the original SOW | [7 empty] | Reviewing the details to estimate the sizing and impacts to the timeline. |  | 7 |  | 8Y | 8Y
| Small Business DCO | 2021-01-28 | Scope |  | Reporting requirements | In the SOW | [9 empty] | 7 |  | 9Y | 9Y
| Small Business DCO | 2021-01-28 | Scope |  | Small Business Lending Scope | In the SOW |  | Scope is too large to integrate with current committed delivery date, May 03. Will need to revisit how to manage this workstream. | [7 empty] | 7 | Follow up with Lauren, Christina and Jason. | 10Y | 10Y
| Small Business DCO | 2021-02-01 | OCM |  | OCM Resourcing | *** | [9 empty] | 3 |  | 11Y | N
| Small Business DCO | 2021-01-12 |  |  | QA Resourcing | [10 empty] | 23 |  | 12Y | 12Y
| Small Business DCO | 2021-01-15 |  |  | PM resourcing | [10 empty] | 20 |  | 13Y | 13Y
| Small Business DCO | 2021-02-04 |  |  | Timeline | Requirements, Product Selector | List of possible change requests: Custom Nav, Product Selector, Reporting, Auto-Adjudication, Application Check. | [8 empty] | 0 |  | 14Y | N
Formulas:
Duration (Days) = IF(RiskTracker[[#This Row],[Date Reported]]="","",IF(RiskTracker[[#This Row],[Closed Date]]="",TODAY()-RiskTracker[[#This Row],[Date Reported]],RiskTracker[[#This Row],[Closed Date]]-RiskTracker[[#This Row],[Date Reported]]))

## Issue Tracking and Resolution
Issue Number | Project Name | Date Reported | Identified by | Task Owner | Due Date | Title | Description | Issue Cause | Impacts | Status | Severity | Probability | Resolution Date | Duration (Days) | Additional Notes | Helper | Helper1
1 | Small Business DCO | 2021-02-04 | Kendyl | Sarah-Mae | 2021-02-26 | Continually late with the requirements, and consequently Temenos will need to do the T24 review process for the services mid-sprint. |  |  |  | In Progress | Moderate |  |  | 0 |  | 1Y | N
2 | Small Business DCO | 2021-02-04 | Chix | Sarah-Mae | 2021-02-26 | As requirements are late, they are constantly behind in developing the test cases, to be |  |  |  | In Progress |  |  |  | 0 |  | 2Y | N
[6 empty] | 30 story points. | 40 story, for a remediation on how |  |  | In Progress
Formulas:
Duration (Days) = IF(IssueTracker[[#This Row],[Date Reported]]="","",IF(IssueTracker[[#This Row],[Resolution Date]]="",TODAY()-IssueTracker[[#This Row],[Date Reported]],IssueTracker[[#This Row],[Resolution Date]]-IssueTracker[[#This Row],[Date Reported]]))

## Impediments Tracking and Status
Impediment Number | Project Name | Date Reported | Identified by | Action Owner | Due Date | Title | Description | Affected SOWs and Stories | Delivery Sprint | Category | Status | Severity | Resolution Date | Duration (Days) | Additional Notes | Helper | Helper1
1 | Small Business DCO | 2021-01-05 | Kendyl | Multiple | Fri, Jan 29, 2021 | Blocked items in Sprint 6 | There are several stories remaining for Sprint 6, that need information: |  | Sprint 6 | Requirements | In Progress | Very High |  | 30 | Completed these items | 1Y | 1Y
|  |  |  | Ian H. | Fri, Jan 29, 2021 |  | 4 stories assigned to Ian |  | Sprint 6 | Requirements | Closed | Very High | Thu, Jan 28, 2021 |  | Completed these items
|  |  |  | Kelvin | Fri, Jan 29, 2021 |  | 1 story assigned to Kelvin | CWBSB-294 | Sprint 7 | Requirements | Closed | High
2 | Small Business DCO | 2021-01-19 | Kendyl | Multiple | Tue, Feb 02, 2021 | Blocked items for Sprint 7 | There are 21 stories remaining for Sprint 7, that need information: |  | Sprint 7 | Requirements | Closed | High |  | 16 |  | 2Y | 2Y
|  |  |  | Ian H. | Fri, Jan 29, 2021 |  | 10 stories assigned to Ian | CWBSB-408, 391, 263, 46, 324, 227, 73, 249, 124, 420 | Sprint 7 | Requirements | Closed | High
|  |  |  | Andy | Fri, Jan 29, 2021 |  | 6 stories assigned to Andy |  | Sprint 7 | Requirements | Closed | High
|  |  |  | Kelvin |  |  | 2 stories assigned to Kelvin | CWBSB-243, 244 | Sprint 7 | Requirements | Closed | High
|  |  |  | Unassigned | Tue, Feb 02, 2021 |  | 1 story that's a dependency to a service integration | CWBSB-125 | Sprint 7 | Requirements | Closed | High
3 | Small Business DCO | 2021-01-27 | Kendyl | Andy | Fri, Jan 29, 2021 | Create Business CIF not working | Escalated to Ring Fence, issue on the webservice. | CWBSB-380, 384,110,122 | Sprint 6 | Integration | In Progress | High |  | 8 | Follow up re: CWBSB-148 | 3Y | 3Y
4 |  |  | Kendyl | Kelvin | 2021-02-04 | There are a couple pages are working through styles for the controls for the expand all / collapse > currently in review with UX (Kelvin) and for the authorized signer they are trying to use standardized requiremetns > in current sprint | Kelvin already updated |  |  |  | In Progress
5 |  |  | Sandra | Kendyl | 2021-02-09 | For review for CWB for the authorized signer they are trying to use standardized requiremetns > in current sprint
Formulas:
Duration (Days) = IF(ImpedTracker[[#This Row],[Date Reported]]="","",IF(ImpedTracker[[#This Row],[Resolution Date]]="",TODAY()-ImpedTracker[[#This Row],[Date Reported]],ImpedTracker[[#This Row],[Resolution Date]]-ImpedTracker[[#This Row],[Date Reported]]))

## Decisions log
Decision Number | Project Name | Visibility | Date Reported | Title | Description | Module | Feature | Functionality | Decision Resolution | Decision Maker | Decision Date | Status | Decision Rationale | Helper | Helper1
1 | Small Business DCO |  | 2021-01-25 | CR Creation for DCO and Warranty | Team to work through the finalized list of defects | Not Applicable | Not Applicable | Not Applicable |  |  |  | In Progress |  | N | 1Y
1 | Small Business DCO | Program Impact | 2021-01-25 | Changes to Temenos Sprint Schedule | Temenos advised that after the project reset, the shift in the demo dates moved the sprint start / end dates | Not Applicable | Not Applicable | Not Applicable | This means that sprints start on Wednesdays and end on Tuesdays; therefore, the next sprint commences Wed Jan 20, and ends on Tues Feb 02. | Kendyl / Lauren | 2021-01-25 | In Review |  | N | 1Y
1 | Small Business DCO | Program Impact | 2021-01-26 | Changes to the DCO Warranty Schedule | To improve our internal quality issues we will be extending the internal testing / review cycles. | Not Applicable | Not Applicable | Not Applicable | - Temenos will send code every other Wednesday - CWB QA completes their first review the following Wednesday - Temenos / CWB will have a week to review / remediate any issues, until the following Thursday. - Finalization of the code package will be that Friday. - The CR is developed on Monday, with the release the following Sunday | CWB Team Consensus, including the business, release management, QA, BA, UX. | 2021-01-26 | In Review | Example with the current build: - Temenos sends build Jan 27 - Chix completes testing by Feb 03 - Any remediation items to be resolved Feb 4 to 11 - Final GNG for the release on Feb 12 - CR defined on Feb 15/16*, and Go Live on Sun Feb 21. | N | 1Y
1 | Small Business DCO |  | 2021-01-26 | Resolving QA testing to Field Spec Discrepancies |  | Not Applicable | Not Applicable | Not Applicable |  |  |  | In Progress |  | N | 1Y
1 | Small Business DCO | Program Impact | 2021-01-27 | Application delivery windows | DCO team looking for confirmation for the deployment windows for our project and warranty releases. | Not Applicable | Not Applicable | Not Applicable | Dayna Confirmed that the best time to facilitate deployments on non-business days after the evening batch processing, and before 8am AST when it's customer system impacting. | Dayna |  | In Review |  | N | 1Y
1 | Small Business DCO | Project Impact | 2021-01-27 | Enhancement work will include CRs from the remaining defects list | Clear defined lines for how to manage any CRs that arise from the contested defects list or other change requests. | Not Applicable | Not Applicable | Not Applicable | Any items in the contested list of defects that will require a CR will be managed by the DCO Enhancements project, with Lorraine. |  |  | In Review |  | N | 1Y
1 | Small Business DCO | Project Impact | 2021-01-28 | Shifting story CWBSB-227 to Sprint 8 | Moving a timeline for the SB DCO bug that impacts the orverarching standards / UX for the platform. | Not Applicable | Not Applicable | Not Applicable | Shifting the timeline for completion of this requirements for Temenos, from Sprint 6 to Sprint 8, so that the team can provide better clarity along with the other global UX requirements |  |  | In Review | This is in conjuction with the global standards / UX document that we will be creating to meet the quality improvement plan for the platform. | 1Y | 1Y
1 | Small Business DCO | Leadership Review | 2021-01-29 | Me-to-Me Funding | M2M Release funding with Release 1 | FALSE | FALSE | FALSE | Basically, what I’m hearing (and how the DR should be worded) is: - M2M personal to business is built and available - B2B business to business is not built, and would require work from our teams, Temenos and possibly C1(?). Impacts timelines and would want to use for DBX so better to build holistically for both o Matching criteria and capabilities also not built to validate legitimate ownership of both accounts | Stacy | 2021-01-29 | In Review | We will offer “Me-2-Me” funding (via Flinks) with limited functionality for Small Business DCO MVP. This will be based on personal DCO - so will be offered to the main applicant (the person who initiated the Small Business DCO application) to fund from a personal account belonging to them (and subject to the same validation we have in personal, that the account belongs to them). | 2Y | 2Y
1 | Small Business DCO | Leadership Review | 2021-01-29 | XML File for product selector | In the absence of a robust cross-platform (Infinity DBX and Journey Manager DCO) solution for product selection and management, we have agreed to utilize a streamlined product catalogue (created/maintained as configurable XML files) coupled with Product Selector form pages in Small Business DCO to meet our needs for the MVP release | FALSE | FALSE | FALSE | This is similar to the approach used for personal DCO, although we will be providing additional attribution for business (accounts and cash management products) and will build out the envisioned “guided journey” pages (which were descoped from personal DCO). Further, this functionality will be leveraged by the Infinity DBX platform as a means to add products for existing clients |  |  |  | NOTE the following risks: - The ultimate cross-platform solution requested of Temenos may result in significant rework in future, and may make some or all of what is being built for Small Business DCO as “throwaway” work. - Operationalizing the proposed solution may result in more manual work (to keep the product catalogue current) than is desirable - Caveat to Temenos was that this needs to be usable for DBX | 3Y | 3Y
[6 empty] | Not Applicable | Not Applicable | Not Applicable

## Action log
Task Number | Project Name | Date Reported | Task Owner | Title | Description | Priority | Task Status | Target Due Date | Actions Required | Status Date | Task Information | Actual Resolution Date | Additional Notes | Helper | Helper1
1 | Small Business DCO | 2021-01-11 | Chix | Dashboard for DCO | Confirmation of when the dashboards for warranty be shared (e.g. end of cycle)? | High | Closed | 2021-01-29 | Chix to confirm | 2021-01-28 |  | 2021-01-28 | SM to TT Chix offline about this.
2 | Small Business DCO | 2021-01-11 | Chix | Comprehensive reporting, e.g. defect open/closure rate chart. | Addition of the created vs resolved defects tab for DCO and test case development | High | Closed | 2021-01-29 | Confirmation that this tab can be added to remove need for additional request | 2021-01-28 |  | 2021-01-28 | Will be able to pull extract from JIRA
3 | Small Business DCO | 2021-01-11 | Chix | Test Case sharing | Confirmation that we are sharing the test cases with Temenos, so they are privy of what you will be validating | Medium | Closed | 2021-01-29 | Chix to confirm | 2021-01-28 |  | 2021-01-28 | Only with Digital, not with DCO. ¦ Could be used as a mitigation for Temenos' Quality Improvement Plan incase of further issues.
4 | Small Business DCO | 2021-01-25 | Andy | Complete: Create Business CIF | service to be completed on EOD on Monday | Critical | In Progress | 2021-01-25 | Need a status update on the outstanding issue; what's next? | 2021-01-28 | 1) Andy facilitated full review and is code complete. 2) Investigation required from Ring-Fence. 3) Chad is facilitating a review will provide feedback, EOD 01/28/2021 |  | Team to continue working on resolving this issue. ¦ Ring Fence requiring a PAX ticket. | 1Y | 1Y
5 | Small Business DCO | 2021-01-25 | Andy | Complete: Create Personal CIF | Need estimate for when the service will be completed. | High | Closed | 2021-01-26 | confirm that this will be ready for EOW or Feb 02. | 2021-01-28 | 1) Andy will have the team update the RAML for the create and update personal CIF for EOD Jan 28 2) Ian to send the details for the matrix to identify relationship to the business (role function ID mapping); currently in review with Candyse, will be completed afternoon Jan 28 3) Andy will advise the team if the full service will be available for 02012021, by EOD on Friday Jan 29 |  | Still being implemented; on track for tomorrow. Slight risk - Testing. | 2Y | 2Y
6 | Small Business DCO | 2021-01-22 | Andy | Update about service availability | Sprint 7 Blockers: RAML/Mock or full services for blocked T24 stories, and their availability for Sprint 7. | High | In Progress | 2021-01-29 | Andy to send note to the team to advise, EOD on Friday | 2021-02-01 | 1) Andy to confirm the following dates: 2) Andy will have the mock services available for Feb 02. 3) Andy will have the full services available for Feb 05. |  | Team to test Feb 1, still on track for Feb 02. | 3Y | 3Y
7 | Small Business DCO | 2021-01-25 | Keith | Complete T24 specific changes for CH33-part3 | update the customer services and finish internal review | Medium | Closed | 2021-01-26 |  | 2021-01-28 | 1) Keith to facilitate a few changes as per Lisa's request. 2) Lisa to review the details from Keith. | 2021-01-28
8 | Small Business DCO | 2021-01-25 | Keith | Handover T24 specific changes for CH33-part3 to RingFence |  | Medium | Closed | 2021-01-29 | On track to deliver | 2021-01-28 | 1) Lisa to send Chix the BRD to draft the test cases, by EOD Jan 29. 2) Chix to provide feedback and buid test cases by EOD Feb 05.* | 2021-01-28 | *The QA Team requires a 5-day delivery window from the time of receipt.
9 | Small Business DCO | 2021-01-22 | Ian H. | Custom Navigation use cases | Provide summary of custom navigation use cases and requirements | Medium | In Progress | 2021-01-29 | This has been handed over from Roland; Ian needs to review the information with the internal teams first. | 2021-02-04 | 1) Ian to have an internal meeting with Sandra / Kelvin this week. 2) Ian to send the details to Kendyl et al. 3) Kendyl to review with the team and advise if there additional questions and provide sizing and impacts the May 03 Go-Live.* |  | Decision from Kendyl: Any format for the details will suffice. Note from Sandra: If this item doesn't fit into the schedule, we will need to escalate this discussion because of its importance. | 4Y | 4Y
10 | Small Business DCO | 2021-01-25 | Ian H. | Sprint 6 blockers | Advised that 2 were going to be completed, and one would need rescheduling | High | Closed | 2021-01-29 | Follow up on the items for Sprint 6. | 2021-01-28 | 1) Ian to review the Sprint 6 stories and provide update in JIRA. | 2021-01-28
11 | Small Business DCO | 2021-01-25 | Chix | Happy Path Test Users | Test users needed for sprint development commencing Feb 3 | Medium | In Progress | 2021-02-02 |  | 2021-01-28 | 1) Chix to setup time with Chad to validate the requirements. |  |  | 5Y | 5Y
12 | Small Business DCO | 2021-01-25 | Chix | Non-Happy Path Test Users | Test users needed for sprint development commencing Feb 17 | Medium | Open | 2021-02-16 |  | 2021-01-28 |  |  | Monitor progress | 6Y | 6Y
13 | Small Business DCO | 2021-01-25 | Chad | Okta Integration | Need details on the scope, integration and consumption for the OKTA integration. | High | Pending | 2021-01-29 | Awaiting meeting invite from IAM team | 2021-01-28 | 1) Madeleine confirmed 10:00 02022021 2) Ensure everyone is invited, Chad, Kendyl, Reinhardt, Dino, SM, Tony Fang*, and Madeleline's Team. SM to follow up about Andy* 3) Madeline to update the meeting invite details and participants. |  | Ensure that we repurpose CWBSB-129 as the OKTA integration changes the need for this work. | 7Y | 7Y
14 | Small Business DCO | 2021-01-28 | Ian H. | Sprint 7 blockers: Requirements | Working on completing these items | High | Closed | 2021-01-29 | Work through the remaining items blocked in JIRA | 2021-02-01 |  |  |  | 8Y | 8Y
15 | Small Business DCO | 2021-01-28 | Kelvin | Sprint 6 Blockers: UX | Working on completing items CWBSB-294 | High | Closed | 2021-01-29 | Sent feedback Jan 30 | 2021-02-01 | 1) Kelvin to complete the story and provide details in JIRA | 2021-01-30 | Additional documentation to be completed by EOD Feb 01.
16 | Small Business DCO | 2021-01-28 | Kelvin | Sprint 7 Blockers: UX | Working on completing items CWBSB-243 and 244 | High | Closed | 2021-02-02 | 1) Waiting on Creative Services for the GIF. | 2021-02-01 | 1) Kelvin to complete the story and provide details in JIRA |  | May take upto a week* Follow up with Kendyl re: Impacts | 9Y | 9Y
17 | Small Business DCO | 2021-02-01 | Chad | Field Spec to Mule API mapping | Needs the team | Critical | Open | 2021-02-02 | 1) Chad to send that out to the CWB team today. 2) Ian and Keith to review the document 3) Follow up with Kendyl about the impacts to moving this into Sprint 7 | 2021-02-01 |  |  | These items were scheduled for sprint 6, and will be rolling over sprint7 | 10Y | N
18 | Small Business DCO | 2021-02-04 | Ian H. | Codat Integration Meeting | Need the details to | [8 empty] | 11Y | N
19 | Small Business DCO | 2021-02-03 | Keith | Avoka Mapping Questions |  | High | In Progress |  | 1) Working with IAN |  |  |  |  | 12Y | N
20 | Small Business DCO | 2021-02-03 | Keith | Supporting BIG on SBDCO service questions | [9 empty] | 13Y | N
21 | Small Business DCO |  | Ian H. | PAN
22 | Small Business DCO | 2021-02-04 | Chad | Create Business Account | Needs this to be reviewed by Ian | [8 empty] | 14Y | N
23 | Small Business DCO | 2021-02-04 | Sandra | Product Selector landing page |  |  |  |  | 1) Sandra to provide the date for delivery |  |  |  | In sprint 8. | 15Y | N
24 | Small Business DCO | 2021-02-04 | Sandra | Wireframes for guided experience for Product Selector (questions asked to clients to offer a product) |  |  |  | 2021-02-16 | 1) Sandra to provide the date for delivery |  |  |  | In sprint 9. | 16Y | N
25 | Small Business DCO | 2021-02-04 | Kendyl | Lessons Learned sessions | Request to shift to increase the time to 45min | [8 empty] | 17Y | N

## DropDowns (hidden)
Project_Name | Risk_Category | Risk_Status | Risk_Severity | Risk_Probability | Risk_Strategy | Issue_Status | Issue_Severity | Issue_Probability |  | Imped_Category | Imped_Status | Imped_Severity
Small Business DCO | Vendor | New | Very Low | Very Low | Avoid | New | Very Low | Very Low |  | Vendor | New | Very Low
Warranty DCO | OCM | Open | Low | Low | Transfer | Open | Low | Low |  | OCM | Open | Low
Data Migration DBX | Communication | Escalating | Moderate | Moderate | Mitigate | In Progress | Moderate | Moderate |  | Communication | In Progress | Moderate
Project D | Cost | Mitigating | High | High | Accept | Pending | High | High |  | Cost | Pending | High
Project E | Deployment | Monitoring | Very High | Very High | Share | Escalated | Very High | Very High |  | Deployment | Escalated | Very High
| Facilities | Closed |  |  | Exploit | Closed |  |  |  | Requirements | Closed
| Infrastructure |  |  |  | Enhance |  |  |  |  | Infrastructure
| Integration | [8 empty] | Integration
| Benefits | [8 empty] | UX / UI
| Quality | [8 empty] | Quality
| Resources | [8 empty] | Resources
| Schedule | [8 empty] | Schedule
| Scope | [8 empty] | Scope
| Technical |  |  |  |  | Decision_Status |  | Action_Priority | Action_Status | Benefits / Objectives
| Training |  |  |  |  | New |  | Low | New | Training
| Objectives |  |  |  |  | Open |  | Medium | Open | Business Approval
[6 empty] | In Progress |  | High | In Progress
[6 empty] | Pending |  | Critical | Pending
[6 empty] | In Review |  |  | Escalated
[6 empty] | Escalated |  |  | Closed
[6 empty] | Approved |  |  | Cancelled
Revoked
Cancelled