Digital Program

Digital Client Onboarding Project Closure Report

December 17, 2020

General Information

| Project Name | Digital Client Onboarding |
| --- | --- |
| Project Manager | Kate Jekabson |
| Project Owner | Christina Mullin/Jason Bond |
| Project Sponsor | Jeff Wright/Azfar Karimuddin |

Document Development History

Build Status:

| Version | Date | Author | Reason | Sections |
| --- | --- | --- | --- | --- |
| 1.0 | 17-12-2020 | Kate Jekabson | Initial Release | All |

Contents

Project Manager’s Report	4

Review of Project <or Project Phase> Objectives	5

Scope	5

Time	5

Cost	6

Benefits Realized	6

Lessons Learned	6

Issues That Occurred	6

What Worked Well	7

Transition Items	7

Sign-off	8

The purpose of the Project Closure Report is to review how the project performed against its objectives, schedule, cost, benefits realized, and lessons learned.

# Project Manager’s Report

The Digital Client Onboarding Closure Report will include the following phases:

- Motive Full Deployment

- Personal Online

- Personal In-Branch

- Small Business Online

- Small Business In-Branch

**Blue text is included for illustrative purposes and must be removed before finalizing the document

Provide a summary of how the project performed and the deliverables it achieved.  For example:

The project achieved its objective of improving the end-user experience and expanding the functional capability and utility of the existing XX Portal application that has been established and incrementally evolved through earlier releases.  This release included refreshing the look and feel of the user interface and adding document management features among other functional enhancements to increase the utility of the system for XYZ industrial accounts and its Key Accounts team.

The implementation phase was completed with the following deliverables:

- XX Release 6.0 SIT Release

- XX Connects Release 6.

- User Acceptance Test Release

- XX Connects Release 6.0 Production Release

- XX Connects Release 6.0

- Implemented Production System

- End Project Report

This project (or this project phase) started on May 9, 2016 and finished on October 28, 2016, with the delivery of Post Go-Live Release 6.1 into production and the end project report by October 28; 4 weeks beyond its baseline end date.  The time and materials project was also completed at 32.5% over its baseline budget but within 3% of its approved budget (set out by change addendum 01).  The variance reasons were data quality improvement support that was added during the UAT phase and functional enhancements that were implemented during the UAT and post-go-live support phases.

In reviewing the project issues and receiving AB key stakeholder feedback, the lessons learned for future similar projects were:

- If a major scope change occurs, collaboratively issue an updated design specification.

- Develop a matrix of statuses and state change triggers in the requirements or design phase.

- Consider the segregation of SharePoint applications and define memory quotas for applications.

- Weekly sprints with sprint demos encouraged early client feedback and collaboration.

- Established, compressive .Net application code framework improved productivity.

- Jointly accessible incident log was critical to effective collaboration throughout the testing and PGLS phases.

# Review of Motive Full Objectives

Provide a description of the project objectives (Scope, Time, and Cost) and the benefits realized.  See blue text under each for example.

## Scope

Text…

Provide a list is deliverables and their outcome.

| Improved Customer Access and Information Customers have improved access to information related to their sites and projects. | Improve Customer access to information related to their sites and projects. - Provide customers with access to documents related to their sites - specifically ESA documents. - Provide customers with access to documents related to their projects in a single location. - Provide customers with additional information on project statuses / milestones. - Provide customers a visual representation of where their project is in the process. |
| --- | --- |
| Enhanced XX Connects Portal functionality | Enhance the functionality of the XX Connects Portal. - Display distributed generation (DG) information. - Improve search functionality. - Display additional information about project types and expected timelines. |

## Time

The Motive MVP version was launched with a Friends and Family pilot on June 22, 2020 and the full launch Canada Wide on July 13, 2020.

Provide a description on the outcome of the project schedule.  For example:

The XX Connects Release 6 system was planned to be implemented in September 2016.  It was actually implemented into production on September 30, 2016.

The project, including four weeks of post go-live support, was completed 4 weeks beyond its baseline end date of October 2, 2016 on October 28, 2016.  Change addendum 01 was approved to revise the critical milestones as well as scope and budget.

| Critical Milestones | Original Delivery Date | Approved Delivery Date | New and Actual End Date |
| --- | --- | --- | --- |
| Build (and Unit Test) | 2016-07-08 | 2016-07-08 | 2016-07-08 |
| System and Integration Test | 2016-07-08 | 2016-08-02 | 2016-08-02 |
| User Acceptance Test | 2016-08-03 | 2016-09-28 | 2016-09-28 |
| Cutover | 2016-08-18 | 2016-10-28 | 2016-10-28 |
| Project Closure | 2016-10-02 | 2016-11-07 | 2016-10-28 |

## Cost

Provide a report of how the project budget was utilized to fund the project activities. For example:

The project was completed 32.5% over its baseline time and materials budget and within 3% of its approved time and materials budget:

| Budget Item | Budget | Approved Budget | Estimate at Completion | Variance at Completion |
| --- | --- | --- | --- | --- |
| Detailed Functional and Technical Design | $0.00 | $0.00 | $5,873 | -$5,873 |
| Build and Unit Testing | $260,300 | $260,317 | $276,488 | -$16,171 |
| System and Integration Testing | $168,000 | $168,000 | $113,907 | $54,093 |
| Business User Acceptance Testing | $50,300 | $201,063 | $242,596 | -$41,532 |
| Cutover | $35,700 | $7,789 | $41,137 | -$33,348 |
| Project Closure and Handover | $3,200 | $31,131 | $6,973 | $24,158 |
| Total | $517,500 | $668,300 | $690,286 | -$21,986 |

### Financial Cost Benefit Analysis

The following is a summary of the Project cost benefit analysis. Full details are available in the PMO Cost Benefit Analysis spreadsheet on the project SharePoint.

| Measure | Result | CAP/NIE | Comment |
| --- | --- | --- | --- |
| Implementation Cost | $ |  |  |
| Annual On-going Cost Summary (5-year view) | $ |  |  |
| Additional Revenue & Cost Savings (5-year view) | $ |  |  |
| ROI | % |  |  |
| Payback Period | Years |  |  |

## Enabled or Realized Benefits

Provide a list of the benefits that were identified with the Project and whether the benefit was realized after go live or if the benefit will be realized at a future date. You can copy the benefits table from your project charter and paste it in here.

| Benefit Summary | Tangible / Intangible | Key Organization Goals | Target Metric to be Achieved | Report Date on Target Metric | Benefit Owner | Comments / Updates |
| --- | --- | --- | --- | --- | --- | --- |
| The Viking – ECN Acquisition - Strategically increase geographic mix | Tangible | Diversifies our presence geographically | Western Canada: 25% Ontario: 55% Quebec: 11% Maritimes: 9% | Jun/2021 | Stephen Murphy |  |
| Western Union Wires – New Generation CWB will activate 1,000 clients in 2017 | Tangible | Grows our number of full-service clients | 1,000 clients ` | Realized in Oct/2019 | Jeff Wright |  |
| NHA Mortgages Backed Securities - Introduction of a competitive “A” mortgage product to drive incremental growth to | Tangible | Grows general commercial loans | Exceed Optimum Mortgage’s growth goal of 21% in fiscal 2017/2018. This will be measured by calculation of overall full year growth at fiscal year-end 2018 (2016 vs 2017 and 2017 vs 2018) | Realized in Jun/2020 | Lester Shore |  |
|  | Choose an item. | Choose an item. |  |  |  |  |

# Lessons Learned

Motive MVP/MMP

| Lessons Learned | What Worked Well |
| --- | --- |
| The timelines were very tight and caused requirements to be missed, should allocate sufficient time to draft and review requriements. | The teams worked well together |
| Identify and communicate dependencies to next sprint deliverables and activities earlier in the sprint planning. | Setup Retrospectives to improve the process after each sprint. |
| More time between Temenos BAs and CWB BA's to help better plan/develop stories. |  |
| Ensure that all meeting requests include a detailed purpose and agenda. This helps people to prepare in advance. |  |

Provide a list of issues that occurred and what worked well for future similar projects.  For example:

These were identified on October 24, 2016 in a joint lessons learned workshop involving the project manager, project owner, and project team members:

## Issues That Occurred

The issues that were raised in the lessons learned workshop at the end of the project were:

- XXX De-scope – The decision to de-scope XXX from the project after the Build and Unit Test phase started led to design gaps that created data quality issues and functional changes discovered throughout testing:

  - Data Quality Issues, e.g. request type mapping, etc.

  - Functional Enhancements, e.g. add new companies, request status, new data services, & ETL, interfaces, etc.

Lesson Learned: If a major scope change occurs, collaboratively review and make changes to the approved design spec and issue an updated design specification.  This will reduce the number of incidents (defects and enhancements) raised in testing and the time and money spent will preserve the budget and schedule of the testing and PGLS phases.

- Data Architecture - did not reflect CIS well enough.  Existing CIS data could have been reused in the design instead of re-entered.

Lesson Learned: Identify reporting requirements sooner.  Also examine enterprise systems as sources of truth in the business requirements and/or design phases.  This will improve the reuse and validity of system data and likely reduce development and testing effort.

- Key Accts Project Lifecycle-related defects arose during testing.  A better understanding of the Key Accts project lifecycle (in the design phase), including what triggers caused what project state changes, would have some of the data quality and functional enhancements raised during testing.

Lesson Learned: Develop a matrix of statuses and state change triggers (in business terms) in the requirements or design phase.

## What Worked Well

Text…

- Weekly Build Sprints and Demos – kept the team productive by setting weekly development tasks, demonstrated progress, and elicited client feedback on UI and functions ahead of the formal SIT and UAT phases.

Lesson Learned:  Weekly sprints with sprint demos during the Build stage will demonstrate progress, address design/build issues early and encourage early client feedback and collaboration.

- Pace of Sprint Demo and UAT Issue Turnaround – There was a fast pace of delivery of sprint functionality during Build and requested enhancement during UAT and PPGLS.  This (as well as the pace of build sprints) was enabled by the reuse of the .Net Code Frameworks that had been put in-place by AE Connect Release 5 project.

Lesson Learned:  An established, compressive .Net application code framework will improve sprint and testing incident resolution productivity.

# Transition Items

The following are outstanding items  identified during the project ((Change Request, Risk, Issue, Action, Dependency, Decision, Expense Item) that have been transitioned to the Sustainment Team for follow up and resolution:

| Outstanding Items | Description | Sustainment Owner |
| --- | --- | --- |
| Choose an item. | <enter description of outstanding item and action required> | <Sustainment Owner Name> |
| Choose an item. |  |  |
| Choose an item. |  |  |

# Sign-off

Authorization to Complete Project:

Sign-off (either digital approval, email or penned signature below) is required from the following people to confirm that the project is now complete:

|  |  |  | or |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| <name, title> Executive Sponsor |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
|  |  |  | or |  |  |  |
| <name, title> Project Owner |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
|  |  |  | or |  |  |  |
| <name, title> AVP, Program Management |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
|  |  |  | or |  |  |  |
| <name, title> Sr. Manager, PMO |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
|  |  |  | or |  |  |  |
| <name, title> Manager, PSC |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |