## Sheet1
Small Business DCO Requirements - Action Log
# | Category | Headline | Description/Question | Status | Status Date | Action log | Reference/Sharepoint link
1 | Business profile | Codat integration | Need to confirm we are targeting Codat integration for release of SB DCO, with purpose of pulling/populating business profile information. | Closed | 2020-08-18 | To do: business/program decision - Christina/Stacy Action review 7/3 Requirement stands: pursue Codat integration as part of DCO with the aim of: (1) Populating business profile information (2) Retrieving financial statements for reference by CWB. This supplements the business verification, but also provides background info that can be leveraged in developing the ongoing relationship. Follow up: IH follow up with RT/integration. 7/6 KB to follow up on Temenos side regarding the available functionality/data via this integration. 8/4 (IH) tech review held 7/31; follow-up with RT and Temenos team scheduled 8/5
2 | Business profile | Consent to retrieve info via Codat | Do we require an explicit consent to pull business profile info via Codat? Can we/should we capture an ongoing consent at this stage, for two-way exchange of financial/transactional data via Codat? | Closed | 2020-09-01 | Action review 7/3 Proceeding with Codat Follow up: IH - pursue regulatory/legal opinion on necessary consent. To discuss at business meeting 7/22 8/4 (IH) confirmed at business mtg 7/28 that will need 2 consents - initial access and ongoing connection. With business/regulatory team for review of wording. 8/18 (IH) eConsent page for Codat drafted with 2 options - for review with CM/SS and team 8/20 1/9 (IH) item closed as consent page was ok'd for Sprint 3 starting 8/31. | e-Consents and Certifications
3 | Business verification | Name search for sole proprietor | There is no registry search/report for a sole prop, but do we need to (always) request a name search for a sole prop, even though many may have no registration? Does Thirdstream Business Search even support Sole Prop? | Closed | 2020-07-03 | To do: (1) Verify current practice for Sole Prop (project team). (2) If name search required/preferred, verify capability of Business Search service with Thirdstream to support this. IH 7/3: API can search for the Sole Prop name reg (confirmed by DH/Thirdstream); if no results returned, will just need to continue the process with personal verification of the proprietor (IDV, credit check, fraud check on the person).
4 | Business verification | Documents upload and storage | For required docs supplied by the client, will use existing Temenos function (widget). Confirm - can documents be persisted in Temenos Infinity platform long enough to be inspected/reviewed as part of a manual review process, if necessary (likely Workspaces)? What mechanism/repository do we need to "transfer" uploaded docs to CWB side, for future reference? Is it sufficient to store along with consolidated application data in Filenet? (Intended for auditability, not quick/frequent access) | Open | 2020-09-01 | To do: (1) Temenos to confirm using their "widget" will allow us to flow uploaded documents through to Workspace queues, if manual inspection is required. (2) Business/program & technical decision required for document retention and future access. Action review 7/3 Our approach should be to AVOID uploading documents if at all possible: rather, gather the needed data points via the screens in the process and have the authorized applicant certify (via digital or e-signature) the data as entered. If upload becomes unavoidable (e.g. regulatory) then we will need a way to identify and persist the document for later inspection and retrieval. Follow up: IH and team to review with regulatory and other business teams as needed. To discuss at business meeting 7/22 8/4 (IH) looking at possibility of post-upload if needed (e.g. jurisdictions where registry does not return all required info, such as shareholders). 1/9 (IH) CW verifying with AML on recommended values DCO will set in T24 for legal ID/Doc Name and Verification fields; current plan is to use registry data (from Business Search API) as our validation. Any entities that are unregistered (partnership or sole prop) would default and go to manual review, then CWB would contact the client for docs.
5 | Business verification | Document generation vs upload - banking resolutions and partnership agreements | Some required documents for corporations and partnerships may be provided via upload if they already exist OR may be supplied/generated by CWB if they do not. These docs are not optional, as they are part of verifying the business, the authorized signers of the business and the ownership. Corporation: banking resolution - list of all authorized signers, directors; certification/signature of (at least) one director of the corporation. - This is required by the bank but also for the corporation's own record-keeping, so implies that we would need to generate an actual (printable) form. - If we do, is it enough for our purposes to capture e-consent/certification of the individual making the application (client can then print and sign for their own records)? Or do we need a formalized/choreographed e-signature? - If client uploads their own document, how do we verify/validate the contents? Implies this would have to be a manual inspection, as there is no prescribed standard format/content that could be machine read. - Is it an option to capture an e-consent/certification along with the names of the authorized signers & directors (to support necessary IDV/fraud checks) and allow the client to provide the supporting doc later, before the account is "activated"? Partnership: partnership agreement - list of partners, certification/signature of all partners. Similar questions to banking resolution - how to verify an uploaded doc; can we proceed based on e-consent if we produce the document, or is full e-signature required; can we allow the client to provide the doc later? | Open | 2020-09-01 | Existing forms: Banking Resolution 4015, Partnership Agreement 4012. To do: business/program & technical decisions (1) Confirm handling for required docs in both cases, i.e. uploaded or generated. (2) Confirm sufficiency of e-consents/certifications, or is there a need for e-signature? (3) Confirm if manual inspection required (to verify contents) for ALL uploaded docs. (4) Confirm if possible to defer acquisition of actual docs until after DCO process (allow e-consent/certifications only in order to complete the process). Action review 7/3 As with docs upload, our approach will be to avoid form generation, gather the needed data points via the screens in the process and have the authorized applicant certify (via digital or e-signature) the data as entered. The T&C to which the client is agreeing should include all necessary disclosures, based on the entity type etc. and the acceptance can be summarized at end of process if necessary for the bank's records. Follow up: IH and team to review with regulatory and other business teams as needed. Once we have a consolidated set of certifications required, need to verify whether digital acceptance (i.e. check box) is enough, or do we need full e-signature? If the latter, should aim to use E-Sign Live as already implemented in CWB. 8/4 (IH) looking at possibility of post-upload if needed (e.g. jurisdictions where registry does not return all required info, such as shareholders).
6 | Business verification | Verifying ownership in different jurisdictions | We are required to verify all beneficial owners of a corporation or partnership, i.e. anyone with >=25% ownership. For some provinces (e.g. AB) we will receive the shareholder % via the registry report (COVR report), but for others (e.g. BC, ON) this data is not part of the registry report. In these other jurisdictions, we would need to ask for client to upload a doc such as a copy of the Corporate Share Registry. - If client uploads their own document, how do we verify/validate the contents? Implies this would have to be a manual inspection, as there is no prescribed standard format/content that could be machine read. - Is it an option to capture an e-consent/certification along with the names and % ownership of the beneficial owners and allow the client to provide the supporting doc later, before the account is "activated"? | Open | 2020-09-01 | Action review 7/3 See notes regarding document uploads (#4 above) Follow up: IH and team to review with regulatory (and other business areas as necessary) to confirm approach (capture data points, not upload docs) is acceptable. 8/4 (IH) looking at possibility of post-upload if needed (e.g. jurisdictions where registry does not return all required info, such as shareholders). 1/9 (IH) CW verifying with AML on recommended values DCO will set in T24 for legal ID/Doc Name and Verification fields; current plan is to use registry data (from Business Search API) as our validation. Any entities that are unregistered (partnership or sole prop) would default and go to manual review, then CWB would contact the client for docs.
7 | Business verification | E-consents/certifications or e-signature | Per doc verification items (5 & 6), along with other points in the process that might require consents or certification by the client, do we need a full, choreographed e-signature solution, or will e-consent/certification be sufficient? Technically, how does recording/retention of e-consent/certification fit with identity and access management (IAM) - Okta in future? | Closed | 2020-09-01 | Per business reviews week of Jun 22-26, premise of using e-consents where possible for DCO is OK, but need to ensure we are covered from regulatory and legal POV in all scenarios. To do: (1) Review draft consents/certifications with project team and refine. (2) Review nature/placement of consents with business SME (David Chesworth, Regulatory) (3) Review legal coverage? (4) Technical handling (IAM)? Action review 7/3 See notes regarding doc generation and certifications (#5 above). Follow up: IH and team to review with regulatory and other business teams as needed. Once we have a consolidated set of certifications required, need to verify whether digital acceptance (i.e. check box) is enough, or do we need full e-signature? If the latter, should aim to use E-Sign Live as already implemented in CWB. To discuss at business meeting 7/22 8/4 (IH) Pursuing approach is to use digital certifications only (no e-sig); with business/regulatory team for review of wording. 1/9 (IH) item closed as disclosures/certifications/signature page was ok'd for Sprint 3 starting 8/31. | e-Consents and Certifications
8 | Business verification | E-certification of Tax Residency for a business entity | A corporation or partnership will require certification of the entity's tax residency being Canada, and that they are "engaged in an active trade or business". We can likely solution these criteria as part of pre-qualification/screening, and capture required data (Business Number, in addition to business name/address/contact info) in the business profile step. Is an e-certification of tax residency adequate, as opposed to generating the RC519 form and having it e-signed? Should an entity with a different tax residency (or different entity classification) be redirected from pre-qual/screening to the supported onboarding process? | Closed | 2020-09-01 | To do: (1) Review approach with project team and refine. (2) Confirm approach and sufficiency of pre-qualification and e-consent in lieu of full RC519 form with business SME (Pearl Frederick, Regulatory). Action review 7/3 See previous notes re docs/forms/certifications (#4, 5, 6, 7 above) Follow up: IH and team to review with regulatory. 8/4 (IH) with business/regulatory team for review of wording. 8/18 (IH) certifications page drafted for review with CM/SS and team 8/20 1/9 (IH) item closed as disclosures/certifications/signature page was ok'd for Sprint 3 starting 8/31. | e-Consents and Certifications
9 | Product selection / account opening | Handling of value-add/ancillary business products/services | One or more of the "menu" of available value-add/ancillary business products/services (e.g. merchant services, wires, payroll etc.) may be of interest to a business onboarding through DCO. Should these be offered up front, as part of product selection? If so, how do we handle gathering of required supporting data, such as anticipated frequency/volume? NOTE: AML requirements for the account activity, but also specific products/services: Avg Monthly Cash Deposits Avg Monthly Cheque Deposits Avg Monthly Incoming Wires Avg Monthly Outgoing Wires Where there is a third-party provider involved, how do we package up the information and turn it into a "referral"? | Open | 2020-08-18 | To do: (1) Review approach with project team and refine. (2) Build out requirements (Product Catalogue and Product Selector) Action review 7/3 Selection of complementary products/services should be part of Product Catalogue and Product Selector. In addition, we should be looking to the later (Account Options) step similar to the personal process, to gather at least basic data required for provisioning of products/services (in addition to those already in the personal flow, like cheques, debit cards etc.) As the DCO audience could be anywhere (i.e. not necessarily within reach of a branch) we will likely need to assume off the bat that online/digital banking access is required and will be "bundled" with the account(s) being opened. Follow up: IH to work with SK on Product Catalogue and Product Selector requirements for SB. 8/4 (IH) Small busines products info received from Product 7/31; finalization of Product Selector design in process with SK. 8/18 (IH) Decision tree for Product Selector guided questions drafted for review.
10 | Product selection / account opening | Capturing intended use of account | This value is required (AML) on a per-account basis, so where should it be captured? Does it make sense to have it up front, with product selection? | Open | 2020-08-18 | To do: (1) Review approach with project team and refine. (2) Build out requirements (Product Catalogue and Product Selector) From SK 7/3: Our original specs for Motive DCO Full used the product selector for selection, but included a product summary page within the Primary Applicant form. The product summary was where we were planning to capture intended use and joint account status. We’ll be using this pattern for CWB Personal DCO as well, and I suspect it may also work for small business, minus the joint application status. The justification for this was that the product selector could focus entirely on collecting the applicant’s product choices without collecting any personal information (like intended use). Essentially during product selection, they haven’t actually started an application yet. Once the client commits to apply, by means of the checkout process, we start the Primary Applicant form which is all about collecting personal information. Action review 7/3 Not covered specifically, but probably makes sense to use a similar pattern for SB as described above. Follow up: IH to work with SK on Product Catalogue and Product Selector requirements for SB. 8/18 (IH) design pattern for SB Product Selector reviewed/confirmed with team, based on personal. Positioning of intended use question still to be confirmed (within Prod Selector or in DCO flow).
11 | Account opening/operating | Signature card | A client signature, or multiple signatures where there are multiple signers (captured on a signature card) are required for new business chequing accounts. Can this be dealt with post-funding, assuming the client will still need to provide signature(s) in order to operate the account? Does this have to entail physical attendance at a branch, or can scanned signatures, submitted electronically, suffice? | Open | 2020-06-26 | To do: (1) Review approach with project team and refine; business operational review may be necessary. (2) Build out requirements. Action review 7/3 Not covered - need to follow up via email. 7/7 asked CW to look into virtual branch/current practice.
12 | Personal Verification | Credit bureaus | Current policy (and T24 CIF requirements) mean that anyone who will be an authorized signer on a new business account, and is a beneficial owner (>=25%) and/or director (of a Corporation) requires an iDecision/bureau. Should we use 600 as the threshold FICO score to determine whether the application requires manual review? If any one (or more) authorized person(s) has an unsatisfactory score, should we kick out to a manual review, rather than a hard decline? Do we have any grounds for requesting a policy review, to exempt applicants onboarding through DCO from needing iDecision/Bureau, given the pre-screening and other due diligence checks, and the small nature of the target businesses we will onboard this way? | Open | 2020-08-18 | To do: (1) Review approach with project team and refine; business operational review may be necessary. (2) Build out requirements. Action review 7/3 IH and team to make recommendations to business for SB DCO. 8/18 (IH) signers/non-signers grid drafted for team review: generally, only signers will require bureau, to meet current policies.
13 | Personal Verification | Fraud checks | Per policy, there are limited attributes we need to capture when an individual associated with a business will not have signing authority on the new business account(s): essentially just their name and role (e.g. Director, Officer, Non-beneficial owner <25%), although the names must be validated via corporate docs (either from the registry search results, or an uploaded document). As part of DCO, should we gather additional attributes (e.g. DOB, address, phone/email) in order to run these individuals through the due diligence/fraud checks (Thirdstream and SAS AML)? | Open | 2020-08-18 | To do: (1) Review approach with project team and refine; business operational review may be necessary. (2) Build out requirements. Action review 7/3 IH and team to make recommendations to business for SB DCO. To discuss at business meeting 7/22 8/18 (IH) signers/non-signers grid drafted for team review.
14 | Business verification | Thirdstream Business Search API | 3S indicated there is some decisioning logic related to use of this service | Open | 2020-07-15 | To do: Follow-up with 3S to understand their decisioning logic. 7/15 based on Contract Defn meeting we will build any decision logic on the Temenos side and just consume the data returned from the 3S API (to be confirmed).
15 | Business verification | Business Pre-search requirements | From Contract Defn meeting 7/15. Requirements to be clarified: - Always require reg# (and jurisdiction) in order to do Pre-search? Pro: much more focused search, expect 1:1 result, works for Sole Prop with only a name registration, as there is still a reg#. This is the recommended approach from 3S, as searching by name and jurisdiction only could return many results that would need to be handled somehow in the UI. Con: some applicants may not have reg# to hand. - If Registration Status returned by the Pre-search is anything other than "ACTIVE", should this go to manual review or be an automatic rejection? - Should we build in a screen edit to disallow selection of QC as the jurisdiction? - What about federal (CA) - can we onboard an entity that only has a federal registration? | Open | 2020-09-01 | 7/20 (IH) emailed Christina and Stacy questions on required fields for Pre-search and handling of status other than ACTIVE. 8/18 (IH) Candyse confirmed with business that there may be (infrequently) non-registered businesses onboarded (Gen Partnership or Sole Prop), but policy requires that Corporations be registered in province where they operate. Still need to confirm handling for non-registered, or where no result returned from business search. 1/9 (IH) verifying with AML regarding non-registered - proposed to default "obtain from client" and send to manual review for follow-up (to obtain docs)
16 | Business verification | Business Order (COVR) requirements | Need to confirm which fields retrieved from the COVR order should be compared with client-entered data. - Consider differences in data entry and how it's recorded in the registry DB, e.g. addresses - could we compare postal code only? - Same goes for names, e.g. could we compare last name or last name and initial only? | Open | 2020-07-15
17 | T24 mapping (Business CIF) | Hold Type field | (Sent to Keith King) Hold Type field – we will probably want to default a value for DCO, but can you confirm what the hold type set on the CIF applies to? Does how the new account is funded make a difference to the limit that might be set at this level? (In some cases, a new business account might be funded via electronic funds transfer, so potentially we could grant a higher limit when those funds hit the new account). | Open | 2020-09-01 | (From KK 1/9) HOLD.TYPE is only used by Remote Deposit Capture. EFT funds do not fall under this. A business decision will be required to provide a defaulted value.
18 | T24 mapping (Business CIF) | Reason Opened field | (Sent to Keith King) Reason Opened field - may not need this assuming we have unique inputter ID - but what happens if someone in branch updates a CIF that was originally created through DCO? How is the origin of the customer creation (DCO vs In Branch) tracked in the Motive/Personal DCO? | Closed | 2020-09-01 | (From KK 1/9) While working with Information management on some of the onboarding reports they found it difficult to confirm what clients/accounts where opened using the DCO process. What happens is if a client/account is updated by a different user the inputter will change on the account. During our discussion it seemed like a good idea was to use the Reason open code to identify DCO on boarded clients. CLOSED 11/18 - now have the DCO Channel field for recording LOB.
19 | T24 mapping (Business CIF) | Relation Customer field | (Sent to Keith King) Relation Customer field - is Avoka really the source? T24 will need to create the individual CIFs and then the Business CIF before it can create the link - is this really orchestrated by Avoka? | Open | 2020-09-01 | (From KK 1/9) Since the relation customers will need to be created using Avoka, they would need to store the CIF’s that will need to be used for the Account opening and Business CIF creation process (unless BIG can provide a solution.) T24 would not be able to handle this type of request.
20 | Workspaces | T24 fields to update via Workspaces (applications in Manual Review) | Need to confirm format and timeline for providing requirements around populating Manual Review items in Workspace queues - data that should be made available in Workspaces, also any (T24) fields that we should be able to update directly from Workspaces, such as Business CIF fields Legal ID, Legal Doc Name, Verification of Ownership. | Open | 2020-09-01
21 | T24 mapping (Business CIF) | Communications Details fields | (Sent to Steve K and CW) wondering a couple of things about the T24 Communications Details fields, specifically around how those are mapped over from DCO. I looked in the Motive journey flow and the mapping doc (similar to what Keith provided us for business). I don’t see anything in the Motive screens around specific CASL consent – the eConsents seem to refer to using personal info in the application and link into the Privacy Statement (which does include some stuff about consents for marketing purposes). Having said that, in the mapping doc it seems like there are default values for Comm Type (CWB-Motive) and Pref Channel (Email), although they say “selected by client”. Similarly, for Customer Consent it says “selected by client”, but I would have thought this would always be Y if they have checked the consent box in the UI. @Steve, do you know how these fields were actually mapped? | Closed | 2020-11-18 | Closed 11/18 - dealt with in mapping for IRD 33
22
23
24
25
26
27
28
29
30