## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of Feb 10, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 6 |  |  |  | Notes: 1. Tests executed - 100% completed 2. Refer to Defect Summary Report tab for information on defects - increase of 3 defects from last report Issues: 1. Testing coverage for different devices and browser - Chix to inform Business Team of IE (desktop) and Safari (desktop/Macbook/iPad) browser testing - Currently not in scope for our testing
Test Execution for Sprint 6
Total Tests Cases Developed | 687 | %
Passed Tests | 568 | % Passed | 82.6783
Failed Tests | 66 | % Failed | 9.607
Blocked Tests | 53 | % Blocked | 7.7147
Active/Unexecuted | 0 | % Unexecuted | 0
Total # of defects logged | 33
Total # of defects deferred | -

## Defects Status
Status of Defects logged by CWB QA Team - as of Feb 10, 2021
| Defects by Status |  | Open/Closed Defect Rate
[5 empty] | 37 | created/opened defects
[5 empty] | 4 | closed defects
[5 empty] | 33 | outstanding defects
[5 empty] | 13 | For Temenos to address
[5 empty] | 18 | For CWB to review/address (ready for UAT, field spec issues, questions, investigate further, etc).
[5 empty] | +3 | from last report
Count by Defect Category
[5 empty] | 18 | Bug (functional issue - not working as specified)
[5 empty] | 5 | CWB-BA-Review (to review and confirm with CWB BA)
[5 empty] | 2 | Intermittent (intermittent issues, cannot reproduce, etc.)
[5 empty] | 3 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
[5 empty] | 2 | Bug-UI (formatting or layout issues)
[5 empty] | 2 | Requirement-Defect (issue with functional specs that need to be corrected)
[5 empty] | 1 | Change type
[5 empty] | 33 | Total should match count for outstanding defects
For the latest list of outstanding defects, please login JIRA and use the following query for "Search" function (under "Issues"menu):
project = "CWB Small Business DCO" AND issuetype in (bug, change) AND reporter in ("Adrian Crisp", "Chix dela Luna", "Susan Bako", "Alka Patnaik", "Harpreet Dhillon", "Candyse Watkinson", "Lorraine Mcleod", "Priya Chodha", "Mary Pele", "Venkata Cherukuri", "Cheryl.Kirchmaier@cwbank.com") AND status != done AND labels not in (Accessibility) ORDER BY key DESC, component ASC, description ASC, resolved DESC
| Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
| Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
| Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
| In Test | - with Temenos for their testing

## Defect Summary
Status of Defects logged by CWB QA Team - as of Feb 10, 2021
Assignee
Issue key | Summary | Priority | Created | Reporter | Status | CWB | Temenos | Fix Version/s
CWBSB-509 | SBDCO - Authorized Signer - Invitation Email - Content in the email received is quite different than in Field Spec. | Medium | 2021-02-11 08:06 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-508 | SBDCO â€“ More About Your Business page - Saved & Resume the Application via Saved email â€“ Industry Sub Sector an Industry dropdowns are not populated | Medium | 2021-02-11 07:53 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin
CWBSB-503 | SBDCO - No Validation Message given in Field Spec but App displays the validation message | Medium | 2021-02-11 06:52 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-497 | SBDCO - Authorized Signer - Decline Page - Page layout is not correct in mobile device | Medium | 2021-02-10 11:55 | priya.chodha@cwbank.com | Backlog |  | manish.varia@accutive.com | Small Biz DCO F&F May 3
CWBSB-496 | SBDCO - Authorized Signer - Birthday & Sin Page - Next and back button button is navigating to different Pages. | Medium | 2021-02-10 11:46 | priya.chodha@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com
CWBSB-495 | SBDCO -Authorized Signer - Entry Page -Validation message with lots of space | Medium | 2021-02-10 11:24 | priya.chodha@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com
CWBSB-494 | SBDCO - Alternate IDV page - Radio button selection and Color issue. | Medium | 2021-02-10 11:08 | priya.chodha@cwbank.com | Backlog |  | manish.varia@accutive.com | Small Biz DCO F&F May 3
CWBSB-489 | SBDCO â€“ More About Your Business â€“ Validation message for additional province displayed for Sole Prop and Gen Partnership | Medium | 2021-02-10 06:51 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin
CWBSB-487 | SBDCO - Applicant - More About Your Business page - Applicant can select same province | Medium | 2021-02-09 11:16 | mary.pele@cwbank.com | Backlog | kendyl.bachelor
CWBSB-483 | SBDCO- Auth Signer Name & Address Page - Unit field accepting non-alphanumeric characters | Medium | 2021-02-09 06:45 | mary.pele@cwbank.com | Backlog | mary.pele@cwbank.com
CWBSB-482 | SBDCO- Auth Signer Name & Address Page - Missing section(sub-heading) on page | Medium | 2021-02-09 05:53 | mary.pele@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com
CWBSB-475 | SBDCO - Authorized Signer â€“ ID Scan interaction with Name and Address page â€“ Uploaded driversâ€™ license is removed | Medium | 2021-02-06 11:20 | cheryl.kirchmaier@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO F&F May 3
CWBSB-474 | SBDCO - Authorized Signer - IDScan Page - Issue with ID Upload | Medium | 2021-02-06 10:54 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-473 | SBDCO -Authorized Signer - IDScan Page - When back button is clicked Contact Info page is displayed inplace of Qualifying questions | Medium | 2021-02-06 10:10 | priya.chodha@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO F&F May 3
CWBSB-472 | SBDCO - Auth Signer - Name & Address Page -Radio buttons are default to yes when ID is uploaded in IDScan page | Medium | 2021-02-06 09:27 | priya.chodha@cwbank.com | Backlog | angela.ahn@accutive.com |  | Small Biz DCO F&F May 3
CWBSB-470 | SBDCO- Disclosures - Tax Residency page- Validation Message Needs Verbiage change | Medium | 2021-02-06 06:47 | mary.pele@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  | Small Biz DCO F&F May 3
CWBSB-469 | SBDCO - Authorized Signer - Entry Page - Validation message is not displayed when invalid token is entered. | Medium | 2021-02-06 06:30 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-468 | SBDCO- Authorized Signer - Entry Page - Progress bar is not displayed in the app but is specified in field Spec. | Medium | 2021-02-06 05:10 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-467 | SBDCO â€“ More About Your Business Page â€“ Annual Revenue â€“ Eleven digits cannot be entered efficiently (See Comments: Make to Currency Field per Spec) | Medium | 2021-02-06 04:55 | cheryl.kirchmaier@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO F&F May 3
CWBSB-466 | SBDCO- Your Role Page- Percentage Ownership field not showing mandatory message | Medium | 2021-02-06 01:56 | mary.pele@cwbank.com | Backlog |  | mary.pele@cwbank.com
CWBSB-465 | SBDCO â€“ Your Business Page â€“ Registered Street/RR Name field displays error message when not expected | Medium | 2021-02-05 11:50 | cheryl.kirchmaier@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-463 | SBDCO - Your Business Page - Issue with Special character in Bus legal Name and Trade or Operating name field | Medium | 2021-02-05 09:01 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-462 | SBDCO - More About Your Business Page - Number of employees Field is accepting invalid data | Medium | 2021-02-05 06:29 | priya.chodha@cwbank.com | Backlog |  | lucyliuxin
CWBSB-461 | SBDCO - Not Qualified Info Page - Invalid Name accepted in the Name field | Medium | 2021-02-05 03:30 | priya.chodha@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO F&F May 3
CWBSB-460 | SBDCO - Existing Customer page - Updates required for the form Values | Medium | 2021-02-05 02:45 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO F&F May 3
CWBSB-459 | SBDCO - Not Qualified Page - Name Field - The \ special character should not be accepted | Medium | 2021-02-04 10:44 | cheryl.kirchmaier@cwbank.com | Blocked | priya.chodha@cwbank.com |  | Small Biz DCO F&F May 3
CWBSB-425 | SBDCO - IDScan Page - Able to move to next screen after uploading a fuzzy picture of my ID and getting an error message | Medium | 2021-01-29 12:25 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-424 | SBDCO- Applicant & Auth Signer - Issue with Radio button selection when the ID is deleted in IDScan Page | Medium | 2021-01-29 11:57 | priya.chodha@cwbank.com | Ready for UAT | angela.ahn@accutive.com |  | Small Biz DCO F&F May 3
CWBSB-412 | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | Medium | 2021-01-27 07:48 | priya.chodha@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com
CWBSB-400 | About Your Business-CODAT page- Validation message not displayed on page | Medium | 2021-01-23 04:56 | mary.pele@cwbank.com | Backlog | mary.pele@cwbank.com
CWBSB-399 | SBDCO - Mobile Verification Page - Change of phone number did not force token - intermittent | Medium | 2021-01-23 04:54 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com
CWBSB-395 | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue | Medium | 2021-01-22 07:31 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com
CWBSB-394 | SBDCO - Qualifying questions page- Next and back button appearing twice when clicked | Medium | 2021-01-22 05:27 | mary.pele@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com