## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of Feb 25, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 7 |  |  |  | Notes: 1. Test execution completed today, Feb 25 2. Sprint 7 package includes: a. 25 user stories (16 stories have known issues) b. 5 change requests c. 6 defect fixes – for defects logged by CWB QA Team d. 14 defects fixes – for defects logged by Temenos 3. Refer to Defect Summary Report tab for information on defects Issues: 1. Testing coverage for different devices and browser - Chix to inform Business Team of IE (desktop) and Safari (desktop/Macbook/iPad) browser testing - Currently not in scope for our testing
Test Execution for Sprint 7
Total Tests Cases Developed | 732 | %
Passed Tests | 599 | % Passed | 81.8306
Failed Tests | 48 | % Failed | 6.5574
Blocked Tests | 85 | % Blocked | 11.612
Active/Unexecuted | 0 | % Unexecuted | 0
Total # of defects logged (outstanding) | 43
Defects logged from Sprint 7 | 16
Defects logged from previous sprints | 27
Note on B14: Chix Dela Luna: From Feb 19 (JIRA date)
Note on B15: Chix Dela Luna: From Feb 19 (JIRA date)

## Defects Status
Status of Defects logged by CWB QA Team - as of Feb 25, 2021
| Defects - by Status |  | Created vs. Resolved chart (Open/Closed rate)
Created defects (54)
Resolved defects (14)
JIRA counts "Done" (11) and "In UAT" (3) as resolved
|  |  |  | 43 | outstanding defects* (defects not in "done" status)
= 54 created defects - 11 defects in "done" status
*Refer to Defect Summary tab for info on OUTSTANDING defects
Count by Defect Category
|  |  |  | 22 | Bug (functional issue - not working as specified)
|  |  |  | 10 | CWB-BA-Review (to review and confirm with CWB BA)
|  |  |  | 1 | Intermittent (intermittent issues, cannot reproduce, etc.)
|  |  |  | 1 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
|  |  |  | 5 | Bug-UI (formatting or layout issues)
|  |  |  | 2 | Requirement-Defect (issue with functional specs that need to be corrected)
|  |  |  | 1 | Change type
|  |  |  | 1 | QA Lead to Review
|  |  |  | 43 | Total matches count for outstanding defects
|  |  |  | 14 | Assigned to Temenos to address
|  |  |  | 29 | Assigned to CWB to review/address (ready for UAT, field spec issues, questions, investigate further, etc).
| Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
| Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
Ready for Review
| Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
| In Test | - with Temenos for their testing
| In UAT | - with CWB for their testing
| Done | - fix for defect has been validated working, issue is resolved, defect is closed

## Defect Summary Report
Summary of Outstanding Defects - logged by CWB QA Team - as of Feb 25, 2021 (total of 43)
Assignee
| Issue key | Summary | Priority | Created | Reporter | Status | CWB | Temenos | Fix Version/s | Category
1 | CWBSB-570 | SBDCO - Applicant & Authorized Signer - Flinks Page - Business Application Time Out | Medium | 2021-02-25 03:34 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug
2 | CWBSB-569 | SBDCO â€“ Authorized Signer â€“ Name & Address page â€“ Error message is displayed regarding dropdown | Medium | 2021-02-24 12:13 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
3 | CWBSB-568 | SBDCO - Authorized Signer - Landing Page -Authorized Signer First and Last name is missing in landing page | Medium | 2021-02-24 07:27 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | CWB-BA-Review
4 | CWBSB-567 | SBDCO - Applicant and Authorized Signer - Security Question Page - Progressive Reveal and Fields behavior on navigation | Medium | 2021-02-24 06:45 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | CWB-BA-Review
5 | CWBSB-566 | SBDCO - Authorized Signer - Manual IDV Page -Discrepency with the content given in Fs and the app, email address hyperlink Issue. | Medium | 2021-02-24 03:31 | priya.chodha@cwbank.com | In Test |  | angela.ahn@accutive.com |  | Bug
6 | CWBSB-565 | SBDCO - Authorized Signer & Applicant - Contact Info Page - Issue with Mobile Number field. | Medium | 2021-02-23 11:23 | priya.chodha@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  |  | QA-Lead-Review
7 | CWBSB-563 | SBDCO - Authorized Signer -Landing Page - Landing Page format is not correct when re-sized. | Medium | 2021-02-23 10:22 | priya.chodha@cwbank.com | Backlog |  | manish.varia@accutive.com |  | Bug-UI
8 | CWBSB-562 | SBDCO - Email Notifications Source is not correct. | Medium | 2021-02-23 10:08 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug
9 | CWBSB-560 | SBDCO - Applicant - Security Question Page - Security question selection dropdown. | Medium | 2021-02-23 06:09 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  |  | Bug
10 | CWBSB-554 | SBDCO - Contact Info Page - Authorized Signer - Validation message do not end with full stop. | Medium | 2021-02-20 09:50 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  |  | CWB-BA-Review
11 | CWBSB-552 | SBDCO - Security Questions page - Next and Back buttons are navigating to different pages, not aligned with info given in FS. | Medium | 2021-02-19 12:42 | priya.chodha@cwbank.com | Backlog | Ian.Hicks@cwbank.com |  |  | Bug
12 | CWBSB-551 | SBDCO - Security question Page - Inline help is hidden behind the progress bar when browser window is re-size. | Medium | 2021-02-19 12:18 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  | Small Biz DCO F&F May 3 | Bug-UI
13 | CWBSB-550 | SBDCO - Security questions Page - Special character â€˜ is not accepted in security answer field. | Medium | 2021-02-19 12:11 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  |  | Bug
14 | CWBSB-549 | SBDCO - Security Question - Question missing 'or university?' | Medium | 2021-02-19 11:55 | cheryl.kirchmaier@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO F&F May 3 | Bug
15 | CWBSB-548 | SBDCO - Desktop - Applicant - Unable to Resume - Static text is off center | Medium | 2021-02-19 07:43 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO F&F May 3 | Bug
16 | CWBSB-547 | SBDCO - Your Business Page - Validation message not aligned with the message given in field spec | Medium | 2021-02-19 05:43 | priya.chodha@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO F&F May 3 | Bug-UI
17 | CWBSB-512 | SBDCO- Auth Signer - Issue with Radio button selection when the ID is deleted in IDScan Page | Medium | 2021-02-11 14:40 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  | Small Biz DCO F&F May 3 | Bug
18 | CWBSB-509 | SBDCO - Authorized Signer - Invitation Email - Content in the email received is quite different than in Field Spec. | Medium | 2021-02-11 08:06 | priya.chodha@cwbank.com | Blocked | priya.chodha@cwbank.com |  |  | CWB-BA-Review
19 | CWBSB-508 | SBDCO â€“ More About Your Business page - Saved & Resume the Application via Saved email â€“ Industry Sub Sector an Industry dropdowns are not populated | Medium | 2021-02-11 07:53 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO F&F May 3 | Bug
20 | CWBSB-503 | SBDCO - No Validation Message given in Field Spec but App displays the validation message | Medium | 2021-02-11 06:52 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | CWB-BA-Review
21 | CWBSB-497 | SBDCO - Authorized Signer - Decline Page - Page layout is not correct in mobile device | Medium | 2021-02-10 11:55 | priya.chodha@cwbank.com | Backlog |  | manish.varia@accutive.com | Small Biz DCO F&F May 3 | Bug-UI
22 | CWBSB-496 | SBDCO - Authorized Signer - Birthday & Sin Page - Next and back button is navigating to different Pages. | Medium | 2021-02-10 11:46 | priya.chodha@cwbank.com | In UAT | Ian.Hicks@cwbank.com |  |  | CWB-BA-Review
23 | CWBSB-495 | SBDCO -Authorized Signer - Entry Page -Validation message with lots of space | Medium | 2021-02-10 11:24 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug-Text
24 | CWBSB-494 | SBDCO - Alternate IDV page - Radio button selection and Color issue. | Medium | 2021-02-10 11:08 | priya.chodha@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO F&F May 3 | Bug-UI
25 | CWBSB-489 | SBDCO â€“ More About Your Business â€“ Validation message for additional province displayed for Sole Prop and Gen Partnership | Medium | 2021-02-10 06:51 | cheryl.kirchmaier@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO F&F May 3 | Bug
26 | CWBSB-487 | SBDCO - Applicant - More About Your Business page - Applicant can select same province | Medium | 2021-02-09 11:16 | mary.pele@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO F&F May 3 | Change
27 | CWBSB-483 | SBDCO- Auth Signer Name & Address Page - Unit field accepting non-alphanumeric characters | Medium | 2021-02-09 06:45 | mary.pele@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  |  | CWB-BA-Review
28 | CWBSB-474 | SBDCO - Authorized Signer - IDScan Page - Issue with ID Upload | Medium | 2021-02-06 10:54 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Intermittent
29 | CWBSB-472 | SBDCO - Auth Signer - Name & Address Page -Radio buttons are default to yes when ID is uploaded in IDScan page | Medium | 2021-02-06 09:27 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  | Small Biz DCO F&F May 3 | Bug
30 | CWBSB-470 | SBDCO- Disclosures - Tax Residency page- Validation Message Needs Verbiage change | Medium | 2021-02-06 06:47 | mary.pele@cwbank.com | Backlog | Ian.Hicks@cwbank.com |  | Small Biz DCO F&F May 3 | Requirement-Defect
31 | CWBSB-469 | SBDCO - Authorized Signer - Entry Page - Validation message is not displayed when invalid token is entered. | Medium | 2021-02-06 06:30 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
32 | CWBSB-468 | SBDCO- Authorized Signer - Entry Page - Progress bar is not displayed in the app but is specified in field Spec. | Medium | 2021-02-06 05:10 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Requirement-Defect
33 | CWBSB-466 | SBDCO- Your Role Page- Percentage Ownership field not showing mandatory message | Medium | 2021-02-06 01:56 | mary.pele@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | CWB-BA-Review
34 | CWBSB-465 | SBDCO â€“ Your Business Page â€“ Registered Street/RR Name field displays error message when not expected | Medium | 2021-02-05 11:50 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
35 | CWBSB-463 | SBDCO - Your Business Page - Issue with Special character in Bus legal Name and Trade or Operating name field | Medium | 2021-02-05 09:01 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  |  | CWB-BA-Review
36 | CWBSB-462 | SBDCO - More About Your Business Page - Number of employees Field is accepting invalid data | Medium | 2021-02-05 06:29 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  | Small Biz DCO F&F May 3 | Bug
37 | CWBSB-461 | SBDCO - Not Qualified Info Page - Invalid Name accepted in the Name field | Medium | 2021-02-05 03:30 | priya.chodha@cwbank.com | In UAT | priya.chodha@cwbank.com |  | Small Biz DCO F&F May 3 | Bug
38 | CWBSB-460 | SBDCO - Existing Customer page - Updates required for the form Values | Medium | 2021-02-05 02:45 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO F&F May 3 | Bug
39 | CWBSB-459 | SBDCO - Not Qualified Page - Name Field - The \ special character should not be accepted | Medium | 2021-02-04 10:44 | cheryl.kirchmaier@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  | Small Biz DCO F&F May 3 | Bug
40 | CWBSB-424 | SBDCO- Applicant - Issue with Radio button selection when the ID is deleted in IDScan Page | Medium | 2021-01-29 11:57 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO F&F May 3 | Bug
41 | CWBSB-412 | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | Medium | 2021-01-27 07:48 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  |  | CWB-BA-Review
42 | CWBSB-395 | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue (Edge Browser) | Medium | 2021-01-22 07:31 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO F&F May 3 | Bug
43 | CWBSB-394 | SBDCO - Qualifying questions page- Next and back button appearing twice when clicked | Medium | 2021-01-22 05:27 | mary.pele@cwbank.com | Backlog |  | kendyl.bachelor |  | Bug