## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of Mar 26, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 9
Test Execution for Sprint 9 |  |  |  | Notes: 1. Day 7 of test execution - 100% complete 2. Sprint 9 package includes: a. 22 stories. Only 7 will be validated during SIT, 15 will be validated during E2E b. 5 change requests. Only 3 will be validated during SIT, 2 will be validated during E2E c. 5 defect fixes – for defects logged by CWB QA Team d. 17 defects fixes – for defects logged by Temenos 3. Refer to Defect Summary Report tab for information on defects Issues: 1. Testing coverage for different devices and browser - Chix to inform Business Team of IE (desktop) and Safari (desktop/Macbook/iPad) browser testing - Currently not in scope for our testing
Total Tests Cases Developed* | 477 | %
Passed Tests | 403 | % Passed | 84.4864
Failed Tests | 40 | % Failed | 8.3857
Blocked Tests | 34 | % Blocked | 7.1279
Active/Unexecuted | 0 | % Unexecuted | 0
Total # of defects logged (outstanding) | 60
Defects logged from Sprint 9 | 22
Defects logged from previous sprints | 38
*includes regression test cases
Note on B15: Chix Dela Luna: From Feb 19 (JIRA date)
Note on B16: Chix Dela Luna: From Feb 19 (JIRA date)

## Defects Status
Status of Defects logged by CWB QA Team - as of Mar 26, 2021
| Defects - by Status |  | Created vs. Resolved chart (Open/Closed rate)
Created defects (89)
Resolved defects (37)
JIRA counts "Done" (29) and "In UAT" (8) as resolved
|  |  |  | 60 | outstanding defects* (defects not in "done" status)
= 89 created defects - 29 defects in "done" status
Count by Defect Category
|  |  |  | 21 | Bug (functional issue - not working as specified)
|  |  |  | 9 | CWB-BA-QA-Review (to review and confirm with CWB BA or QA)
|  |  |  | 23 | Bug-UI (formatting or layout issues)
|  |  |  | 3 | Requirement-Defect (issue with functional specs that need to be corrected)
|  |  |  | 2 | Intermittent (intermittent issues, cannot reproduce, etc.)
|  |  |  | 1 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
|  |  |  | 1 | Change type
|  |  |  | 60 | Total matches count for outstanding defects
Count by Defect Assignee
|  |  |  | 23 | Assigned to Temenos to address
|  |  |  | 37 | Assigned to CWB to address
- for retesting, field specs or requirement issue, to review, questions, investigate further, etc
Refer to Defect Summary tab for info on OUTSTANDING defects for more info on defect breakdown
| Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
| Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
| Ready for Review | - defect is ready for Temenos review
| In Development | - solution for defect is in development
| Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
| In Test | - with Temenos for their testing
| In UAT | - with CWB for their testing
| Done | - fix for defect has been validated working, issue is resolved, defect is closed

## Defect Summary Report
Summary of Outstanding Defects - logged by CWB QA Team - as of Mar 26
Assignee
| Issue key | Summary | Priority | Created | Reporter | Status | CWB | Temenos | Fix Version/s | Category
1 | CWBSB-736 | SBDCO - Applicant - Non-Signer Owners Page - Validation message is displayed when quebec address is selected, but FS do not state any message for qc selection | Medium | 2021-03-27 11:15 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
2 | CWBSB-735 | SBDCO - Authorized Signer - Qualifying question page - Validation message | Medium | 2021-03-27 04:56 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
3 | CWBSB-727 | SBDCO â€“ Mobile â€“ Authorised Signer eConsent â€“ No error message header displayed | Medium | 2021-03-25 05:52 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug-UI
4 | CWBSB-726 | SBDCO - The Back button on a mobile browser causes the application to be lost | Medium | 2021-03-25 03:54 | Yigal.Shinderman@cwbank.com | Backlog | Ian.Hicks@cwbank.com |  |  | CWB-BA-QA-Review
5 | CWBSB-725 | SBDCO - Authorized Signer - Name and Address - header for What's your address? | Medium | 2021-03-25 03:30 | cheryl.kirchmaier@cwbank.com | Backlog | Ian.Hicks@cwbank.com |  |  | CWB-BA-QA-Review
6 | CWBSB-724 | SBDCO - Applicant - Your Business Page - Use this as my business mailing address radio button group should be mandatory | Medium | 2021-03-25 03:14 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Requirement-Defect
7 | CWBSB-722 | SBDCO â€“ Mobile â€“ Non-signing owners - The inline help and icon are displayed off screen | Medium | 2021-03-23 10:03 | cheryl.kirchmaier@cwbank.com | Backlog |  | smatharu |  | Bug-UI
8 | CWBSB-721 | SBDCO - Applicant - Birthday & SIN page - on all iPhone devices for Safari - multiple inline messages stay open | Medium | 2021-03-23 08:51 | Yigal.Shinderman@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug-UI
9 | CWBSB-720 | SBDCO â€“ Non-signer Owners â€“ Corporation â€“ Director â€“ not displayed, should be | Medium | 2021-03-23 06:56 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
10 | CWBSB-719 | SBDCO - Non-Signing Owners - Address - Issues with characters allowed, error message incorrect | Medium | 2021-03-23 05:33 | cheryl.kirchmaier@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug-UI
11 | CWBSB-718 | SBDCO - Applicant - Contact Info Page - Mobile verification Page is not displayed when mobile number is changed. | Medium | 2021-03-23 04:36 | priya.chodha@cwbank.com | Backlog |  | dan.riberdy |  | Bug
12 | CWBSB-716 | SBDCO â€“ Mobile â€“ Pages for small business - Next button is displayed highlighted | Medium | 2021-03-20 07:26 | cheryl.kirchmaier@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug-UI
13 | CWBSB-706 | UX/UI: Business form length difference | Medium | 2021-03-19 08:43 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  |  | Bug-UI
14 | CWBSB-705 | UX/UI: Email-spacing issue on top and bottom edge, top bar length | Medium | 2021-03-19 08:32 | karthik.padumati@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug-UI
15 | CWBSB-702 | UX/UI: Card Alignment display | Medium | 2021-03-19 06:05 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
16 | CWBSB-701 | UX/UI: Funding Page - Funding UI spacing | Medium | 2021-03-19 05:29 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
17 | CWBSB-700 | UX/UI: Business Type Selection - Radio Button Spacing | Medium | 2021-03-19 05:09 | venayak.rajahrajaswaran@cwbank.com | Backlog |  | kendyl.bachelor |  | Bug-UI
18 | CWBSB-699 | UX/UI: Step 6 - Our Fine Print - Control Placement | Medium | 2021-03-19 05:07 | venayak.rajahrajaswaran@cwbank.com | Backlog | venayak.rajahrajaswaran@cwbank.com |  |  | Bug-UI
19 | CWBSB-698 | UX/UI: Funding - UI Spacing | Medium | 2021-03-19 05:04 | venayak.rajahrajaswaran@cwbank.com | Backlog | venayak.rajahrajaswaran@cwbank.com |  |  | Bug-UI
20 | CWBSB-697 | UX/UI: Step 1 - Let's get started - Horizontal radio buttons and selection | Medium | 2021-03-19 04:35 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
21 | CWBSB-696 | UX/UI: Access to Digital Banking Page - Missing and incorrect format | Medium | 2021-03-19 04:15 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
22 | CWBSB-694 | UX/UI: Step 13 - Funding Page - UI spacing issue | Medium | 2021-03-19 03:00 | Chix.DelaLuna@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  |  | Bug-UI
23 | CWBSB-640 | SBDCO â€“U/X Mobile â€“ Authorized Signer â€“ Submission Complete and Cancel - Footer | Medium | 2021-03-12 02:48 | cheryl.kirchmaier@cwbank.com | Backlog |  | manish.varia@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
24 | CWBSB-637 | SBDCO - Security Question - Mobile - Display of two line question | Medium | 2021-03-10 10:24 | cheryl.kirchmaier@cwbank.com | Backlog | kendyl.bachelor |  |  | Bug-UI
25 | CWBSB-634 | SBDCO - Authorized Signer - E-Consent Page - Inline help for do you need business debit card question is misplaced. | Medium | 2021-03-10 09:16 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
26 | CWBSB-633 | SBDCO - Disclosures - Tax Residency - Mobile - Text overlaps for long business name | Medium | 2021-03-10 06:47 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug-UI
27 | CWBSB-632 | SBDCO - More about your Business page - Validation message is not displayed for additional province/terriotory of registration field when value is same as other field. | Medium | 2021-03-09 06:02 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
28 | CWBSB-625 | SBDCO - Owners, Directors, Signers - First and Last name fields accept \ special character | Medium | 2021-03-05 15:57 | cheryl.kirchmaier@cwbank.com | In Test | cheryl.kirchmaier@cwbank.com |  |  | Bug
29 | CWBSB-623 | SBDCO - More About your Business Page - Validation message not correct for fields | Medium | 2021-03-05 11:23 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
30 | CWBSB-622 | SBDCO - More About your Business Page - Inline help for Province/Territory field is not correct as given in the field Spec. | Medium | 2021-03-05 10:24 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
31 | CWBSB-621 | SBDCO - Account Selection Page â€“ Quantity is not saved when toggling Chequing and Savings | Medium | 2021-03-05 07:16 | cheryl.kirchmaier@cwbank.com | Blocked | cheryl.kirchmaier@cwbank.com |  |  | Bug
32 | CWBSB-620 | SBDCO - Applicant - Not Qualified Info Page - Email address field is accepting invalid formats. | Medium | 2021-03-05 04:18 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
33 | CWBSB-619 | SBDCO- Not Qualified Information Page â€“ Page does not move focus to error message | Medium | 2021-03-05 03:34 | cheryl.kirchmaier@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
34 | CWBSB-570 | SBDCO - Applicant & Authorized Signer - Flinks Page - Business Application Time Out | Medium | 2021-02-25 03:34 | priya.chodha@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
35 | CWBSB-569 | SBDCO â€“ Authorized Signer â€“ Name & Address page â€“ Error message is displayed regarding dropdown (After Time Out) | Medium | 2021-02-24 12:13 | cheryl.kirchmaier@cwbank.com | Backlog |  | dan.riberdy | Small Biz DCO R1 (F&F) | Bug
36 | CWBSB-568 | SBDCO - Authorized Signer - Landing Page -Authorized Signer First and Last name is missing in landing page | Medium | 2021-02-24 07:27 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
37 | CWBSB-567 | SBDCO - Applicant and Authorized Signer - Security Question Page - Progressive Reveal and Fields behavior on navigation | Medium | 2021-02-24 06:45 | priya.chodha@cwbank.com | In UAT | Ian.Hicks@cwbank.com |  |  | CWB-BA-QA-Review
38 | CWBSB-566 | SBDCO - Authorized Signer - Manual IDV Page -Discrepency with the content given in Fs and the app, email address hyperlink Issue. | Medium | 2021-02-24 03:31 | priya.chodha@cwbank.com | In UAT | priya.chodha@cwbank.com |  |  | Bug
39 | CWBSB-565 | SBDCO - Authorized Signer & Applicant - Contact Info Page - Issue with Mobile Number field. | Medium | 2021-02-23 11:23 | priya.chodha@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  |  | TBD
40 | CWBSB-552 | SBDCO - Security Questions page - Next and Back buttons are navigating to different pages, not aligned with info given in FS. | Medium | 2021-02-19 12:42 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
41 | CWBSB-550 | SBDCO - Security questions Page - Special character â€˜ is not accepted in security answer field. | Medium | 2021-02-19 12:11 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
42 | CWBSB-548 | SBDCO - Desktop: Submission Completed Page -Center (Please See Latest Comment) | Medium | 2021-02-19 07:43 | cheryl.kirchmaier@cwbank.com | Blocked |  | kendyl.bachelor | Small Biz DCO R1 (F&F) | Bug
43 | CWBSB-547 | SBDCO - Your Business Page - Validation message not aligned with the message given in field spec | Medium | 2021-02-19 05:43 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
44 | CWBSB-509 | SBDCO - Authorized Signer - Invitation Email - Content in the email received is quite different than in Field Spec. | Medium | 2021-02-11 08:06 | priya.chodha@cwbank.com | Blocked | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
45 | CWBSB-503 | SBDCO - No Validation Message given in Field Spec but App displays the validation message | Medium | 2021-02-11 06:52 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
46 | CWBSB-497 | SBDCO - Authorized Signer - Decline Page - Page layout is not correct in mobile device | Medium | 2021-02-10 11:55 | priya.chodha@cwbank.com | In Test |  | dan.riberdy | Small Biz DCO R1 (F&F) | Bug-UI
47 | CWBSB-496 | SBDCO - Authorized Signer - Birthday & Sin Page - Next and back button is navigating to different Pages. | Medium | 2021-02-10 11:46 | priya.chodha@cwbank.com | In UAT | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
48 | CWBSB-495 | SBDCO -Authorized Signer - Entry Page -Validation message with lots of space | Medium | 2021-02-10 11:24 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug-Text
49 | CWBSB-494 | SBDCO - Alternate IDV page - Radio button selection and Color issue. | Medium | 2021-02-10 11:08 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
50 | CWBSB-487 | SBDCO - Applicant - More About Your Business page - Applicant can select same province | Medium | 2021-02-09 11:16 | mary.pele@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO R1 (F&F) | Change
51 | CWBSB-474 | SBDCO - Authorized Signer - IDScan Page - Issue with ID Upload | Medium | 2021-02-06 10:54 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Intermittent
52 | CWBSB-472 | SBDCO - Auth Signer - Name & Address Page -Radio buttons are default to yes when ID is uploaded in IDScan page | Medium | 2021-02-06 09:27 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
53 | CWBSB-470 | SBDCO- Disclosures - Tax Residency page- Validation Message Needs Verbiage change | Medium | 2021-02-06 06:47 | mary.pele@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  | Small Biz DCO R1 (F&F) | Requirement-Defect
54 | CWBSB-469 | SBDCO - Authorized Signer - Entry Page - Validation message is not displayed when invalid token is entered. | Medium | 2021-02-06 06:30 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
55 | CWBSB-468 | SBDCO- Authorized Signer - Entry Page - Progress bar is not displayed in the app but is specified in field Spec. | Medium | 2021-02-06 05:10 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Requirement-Defect
56 | CWBSB-460 | SBDCO - Existing Customer page - Updates required for the form Values | Medium | 2021-02-05 02:45 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
57 | CWBSB-424 | SBDCO- Applicant - Issue with Radio button selection when the ID is deleted in IDScan Page | Medium | 2021-01-29 11:57 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
58 | CWBSB-412 | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | Medium | 2021-01-27 07:48 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | CWB-BA-QA-Review
59 | CWBSB-395 | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue (Edge Browser) | Medium | 2021-01-22 07:31 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
60 | CWBSB-394 | SBDCO - Qualifying questions page- Next and back button appearing twice when clicked | Medium | 2021-01-22 05:27 | mary.pele@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  | Small Biz DCO R1 (F&F) | Intermittent

## Sprint Report
Sprint 9 - March 26
Regression Testing Completed |  |  |  | Sprint Report
Total Regression Test Cases To Date | 213 | % |  |  | Planned/Delivered | Tested | Passed | Failed | Notes
Passed Tests | 180 | % Passed | 84.507 | Number of Stories | 22 | 7** | 4 | 3 | Defects have been logged
Failed Tests | 18 | % Failed | 8.4507 | Number of Changes | 5 | 3** | 2 | 3 | Defects have been logged
Blocked Tests | 15 | % Blocked | 7.0423 | Number of Defects logged by CWB | 5 | 5 | 4 | 1 | One defect reopened
Active/Unexecuted | 0 | % Unexecuted | 0 | Number Defects logged by Temenos | 17 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos. Temenos' QA testers confirms fixes for these.
** Testing the rest of the stories will be covered during E2E