## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of May 11, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 12
Test Execution for Sprint 12 |  |  |  | Notes: 1. Day 10 of test execution - 99.8% complete 2. Sprint 12 package includes: a. 18 stories: 9 will be validated, 3 delivered with known issues, 6 will be validated during E2E b. 3 change requests c. 2 defect fixes – for defects logged by CWB QA Team d. 8 defects fixes – for defects logged by Temenos (excluded from CWB testing) 3. Refer to Defect Summary Report tab for information on defects
Total Tests Cases Developed | 414 | %
Passed Tests | 317 | % Passed | 76.57
Failed Tests | 96 | % Failed | 23.1884
Blocked Tests | 0 | % Blocked | 0
Active/Unexecuted | 1 | % Unexecuted | 0.24155
Total # of defects logged (outstanding) | 71
Defects logged from Sprint 12 | 13 | 1 logged today
Defects logged from previous sprints | 58 | none closed today
Note on B15: Chix Dela Luna: From Feb 19 (JIRA date)
Note on B16: Chix Dela Luna: From Feb 19 (JIRA date)

## Defects Status
Status of Defects logged by CWB QA Team - as of May 11, 2021
| Defects |  |  | Created vs. Resolved chart (Open/Closed rate)
Created defects (127)
Resolved defects (65)
JIRA counts "Done" (56) and "In UAT" (9) as resolved
[5 empty] | 71 | outstanding defects* (defects not in "done" status)
= 127 created defects - 56 defects in "done" status
Count by Defect Category
[5 empty] | 32 | Bug (functional issue - not working as specified)
[5 empty] | 7 | CWB-BA-QA-Review (to review and confirm with CWB BA or QA)
[5 empty] | 26 | Bug-UI (formatting or layout issues)
[5 empty] | 3 | Requirement-Defect (issue with functional specs that need to be corrected)
[5 empty] | 2 | Intermittent (intermittent issues, cannot reproduce, etc.)
[5 empty] | 1 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
[5 empty] | 0 | Change type
[5 empty] | 71 | Total matches count for outstanding defects
Count by Defect Assignee
[5 empty] | 32 | Assigned to Temenos/BIG to address
[5 empty] | 39 | Assigned to CWB to address
- for retesting, field specs or requirement issue, to review, questions, investigate further, etc
Refer to Defect Summary tab for info on OUTSTANDING defects for more info on defect breakdown
|  | Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
|  | Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
|  | Ready for Review | - defect is ready for Temenos review
|  | In Development | - solution for defect is in development
|  | Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
|  | In Test | - with Temenos for their testing
|  | In UAT | - with CWB for their testing
|  | Done | - fix for defect has been validated working, issue is resolved, defect is closed

## Defect Summary Report
Summary of Outstanding Defects - logged by CWB QA Team - as of May 11
Assignee
| Issue key | Summary | Priority | Created | Reporter | Status | CWB | Temenos | Fix Version/s | Category
1 | CWBSB-944 | SBDCO - Method Selection page - MAC Safari - Overlapping between Motive Financial Image and Text | Medium | 2021-05-12 04:14 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug-UI
2 | CWBSB-940 | SBDCO - Application Approval Email - HTML coding in the email | Medium | 2021-05-11 08:17 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug
3 | CWBSB-939 | SBDCO - Dynamic Finish - Cheque - Motive Financial incorrect, should be CWB | Medium | 2021-05-11 07:19 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
4 | CWBSB-935 | SBDCO - Email - Cancel - Authorized Signer initiates - The link for here is not the same color as applicant | Medium | 2021-05-08 04:32 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin |  | Bug-UI
5 | CWBSB-930 | About your Application- Product descriptions are missing when user clicked continue in the timeout modal popup | Medium | 2021-05-05 05:05 | Venkata.Cherukuri@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug
6 | CWBSB-929 | SBDCO - Applicant - Page freezes once a GP is on Business Disclosures and Signature Page | Medium | 2021-05-05 03:41 | Yigal.Shinderman@cwbank.com | Backlog |  | lucyliuxin |  | Bug-UI
7 | CWBSB-928 | SBDCO - Application Approval - No PAN is displayed | Medium | 2021-05-04 07:55 | cheryl.kirchmaier@cwbank.com | Awaiting Information | Ian.Hicks@cwbank.com |  |  | Bug
8 | CWBSB-927 | SBDCO - Dynamic Finish page - Cheque - Spacing, Font, Buttons and Verbiage issues | Medium | 2021-05-04 04:54 | Yigal.Shinderman@cwbank.com | In Test |  | angela.ahn@accutive.com |  | Bug-UI
9 | CWBSB-926 | SBDCO - Applicant - App - eConsent page - Hyperlink redirects user to google | Medium | 2021-05-04 03:14 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
10 | CWBSB-924 | SBDCO - Business Disclosures and Signature - Sole Prop - Back button â€“ Goes to App-Flinks page, should not | Medium | 2021-05-04 02:16 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
11 | CWBSB-923 | SBDCO - What you've Selected Page: Quantity number is missing inside the product card | Medium | 2021-05-01 08:25 | Sanju.Bhandoria@cwbank.com | Backlog | Sanju.Bhandoria@cwbank.com |  |  | Bug
12 | CWBSB-922 | SBDCO - Account Options - Extra text on page but not in FS | Medium | 2021-05-01 07:28 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
13 | CWBSB-918 | SBDCO - Account Selection - Back button is not displayed | Medium | 2021-05-01 01:00 | cheryl.kirchmaier@cwbank.com | Backlog |  | dpoole |  | Bug
14 | CWBSB-878 | SBDCO - Samsung Tab S6 Lite - Portrait - Multiple issues on multiple pages | Medium | 2021-04-22 01:14 | cheryl.kirchmaier@cwbank.com | Backlog |  | llaurent |  | Bug
15 | CWBSB-872 | SBDCO â€“ Owners, Directors, Signers â€“ 100% Ownership â€“ Non-signing Owners page is displayed, should not be | Medium | 2021-04-21 05:00 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
16 | CWBSB-871 | SBDCO â€“ Owners, Directors, Signers â€“ Validation message for % Ownership field not as per FS 2.8 | Medium | 2021-04-21 04:41 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
17 | CWBSB-867 | SBDCO â€“ Owners,Directors,Signers â€“ Email address validation not as per FS when characters entered | Medium | 2021-04-20 09:10 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
18 | CWBSB-864 | SBDCO - Account Selection - Back button â€“ Displays Something Went Wrong _ No modal message | Medium | 2021-04-17 07:39 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
19 | CWBSB-862 | SBDCO- A Convenient option page - Flinks Capital does not accept username or password - iPhone 11 Safari Browser | Medium | 2021-04-17 06:09 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
20 | CWBSB-860 | SBDCO-More Options- Help URL is showing page not found error | Medium | 2021-04-17 04:53 | Venkata.Cherukuri@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug
21 | CWBSB-852 | SBDCO â€“ Performance â€“ More About Your Business â€“ selecting from the Industry dropdowns is slow | Medium | 2021-04-16 08:38 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
22 | CWBSB-851 | SBDCO-Choose your account(s) page-2 scroll bars are displayed in the page | Medium | 2021-04-16 05:59 | Venkata.Cherukuri@cwbank.com | Backlog | Venkata.Cherukuri@cwbank.com |  |  | Bug-UI
23 | CWBSB-849 | SBDCO - Account Selection â€“ Displays Monthly Free Transactions when value = 0, should not | Medium | 2021-04-16 02:19 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin |  | Bug
24 | CWBSB-848 | SBDCO - Submission Complete Model - Alignment is not appropriate | Medium | 2021-04-16 01:33 | Venkata.Cherukuri@cwbank.com | In UAT | Venkata.Cherukuri@cwbank.com |  |  | Bug-UI
25 | CWBSB-839 | SBDCO - Business Account Options - UX/UI - Section (accordion with Open all/Close all) is missing | Medium | 2021-04-15 01:16 | cheryl.kirchmaier@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug-UI
26 | CWBSB-828 | SBDCO - Owners and Directors Page - Issue on resizing the page | Medium | 2021-04-13 07:38 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  |  | Bug-UI
27 | CWBSB-814 | SBDCO - Business Account Options - Desktop and Mobile - -Display of inline help | Medium | 2021-04-10 05:29 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
28 | CWBSB-813 | SBDCO - Applicant - Application Time Out Page - alignment issue with the Continue button | Medium | 2021-04-10 04:29 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
29 | CWBSB-812 | SBDCO - Owners, Directors and Signers Page - The word Delete is not fully displayed - MAC Safari | Medium | 2021-04-10 02:48 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
30 | CWBSB-811 | SBDCO â€“ Business Account Options â€“ More Options â€“ Cannot Save application | Medium | 2021-04-10 02:32 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
31 | CWBSB-804 | SBDCO_Applicant_IDScan Page_The title of the ID uploaded is repeating | Medium | 2021-04-09 03:35 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
32 | CWBSB-790 | SBDCO - Owners, Directors and Signers - Mandatory msg and caption for phone number does not match FS 2.7 | Medium | 2021-04-08 02:54 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug-Text
33 | CWBSB-736 | SBDCO - Applicant - Non-Signer Owners Page - Validation message is displayed when quebec address is selected, but FS do not state any message for qc selection | Medium | 2021-03-27 11:15 | priya.chodha@cwbank.com | Backlog |  | lucyliuxin |  | Bug
34 | CWBSB-735 | SBDCO - Authorized Signer - Qualifying question page - Validation message | Medium | 2021-03-27 04:56 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
35 | CWBSB-727 | SBDCO â€“ Mobile â€“ Authorised Signer eConsent â€“ No error message header displayed | Medium | 2021-03-25 05:52 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug-UI
36 | CWBSB-726 | SBDCO - The Back button on a mobile browser causes the application to be lost | Medium | 2021-03-25 03:54 | Yigal.Shinderman@cwbank.com | Awaiting Information |  | rcurran |  | CWB-BA-QA-Review
37 | CWBSB-724 | SBDCO - Applicant - Your Business Page - Use this as my business mailing address radio button group should be mandatory | Medium | 2021-03-25 03:14 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Requirement-Defect
38 | CWBSB-722 | SBDCO â€“ Mobile â€“ Non-signing owners - The inline help and icon are displayed off screen | Medium | 2021-03-23 10:03 | cheryl.kirchmaier@cwbank.com | Backlog |  | smatharu | Small Biz DCO R1 (F&F) | Bug-UI
39 | CWBSB-721 | SBDCO - Applicant - Birthday & SIN page - on all iPhone devices for Safari - multiple inline messages stay open | Medium | 2021-03-23 08:51 | Yigal.Shinderman@cwbank.com | Backlog |  | smatharu | Small Biz DCO R1 (F&F) | Bug-UI
40 | CWBSB-716 | SBDCO â€“ Mobile â€“ Pages for small business - Next button is displayed highlighted | Medium | 2021-03-20 07:26 | cheryl.kirchmaier@cwbank.com | Backlog |  | kendyl.bachelor | Small Biz DCO R1 (F&F) | Bug-UI
41 | CWBSB-705 | UX/UI: Email-spacing issue on top and bottom edge, top bar length | Medium | 2021-03-19 08:32 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
42 | CWBSB-702 | UX/UI: Card Alignment display | Medium | 2021-03-19 06:05 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
43 | CWBSB-701 | UX/UI: Funding Page - Funding UI spacing | Medium | 2021-03-19 05:29 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
44 | CWBSB-700 | UX/UI: Business Type Selection - Radio Button Spacing | Low | 2021-03-19 05:09 | venayak.rajahrajaswaran@cwbank.com | Ready for UAT | Yigal.Shinderman@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
45 | CWBSB-699 | UX/UI: Step 6 - Our Fine Print - Control Placement | Medium | 2021-03-19 05:07 | venayak.rajahrajaswaran@cwbank.com | Backlog | venayak.rajahrajaswaran@cwbank.com |  |  | Bug-UI
46 | CWBSB-698 | UX/UI: Funding - UI Spacing | Medium | 2021-03-19 05:04 | venayak.rajahrajaswaran@cwbank.com | Backlog | venayak.rajahrajaswaran@cwbank.com |  |  | Bug-UI
47 | CWBSB-697 | UX/UI: Step 1 - Let's get started - Horizontal radio buttons and selection | Medium | 2021-03-19 04:35 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
48 | CWBSB-696 | UX/UI: Access to Digital Banking Page - Missing and incorrect format | Medium | 2021-03-19 04:15 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
49 | CWBSB-694 | UX/UI: Step 13 - Funding Page - UI spacing issue | Medium | 2021-03-19 03:00 | Chix.DelaLuna@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
50 | CWBSB-640 | SBDCO â€“U/X Mobile â€“ Authorized Signer â€“ Submission Complete and Cancel - Footer | Medium | 2021-03-12 02:48 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug-UI
51 | CWBSB-637 | SBDCO - Security Question - Mobile - Display of two line question | Medium | 2021-03-10 10:24 | cheryl.kirchmaier@cwbank.com | Backlog |  | smatharu | Small Biz DCO R1 (F&F) | Bug-UI
52 | CWBSB-620 | SBDCO - Applicant - Not Qualified Info Page - Email address field is accepting invalid formats. | Medium | 2021-03-05 04:18 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
53 | CWBSB-570 | SBDCO - Applicant & Authorized Signer - Flinks Page - Business Application Time Out | Medium | 2021-02-25 03:34 | priya.chodha@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
54 | CWBSB-569 | SBDCO â€“ Authorized Signer â€“ Name & Address page â€“ Error message is displayed regarding dropdown (After Time Out) | Medium | 2021-02-24 12:13 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
55 | CWBSB-567 | SBDCO - Applicant and Authorized Signer - Security Question Page - Progressive Reveal and Fields behavior on navigation | Medium | 2021-02-24 06:45 | priya.chodha@cwbank.com | In UAT | Ian.Hicks@cwbank.com |  |  | CWB-BA-QA-Review
56 | CWBSB-565 | SBDCO - Authorized Signer & Applicant - Contact Info Page - Issue with Mobile Number field. | Medium | 2021-02-23 11:23 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | CWB-BA-QA-Review
57 | CWBSB-550 | SBDCO - Security questions Page - Special character â€˜ is not accepted in security answer field. | Medium | 2021-02-19 12:11 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
58 | CWBSB-547 | SBDCO - Your Business Page - Validation message not aligned with the message given in field spec | Medium | 2021-02-19 05:43 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
59 | CWBSB-509 | SBDCO - Authorized Signer - Invitation Email - Content in the email received is quite different than in Field Spec. | Medium | 2021-02-11 08:06 | priya.chodha@cwbank.com | Blocked | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
60 | CWBSB-503 | SBDCO - No Validation Message given in Field Spec but App displays the validation message | Medium | 2021-02-11 06:52 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
61 | CWBSB-496 | SBDCO - Authorized Signer - Birthday & Sin Page - Next and back button is navigating to different Pages. | Medium | 2021-02-10 11:46 | priya.chodha@cwbank.com | In UAT | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
62 | CWBSB-494 | SBDCO - Alternate IDV page - Radio button selection and Color issue. | Medium | 2021-02-10 11:08 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
63 | CWBSB-474 | SBDCO - Authorized Signer - IDScan Page - Issue with ID Upload | Medium | 2021-02-06 10:54 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Intermittent
64 | CWBSB-472 | SBDCO - Auth Signer - Name & Address Page -Radio buttons are default to yes when ID is uploaded in IDScan page | Medium | 2021-02-06 09:27 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
65 | CWBSB-470 | SBDCO- Disclosures - Tax Residency page- Validation Message Needs Verbiage change | Medium | 2021-02-06 06:47 | mary.pele@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  | Small Biz DCO R1 (F&F) | Requirement-Defect
66 | CWBSB-468 | SBDCO- Authorized Signer - Entry Page - Progress bar is not displayed in the app but is specified in field Spec. | Medium | 2021-02-06 05:10 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Requirement-Defect
67 | CWBSB-460 | SBDCO - Existing Customer page - Updates required for the form Values | Medium | 2021-02-05 02:45 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
68 | CWBSB-424 | SBDCO- Applicant - Issue with Radio button selection when the ID is deleted in IDScan Page | Medium | 2021-01-29 11:57 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
69 | CWBSB-412 | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | Medium | 2021-01-27 07:48 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | CWB-BA-QA-Review
70 | CWBSB-395 | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue (Edge Browser) | Medium | 2021-01-22 07:31 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
71 | CWBSB-394 | SBDCO - Qualifying questions page- Next and back button appearing twice when clicked | Medium | 2021-01-22 05:27 | mary.pele@cwbank.com | Backlog |  | kendyl.bachelor | Small Biz DCO R1 (F&F) | Intermittent

## Sprint Report
Sprint 12 - Started Apr 28 - to complete May 11
Regression Testing Completed |  |  |  | Sprint Report - Sprint 12
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed | Notes
Passed Tests | - | % Passed | - | Number of Stories | TBD | TBD | TBD | TBD
Failed Tests | - | % Failed | - | Number of Changes | TBD | TBD | TBD | TBD
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | TBD | TBD | TBD | TBD
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | TBD | TBD | TBD | TBD
** Testing the rest of the stories will be covered during E2E