## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of May 21, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 13
Test Execution for Sprint 13 |  |  |  | Notes: 1. Day 8 of test execution - 100% complete 2. Sprint 13 package includes: a. 3 stories: 2 will be validated, 1 will be validated during E2E b. 1 change request c. 8 defect fixes – for defects logged by CWB QA Team d. 11 defect fixes – for defects logged by Temenos (excluded from CWB testing) 3. Refer to Defect Summary Report tab for information on defects
Total Tests Cases Developed | 253 | %
Passed Tests | 101 | % Passed | 39.9209
Failed Tests | 40 | % Failed | 15.8103
Blocked Tests | 112 | % Blocked | 44.2688
Active/Unexecuted |  | % Unexecuted | 0
Total # of defects logged (outstanding) | 67
Defects logged from Sprint 13 | 7 | none logged today
Defects logged from previous sprints | 60 | 2 closed today

## Defects Status
Status of Defects logged by CWB QA Team - as of May 21, 2021
| Defects |  | Created vs. Resolved chart (Open/Closed rate)
[5 empty] | Created defects = | 133
[5 empty] | Resolved defects = | 75
[5 empty] | JIRA counts "Done" = | 66 | and "In UAT" = | 9 | as resolved
|  |  |  | 67 | outstanding defects* (defects not in "done" status) = |  |  |  |  | 133 | created defects less | 66 | defects in "done" status
Count by Defect Category
|  |  |  | 30 | Bug (functional issue - not working as specified)
|  |  |  | 6 | CWB-BA-QA-Review (to review and confirm with CWB BA or QA)
|  |  |  | 25 | Bug-UI (formatting or layout issues)
|  |  |  | 3 | Requirement-Defect (issue with functional specs that need to be corrected)
|  |  |  | 2 | Intermittent (intermittent issues, cannot reproduce, etc.)
|  |  |  | 1 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
|  |  |  | 0 | Change type
|  |  |  | 67 | Total matches count for outstanding defects
Count by Defect Assignee
|  |  |  | 31 | Assigned to Temenos/BIG to address
|  |  |  | 36 | Assigned to CWB to address, for retesting, field specs or requirement issue, to review, questions, investigate further, etc
Refer to Defect Summary tab for info on OUTSTANDING defects for more info on defect breakdown
| Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
| Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
| Ready for Review | - defect is ready for Temenos review
| In Development | - solution for defect is in development
| Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
| In Test | - with Temenos for their testing
| In UAT | - with CWB for their testing
| Done | - fix for defect has been validated working, issue is resolved, defect is closed

## Defect Summary Report
Summary of Outstanding Defects - logged by CWB QA Team - as of May 21
Assignee
| Issue key | Summary | Priority | Created | Reporter | Status | CWB | Temenos | Fix Version/s | Category
1 | CWBSB-964 | SBDCO - CODAT - prefill - receiving generic error message 'Something went wrong' | Medium | 2021-05-19 07:23 | cheryl.kirchmaier@cwbank.com | In Test |  | angela.ahn@accutive.com |  | Bug
2 | CWBSB-962 | SBDCO - Applicant - Business Accounts Options Page - Open All/Close All accordion is way too close to the right side of the page | Medium | 2021-05-18 07:13 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
3 | CWBSB-960 | SBDCO - Applicant - A GP/CORP applicant at 100% ownership is taken to the Ownership structure page. | Medium | 2021-05-15 09:05 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug-UI
4 | CWBSB-959 | SBDCO - Owners, Directors, Signers - Cannot Save application from Options | Medium | 2021-05-15 08:27 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
5 | CWBSB-954 | SBDCO - E2E - Corp â€“ Non-Signer not displayed in T24 for Small Business â€“ Basic Details, should be | Medium | 2021-05-14 07:52 | cheryl.kirchmaier@cwbank.com | Approved | Ian.Hicks@cwbank.com |  |  | Bug
6 | CWBSB-953 | Codat page-Images of the accounting packages are not loading, when user clicked continue in the timeout modal popup | Medium | 2021-05-14 05:56 | Venkata.Cherukuri@cwbank.com | Backlog | Venkata.Cherukuri@cwbank.com |  |  | Bug
7 | CWBSB-944 | SBDCO - Method Selection page - MAC Safari - Overlapping between Motive Financial Image and Text | Medium | 2021-05-12 04:14 | Yigal.Shinderman@cwbank.com | In Development |  | lucyliuxin |  | Bug-UI
8 | CWBSB-940 | SBDCO - Application Approval Email - HTML coding in the email | Medium | 2021-05-11 08:17 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug
9 | CWBSB-939 | SBDCO - Dynamic Finish - Cheque - Motive Financial incorrect, should be CWB | Medium | 2021-05-11 07:19 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
10 | CWBSB-935 | SBDCO - Email - Cancel - Authorized Signer initiates - The link for here is not the same color as applicant | Medium | 2021-05-08 04:32 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug-UI
11 | CWBSB-930 | About your Application- Product descriptions are missing when user clicked continue in the timeout modal popup | Medium | 2021-05-05 05:05 | Venkata.Cherukuri@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
12 | CWBSB-929 | SBDCO - Applicant - Page freezes once a GP is on Business Disclosures and Signature Page | Medium | 2021-05-05 03:41 | Yigal.Shinderman@cwbank.com | Backlog |  | lucyliuxin |  | Bug-UI
13 | CWBSB-927 | SBDCO - Dynamic Finish page - Cheque - Spacing, Font, Buttons and Verbiage issues | Medium | 2021-05-04 04:54 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
14 | CWBSB-926 | SBDCO - Applicant - App - eConsent page - Hyperlink redirects user to google | Medium | 2021-05-04 03:14 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
15 | CWBSB-924 | SBDCO - Business Disclosures and Signature - Sole Prop - Back button â€“ Goes to App-Flinks page, should not | Medium | 2021-05-04 02:16 | cheryl.kirchmaier@cwbank.com | Blocked |  | angela.ahn@accutive.com |  | Bug
16 | CWBSB-923 | SBDCO - What you've Selected Page: Quantity number is missing inside the product card | Medium | 2021-05-01 08:25 | Sanju.Bhandoria@cwbank.com | Backlog | Sanju.Bhandoria@cwbank.com |  |  | Bug
17 | CWBSB-918 | SBDCO - Account Selection - Back button is not displayed | Medium | 2021-05-01 01:00 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
18 | CWBSB-878 | SBDCO - Samsung Tab S6 Lite - Portrait - Multiple issues on multiple pages | Medium | 2021-04-22 01:14 | cheryl.kirchmaier@cwbank.com | Backlog |  | llaurent |  | Bug
19 | CWBSB-864 | SBDCO - Account Selection - Back button â€“ Displays Something Went Wrong _ No modal message | Medium | 2021-04-17 07:39 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
20 | CWBSB-862 | SBDCO- A Convenient option page - Flinks Capital does not accept username or password - iPhone 11 Safari Browser | Medium | 2021-04-17 06:09 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
21 | CWBSB-860 | SBDCO-More Options- Help URL is showing page not found error | Medium | 2021-04-17 04:53 | Venkata.Cherukuri@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug
22 | CWBSB-852 | SBDCO â€“ Performance â€“ More About Your Business â€“ selecting from the Industry dropdowns is slow | Medium | 2021-04-16 08:38 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
23 | CWBSB-851 | SBDCO-Choose your account(s) page-2 scroll bars are displayed in the page | Medium | 2021-04-16 05:59 | Venkata.Cherukuri@cwbank.com | Ready for UAT | Venkata.Cherukuri@cwbank.com |  |  | Bug-UI
24 | CWBSB-849 | SBDCO - Account Selection â€“ Displays Monthly Free Transactions when value = 0, should not | Medium | 2021-04-16 02:19 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin |  | Bug
25 | CWBSB-839 | SBDCO - Business Account Options - UX/UI - Section (accordion with Open all/Close all) is missing | Medium | 2021-04-15 01:16 | cheryl.kirchmaier@cwbank.com | Blocked |  | angela.ahn@accutive.com |  | Bug-UI
26 | CWBSB-813 | SBDCO - Applicant - Application Time Out Page - alignment issue with the Continue button | Medium | 2021-04-10 04:29 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
27 | CWBSB-812 | SBDCO - Owners, Directors and Signers Page - The word Delete is not fully displayed - MAC Safari | Medium | 2021-04-10 02:48 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
28 | CWBSB-811 | SBDCO â€“ Business Account Options â€“ More Options â€“ Cannot Save application | Medium | 2021-04-10 02:32 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
29 | CWBSB-804 | SBDCO_Applicant_IDScan Page_The title of the ID uploaded is repeating | Medium | 2021-04-09 03:35 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
30 | CWBSB-790 | SBDCO - Owners, Directors and Signers - Mandatory msg and caption for phone number does not match FS 2.7 | Medium | 2021-04-08 02:54 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug-Text
31 | CWBSB-736 | SBDCO - Applicant - Non-Signer Owners Page - Validation message is displayed when quebec address is selected, but FS do not state any message for qc selection | Medium | 2021-03-27 11:15 | priya.chodha@cwbank.com | Backlog |  | lucyliuxin |  | Bug
32 | CWBSB-735 | SBDCO - Authorized Signer - Qualifying question page - Validation message | Medium | 2021-03-27 04:56 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
33 | CWBSB-727 | SBDCO â€“ Mobile â€“ Authorised Signer eConsent â€“ No error message header displayed | Medium | 2021-03-25 05:52 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug-UI
34 | CWBSB-724 | SBDCO - Applicant - Your Business Page - Use this as my business mailing address radio button group should be mandatory | Medium | 2021-03-25 03:14 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Requirement-Defect
35 | CWBSB-722 | SBDCO â€“ Mobile â€“ Non-signing owners - The inline help and icon are displayed off screen | Medium | 2021-03-23 10:03 | cheryl.kirchmaier@cwbank.com | In Test |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
36 | CWBSB-721 | SBDCO - Applicant - Birthday & SIN page - on all iPhone devices for Safari - multiple inline messages stay open | Medium | 2021-03-23 08:51 | Yigal.Shinderman@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
37 | CWBSB-716 | SBDCO â€“ Mobile â€“ Pages for small business - Next button is displayed highlighted | Medium | 2021-03-20 07:26 | cheryl.kirchmaier@cwbank.com | Awaiting Information |  | rcurran | Small Biz DCO R1 (F&F) | Bug-UI
38 | CWBSB-705 | UX/UI: Email-spacing issue on top and bottom edge, top bar length | Medium | 2021-03-19 08:32 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
39 | CWBSB-702 | UX/UI: Card Alignment display | Medium | 2021-03-19 06:05 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
40 | CWBSB-701 | UX/UI: Funding Page - Funding UI spacing | Medium | 2021-03-19 05:29 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
41 | CWBSB-699 | UX/UI: Step 6 - Our Fine Print - Control Placement | Medium | 2021-03-19 05:07 | venayak.rajahrajaswaran@cwbank.com | Backlog | venayak.rajahrajaswaran@cwbank.com |  |  | Bug-UI
42 | CWBSB-698 | UX/UI: Funding - UI Spacing | Medium | 2021-03-19 05:04 | venayak.rajahrajaswaran@cwbank.com | Backlog | venayak.rajahrajaswaran@cwbank.com |  |  | Bug-UI
43 | CWBSB-697 | UX/UI: Step 1 - Let's get started - Horizontal radio buttons and selection | Medium | 2021-03-19 04:35 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
44 | CWBSB-696 | UX/UI: Access to Digital Banking Page - Missing and incorrect format | Medium | 2021-03-19 04:15 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
45 | CWBSB-694 | UX/UI: Step 13 - Funding Page - UI spacing issue | Medium | 2021-03-19 03:00 | Chix.DelaLuna@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
46 | CWBSB-640 | SBDCO â€“U/X Mobile â€“ Authorized Signer â€“ Submission Complete and Cancel - Footer | Medium | 2021-03-12 02:48 | cheryl.kirchmaier@cwbank.com | Ready for Review |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
47 | CWBSB-637 | SBDCO - Security Question - Mobile - Display of two line question | Medium | 2021-03-10 10:24 | cheryl.kirchmaier@cwbank.com | Backlog |  | smatharu | Small Biz DCO R1 (F&F) | Bug-UI
48 | CWBSB-620 | SBDCO - Applicant - Not Qualified Info Page - Email address field is accepting invalid formats. | Medium | 2021-03-05 04:18 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
49 | CWBSB-570 | SBDCO - Applicant & Authorized Signer - Flinks Page - Business Application Time Out | Medium | 2021-02-25 03:34 | priya.chodha@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
50 | CWBSB-569 | SBDCO â€“ Authorized Signer â€“ Name & Address page â€“ Error message is displayed regarding dropdown (After Time Out) | Medium | 2021-02-24 12:13 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
51 | CWBSB-567 | SBDCO - Applicant and Authorized Signer - Security Question Page - Progressive Reveal and Fields behavior on navigation | Medium | 2021-02-24 06:45 | priya.chodha@cwbank.com | In UAT | Ian.Hicks@cwbank.com |  |  | CWB-BA-QA-Review
52 | CWBSB-565 | SBDCO - Authorized Signer & Applicant - Contact Info Page - Issue with Mobile Number field. | Medium | 2021-02-23 11:23 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | CWB-BA-QA-Review
53 | CWBSB-550 | SBDCO - Security questions Page - Special character â€˜ is not accepted in security answer field. | Medium | 2021-02-19 12:11 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
54 | CWBSB-547 | SBDCO - Your Business Page - Validation message not aligned with the message given in field spec | Medium | 2021-02-19 05:43 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
55 | CWBSB-509 | SBDCO - Authorized Signer - Invitation Email - Content in the email received is quite different than in Field Spec. | Medium | 2021-02-11 08:06 | priya.chodha@cwbank.com | Blocked | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
56 | CWBSB-503 | SBDCO - No Validation Message given in Field Spec but App displays the validation message | Medium | 2021-02-11 06:52 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
57 | CWBSB-496 | SBDCO - Authorized Signer - Birthday & Sin Page - Next and back button is navigating to different Pages. | Medium | 2021-02-10 11:46 | priya.chodha@cwbank.com | In UAT | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
58 | CWBSB-494 | SBDCO - Alternate IDV page - Radio button selection and Color issue. | Medium | 2021-02-10 11:08 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
59 | CWBSB-474 | SBDCO - Authorized Signer - IDScan Page - Issue with ID Upload | Medium | 2021-02-06 10:54 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Intermittent
60 | CWBSB-472 | SBDCO - Auth Signer - Name & Address Page -Radio buttons are default to yes when ID is uploaded in IDScan page | Medium | 2021-02-06 09:27 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
61 | CWBSB-470 | SBDCO- Disclosures - Tax Residency page- Validation Message Needs Verbiage change | Medium | 2021-02-06 06:47 | mary.pele@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  | Small Biz DCO R1 (F&F) | Requirement-Defect
62 | CWBSB-468 | SBDCO- Authorized Signer - Entry Page - Progress bar is not displayed in the app but is specified in field Spec. | Medium | 2021-02-06 05:10 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Requirement-Defect
63 | CWBSB-460 | SBDCO - Existing Customer page - Updates required for the form Values | Medium | 2021-02-05 02:45 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
64 | CWBSB-424 | SBDCO- Applicant - Issue with Radio button selection when the ID is deleted in IDScan Page | Medium | 2021-01-29 11:57 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
65 | CWBSB-412 | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | Medium | 2021-01-27 07:48 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | CWB-BA-QA-Review
66 | CWBSB-395 | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue (Edge Browser) | Medium | 2021-01-22 07:31 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
67 | CWBSB-394 | SBDCO - Qualifying questions page- Next and back button appearing twice when clicked | Medium | 2021-01-22 05:27 | mary.pele@cwbank.com | Backlog |  | kendyl.bachelor | Small Biz DCO R1 (F&F) | Intermittent

## Sprint Report
Sprint 12 - Started Apr 28 - to complete May 11
Regression Testing Completed |  |  |  | Sprint Report - Sprint 12
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 18** | 12 | 5 | 7 | Defects logged
Failed Tests | - | % Failed | - | Number of Changes | 3 | 3 | 3 | - | All passed
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 2 | 2 | 1 | 1 | CWBSB-848 was taken out of Sprint 12
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 8 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
** Testing the rest of the stories will be covered during E2E
Sprint 13 - Started May 12 - to complete May 25
Regression Testing Completed |  |  |  | Sprint Report - Sprint 13
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | TBD | TBD | TBD | TBD
Failed Tests | - | % Failed | - | Number of Changes | TBD | TBD | TBD | TBD
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | TBD | TBD | TBD | TBD
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | TBD | TBD | TBD | TBD
** Testing the rest of the stories will be covered during E2E