## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of Jun 4, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 14
Test Execution for Sprint 14 |  |  |  | Notes: 1. Day 8 of test execution - 88.1% 2. Sprint 14 package includes: a. 8 stories: 5 will be validated, 3 will be validated during E2E b. 2 change requests c. 8 defect fixes – for defects logged by CWB QA Team d. 16 defect fixes – for defects logged by Temenos (excluded from CWB testing) 3. Refer to Defect Summary Report tab for information on defects
Total Tests Cases Developed | 327 | %
Passed Tests | 138 | % Passed | 42.2018
Failed Tests | 93 | % Failed | 28.4404
Blocked Tests | 57 | % Blocked | 17.4312
Active/Unexecuted | 39 | % Unexecuted | 11.9266
Total # of defects logged (outstanding) | 73
Defects logged from Sprint 14 | 12 | none logged today
Defects logged from previous sprints | 61 | 2 closed today

## Defects Status
Status of Defects logged by CWB QA Team - as of Jun 4, 2021
| Defects |  | Created vs. Resolved chart (Open/Closed rate)
[5 empty] | Created defects = | 146
[5 empty] | Resolved defects = | 84
[5 empty] | JIRA counts "Done" = | 73 | and "In UAT" = | 11 | as resolved
|  |  |  | 73 | outstanding defects* (defects not in "done" status) = |  |  |  |  | 146 | created defects less | 73 | defects in "done" status
Count by Defect Category
|  |  |  | 31 | Bug (functional issue - not working as specified)
|  |  |  | 6 | CWB-BA-QA-Review (to review and confirm with CWB BA or QA)
|  |  |  | 25 | Bug-UI (formatting or layout issues)
|  |  |  | 3 | Requirement-Defect (issue with functional specs that need to be corrected)
|  |  |  | 2 | Intermittent (intermittent issues, cannot reproduce, etc.)
|  |  |  | 6 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
|  |  |  | 0 | Change type
|  |  |  | 73 | Total matches count for outstanding defects
Count by Defect Assignee
|  |  |  | 32 | Assigned to Temenos/BIG to address
|  |  |  | 41 | Assigned to CWB to address, for retesting, field specs or requirement issue, to review, questions, investigate further, etc
Refer to Defect Summary tab for info on OUTSTANDING defects for more info on defect breakdown
| Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
| Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
| Ready for Review | - defect is ready for Temenos review
| In Development | - solution for defect is in development
| Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
| In Test | - with Temenos for their testing
| In UAT | - with CWB for their testing
| Done | - fix for defect has been validated working, issue is resolved, defect is closed

## Defect Summary Report
Summary of Outstanding Defects - logged by CWB QA Team - as of Jun 4
Assignee
| Issue key | Summary | Priority | Created | Reporter | Status | CWB | Temenos | Fix Version/s | Category
1 | CWBSB-1007 | To complete your Application Model page- Product descriptions is missing the updated phone number according to ( Spec V1.7) | Medium | 2021-06-02 07:18 | Venkata.Cherukuri@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-Text
2 | CWBSB-1005 | SBDCO - Mobile - Save Confirmation' Email - Resume button cleanup | Medium | 2021-06-02 04:04 | cheryl.kirchmaier@cwbank.com | Approved |  | llaurent | Small Biz DCO R1 (F&F) | Bug-UI
3 | CWBSB-999 | SBDCO_Applicant_ Product summary page_Remove button is not working for Complementary Business Products | Medium | 2021-06-01 08:21 | karthik.padumati@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  |  | Bug
4 | CWBSB-998 | SBDCO - Mobile - Android - Await Authorized Signer - Text on button for Proceed to next step is not centered | Medium | 2021-06-01 06:18 | cheryl.kirchmaier@cwbank.com | In Test |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
5 | CWBSB-994 | SBDCO - Online Banking & Delegates Page - Delete button does not appear to the right side of the page | Medium | 2021-05-29 06:31 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
6 | CWBSB-991 | SBDCO - Workspaces - Claim and Decision where MISMATCH, returns with error | Medium | 2021-05-29 05:26 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
7 | CWBSB-990 | SBDCO - Applicant - Save application page - incorrect verbiage | Medium | 2021-05-29 02:34 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-Text
8 | CWBSB-989 | SMBDCO - Footer link for 'Careers' does not align with the links above | Low | 2021-05-28 07:54 | Yigal.Shinderman@cwbank.com | Ready for UAT | Yigal.Shinderman@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
9 | CWBSB-988 | SBDCO - Back Navigation - Modal does not display as per Figma | Medium | 2021-05-28 04:58 | cheryl.kirchmaier@cwbank.com | Ready for Review |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug-UI
10 | CWBSB-987 | SBDCO - Applicant - IDScan Page Modal - Spec not updated with latest verbiage | Medium | 2021-05-28 04:46 | Yigal.Shinderman@cwbank.com | Backlog | Ian.Hicks@cwbank.com |  |  | Bug-Text
11 | CWBSB-986 | SBDCO - Landing page of Auth-signer -Online and Mobile Banking text should be displayed as 'Digital Banking' as per the spec v1.7 | Medium | 2021-05-28 03:00 | Venkata.Cherukuri@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  |  | Bug-Text
12 | CWBSB-984 | SBDCO_ Applicant_ Login to CODAT page static text missing. | Medium | 2021-05-27 08:52 | karthik.padumati@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  |  | Bug-Text
13 | CWBSB-964 | SBDCO - CODAT - prefill - receiving generic error message 'Something went wrong' | Medium | 2021-05-19 07:23 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
14 | CWBSB-960 | SBDCO - Applicant - A GP/CORP applicant at 100% ownership is taken to the Ownership structure page. | Medium | 2021-05-15 09:05 | Yigal.Shinderman@cwbank.com | Approved |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug-UI
15 | CWBSB-959 | SBDCO - Owners, Directors, Signers - Cannot Save application from Options | Medium | 2021-05-15 08:27 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
16 | CWBSB-954 | SBDCO - E2E - Corp â€“ Non-Signer not displayed in T24 for Small Business â€“ Basic Details, should be | Medium | 2021-05-14 07:52 | cheryl.kirchmaier@cwbank.com | Blocked |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
17 | CWBSB-953 | Codat page-Images of the accounting packages are not loading, when user clicked continue in the timeout modal popup | Medium | 2021-05-14 05:56 | Venkata.Cherukuri@cwbank.com | Backlog | Venkata.Cherukuri@cwbank.com |  |  | Bug
18 | CWBSB-944 | SBDCO - Method Selection page - MAC Safari - Overlapping between Motive Financial Image and Text | Medium | 2021-05-12 04:14 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
19 | CWBSB-940 | SBDCO - Application Approval Email - HTML coding in the email | Medium | 2021-05-11 08:17 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug
20 | CWBSB-939 | SBDCO - Dynamic Finish - Cheque - Motive Financial incorrect, should be CWB | Medium | 2021-05-11 07:19 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
21 | CWBSB-930 | About your Application- Product descriptions are missing when user clicked continue in the timeout modal popup | Medium | 2021-05-05 05:05 | Venkata.Cherukuri@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
22 | CWBSB-929 | SBDCO - Applicant - Page freezes once a GP is on Business Disclosures and Signature Page | Medium | 2021-05-05 03:41 | Yigal.Shinderman@cwbank.com | In Test |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
23 | CWBSB-927 | SBDCO - Dynamic Finish page - Cheque - Spacing, Font, Buttons and Verbiage issues | Medium | 2021-05-04 04:54 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
24 | CWBSB-926 | SBDCO - Applicant - App - eConsent page - Hyperlink redirects user to google | Medium | 2021-05-04 03:14 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
25 | CWBSB-924 | SBDCO - Business Disclosures and Signature - Sole Prop - Back button â€“ Goes to App-Flinks page, should not | Medium | 2021-05-04 02:16 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
26 | CWBSB-923 | SBDCO - What you've Selected Page: Quantity number is missing inside the product card | Medium | 2021-05-01 08:25 | Sanju.Bhandoria@cwbank.com | Backlog |  | Sanju.Bhandoria@cwbank.com |  | Bug
27 | CWBSB-878 | SBDCO - Samsung Tab S6 Lite - Portrait - Multiple issues on multiple pages | Medium | 2021-04-22 01:14 | cheryl.kirchmaier@cwbank.com | Backlog |  | llaurent |  | Bug
28 | CWBSB-864 | SBDCO - Account Selection - Back button â€“ Displays Something Went Wrong _ No modal message | Medium | 2021-04-17 07:39 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
29 | CWBSB-862 | SBDCO- A Convenient option page - Flinks Capital does not accept username or password - iPhone 11 Safari Browser | Medium | 2021-04-17 06:09 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
30 | CWBSB-860 | SBDCO-More Options- Help URL is showing page not found error | Medium | 2021-04-17 04:53 | Venkata.Cherukuri@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug
31 | CWBSB-852 | SBDCO â€“ Performance â€“ More About Your Business â€“ selecting from the Industry dropdowns is slow | Medium | 2021-04-16 08:38 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
32 | CWBSB-849 | SBDCO - Account Selection â€“ Displays Monthly Free Transactions when value = 0, should not | Medium | 2021-04-16 02:19 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin |  | Bug
33 | CWBSB-839 | SBDCO - Business Account Options - UX/UI - Section (accordion with Open all/Close all) is missing | Medium | 2021-04-15 01:16 | cheryl.kirchmaier@cwbank.com | Blocked |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
34 | CWBSB-813 | SBDCO - Applicant - Application Time Out Page - alignment issue with the Continue button | Medium | 2021-04-10 04:29 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
35 | CWBSB-812 | SBDCO - Owners, Directors and Signers Page - The word Delete is not fully displayed - MAC Safari | Medium | 2021-04-10 02:48 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
36 | CWBSB-811 | SBDCO â€“ Business Account Options â€“ More Options â€“ Cannot Save application | Medium | 2021-04-10 02:32 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
37 | CWBSB-804 | SBDCO_Applicant_IDScan Page_The title of the ID uploaded is repeating | Medium | 2021-04-09 03:35 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
38 | CWBSB-790 | SBDCO - Owners, Directors and Signers - Mandatory msg and caption for phone number does not match FS 2.7 | Medium | 2021-04-08 02:54 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug-Text
39 | CWBSB-736 | SBDCO - Applicant - Non-Signer Owners Page - Validation message is displayed when quebec address is selected, but FS do not state any message for qc selection | Medium | 2021-03-27 11:15 | priya.chodha@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug
40 | CWBSB-735 | SBDCO - Authorized Signer - Qualifying question page - Validation message | Medium | 2021-03-27 04:56 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
41 | CWBSB-727 | SBDCO â€“ Mobile â€“ Authorised Signer eConsent â€“ No error message header displayed | Medium | 2021-03-25 05:52 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug-UI
42 | CWBSB-724 | SBDCO - Applicant - Your Business Page - Use this as my business mailing address radio button group should be mandatory | Medium | 2021-03-25 03:14 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Requirement-Defect
43 | CWBSB-721 | SBDCO - Applicant - Birthday & SIN page - on all iPhone devices for Safari - multiple inline messages stay open | Medium | 2021-03-23 08:51 | Yigal.Shinderman@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
44 | CWBSB-716 | SBDCO â€“ Mobile â€“ Pages for small business - Next button is displayed highlighted | Medium | 2021-03-20 07:26 | cheryl.kirchmaier@cwbank.com | Awaiting Information |  | rcurran | Small Biz DCO R1 (F&F) | Bug-UI
45 | CWBSB-705 | UX/UI: Email-spacing issue on top and bottom edge, top bar length | Medium | 2021-03-19 08:32 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
46 | CWBSB-702 | UX/UI: Card Alignment display | Medium | 2021-03-19 06:05 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
47 | CWBSB-701 | UX/UI: Funding Page - Funding UI spacing | Medium | 2021-03-19 05:29 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
48 | CWBSB-699 | UX/UI: Step 6 - Our Fine Print - Control Placement | Medium | 2021-03-19 05:07 | venayak.rajahrajaswaran@cwbank.com | Backlog | venayak.rajahrajaswaran@cwbank.com |  |  | Bug-UI
49 | CWBSB-698 | UX/UI: Funding - UI Spacing | Medium | 2021-03-19 05:04 | venayak.rajahrajaswaran@cwbank.com | Backlog | venayak.rajahrajaswaran@cwbank.com |  |  | Bug-UI
50 | CWBSB-697 | UX/UI: Step 1 - Let's get started - Horizontal radio buttons and selection | Medium | 2021-03-19 04:35 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
51 | CWBSB-696 | UX/UI: Access to Digital Banking Page - Missing and incorrect format | Medium | 2021-03-19 04:15 | gem.adelaja@cwbank.com | Backlog | gem.adelaja@cwbank.com |  |  | Bug-UI
52 | CWBSB-694 | UX/UI: Step 13 - Funding Page - UI spacing issue | Medium | 2021-03-19 03:00 | Chix.DelaLuna@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
53 | CWBSB-637 | SBDCO - Security Question - Mobile - Display of two line question | Medium | 2021-03-10 10:24 | cheryl.kirchmaier@cwbank.com | In Development |  | smatharu | Small Biz DCO R1 (F&F) | Bug-UI
54 | CWBSB-620 | SBDCO - Applicant - Not Qualified Info Page - Email address field is accepting invalid formats. | Medium | 2021-03-05 04:18 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
55 | CWBSB-570 | SBDCO - Applicant & Authorized Signer - Flinks Page - Business Application Time Out | Medium | 2021-02-25 03:34 | priya.chodha@cwbank.com | Backlog | Chix.DelaLuna@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
56 | CWBSB-569 | SBDCO â€“ Authorized Signer â€“ Name & Address page â€“ Error message is displayed regarding dropdown (After Time Out) | Medium | 2021-02-24 12:13 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
57 | CWBSB-567 | SBDCO - Applicant and Authorized Signer - Security Question Page - Progressive Reveal and Fields behavior on navigation | Medium | 2021-02-24 06:45 | priya.chodha@cwbank.com | In UAT | Ian.Hicks@cwbank.com |  |  | CWB-BA-QA-Review
58 | CWBSB-565 | SBDCO - Authorized Signer & Applicant - Contact Info Page - Issue with Mobile Number field. | Medium | 2021-02-23 11:23 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | CWB-BA-QA-Review
59 | CWBSB-550 | SBDCO - Security questions Page - Special character â€˜ is not accepted in security answer field. | Medium | 2021-02-19 12:11 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
60 | CWBSB-547 | SBDCO - Your Business Page - Validation message not aligned with the message given in field spec | Medium | 2021-02-19 05:43 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
61 | CWBSB-509 | SBDCO - Authorized Signer - Invitation Email - Content in the email received is quite different than in Field Spec. | Medium | 2021-02-11 08:06 | priya.chodha@cwbank.com | Blocked | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
62 | CWBSB-503 | SBDCO - No Validation Message given in Field Spec but App displays the validation message | Medium | 2021-02-11 06:52 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
63 | CWBSB-496 | SBDCO - Authorized Signer - Birthday & Sin Page - Next and back button is navigating to different Pages. | Medium | 2021-02-10 11:46 | priya.chodha@cwbank.com | In UAT | priya.chodha@cwbank.com |  |  | CWB-BA-QA-Review
64 | CWBSB-494 | SBDCO - Alternate IDV page - Radio button selection and Color issue. | Medium | 2021-02-10 11:08 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
65 | CWBSB-474 | SBDCO - Authorized Signer - IDScan Page - Issue with ID Upload | Medium | 2021-02-06 10:54 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Intermittent
66 | CWBSB-472 | SBDCO - Auth Signer - Name & Address Page -Radio buttons are default to yes when ID is uploaded in IDScan page | Medium | 2021-02-06 09:27 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
67 | CWBSB-470 | SBDCO- Disclosures - Tax Residency page- Validation Message Needs Verbiage change | Medium | 2021-02-06 06:47 | mary.pele@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  | Small Biz DCO R1 (F&F) | Requirement-Defect
68 | CWBSB-468 | SBDCO- Authorized Signer - Entry Page - Progress bar is not displayed in the app but is specified in field Spec. | Medium | 2021-02-06 05:10 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Requirement-Defect
69 | CWBSB-460 | SBDCO - Existing Customer page - Updates required for the form Values | Medium | 2021-02-05 02:45 | priya.chodha@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
70 | CWBSB-424 | SBDCO- Applicant - Issue with Radio button selection when the ID is deleted in IDScan Page | Medium | 2021-01-29 11:57 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
71 | CWBSB-412 | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | Medium | 2021-01-27 07:48 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | CWB-BA-QA-Review
72 | CWBSB-395 | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue (Edge Browser) | Medium | 2021-01-22 07:31 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
73 | CWBSB-394 | SBDCO - Qualifying questions page- Next and back button appearing twice when clicked | Medium | 2021-01-22 05:27 | mary.pele@cwbank.com | Backlog |  | kendyl.bachelor | Small Biz DCO R1 (F&F) | Intermittent

## Sprint Report
Sprint 12 - Started Apr 28 - to complete May 11
Regression Testing Completed |  |  |  | Sprint Report - Sprint 12
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 18** | 12 | 5 | 7 | Defects logged
Failed Tests | - | % Failed | - | Number of Changes | 3 | 3 | 3 | - | All passed
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 2 | 2 | 1 | 1 | CWBSB-848 was taken out of Sprint 12
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 8 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
** Testing the rest of the stories will be covered during E2E
Sprint 13 - Started May 12 - to complete May 25
Regression Testing Completed |  |  |  | Sprint Report - Sprint 13
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 3* | 0 | 0 | 1 | Only 1 story was to be tested in Sprint 13, the rest are for E2E.
Failed Tests | - | % Failed | - | Number of Changes | 1 | 0 | 0 | 1 | Blocked due to test data not being available
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 8 | 7 | 7 | 1 | Untested story associated with a story is Backlog
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 11 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
* Testing the rest of the stories will be covered during E2E