## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of Jun 22, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 15
Test Execution for Sprint 15 |  |  |  | Notes: 1. Day 10 of test execution - 100% 2. Sprint 15 package includes: a. 5 stories: 2 will be validated, 3 will be validated during E2E b. 1 change requests c. 8 defect fixes – for defects logged by CWB QA Team 3. Refer to Defect Summary Report tab for information on defects
Total Tests Cases Developed | 287 | %
Passed Tests | 132 | % Passed | 45.993
Failed Tests | 46 | % Failed | 16.0279
Blocked Tests | 109 | % Blocked | 37.9791
Active/Unexecuted | 0 | % Unexecuted | 0
Total # of defects logged (outstanding) | 60
Defects logged from Sprint 15 | 6 | 1 logged today 1 closed today
Defects logged from previous sprints | 54 | none closed today

## Defects Status
Status of Defects logged by CWB QA Team - as of Jun 22, 2021
| Defects |  | Created vs. Resolved chart (Open/Closed rate)
[5 empty] | Created defects = | 152
[5 empty] | Resolved defects = | 101
[5 empty] | JIRA counts "Done" = | 92 | and "In UAT" = | 9 | as resolved
|  |  |  | 60 | outstanding defects* (defects not in "done" status) = |  |  |  |  | 152 | created defects less | 92 | defects in "done" status
Count by Defect Category
|  |  |  | 31 | Bug (functional issue - not working as specified)
|  |  |  | 3 | CWB-BA-QA-Review (to review and confirm with CWB BA or QA)
|  |  |  | 18 | Bug-UI (formatting or layout issues)
|  |  |  | 2 | Requirement-Defect (issue with functional specs that need to be corrected)
|  |  |  | 1 | Intermittent (intermittent issues, cannot reproduce, etc.)
|  |  |  | 5 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
|  |  |  | 0 | Change type
|  |  |  | 60 | Total matches count for outstanding defects
Count by Defect Assignee
|  |  |  | 36 | Assigned to Temenos/BIG to address
|  |  |  | 24 | Assigned to CWB to address, for retesting, field specs or requirement issue, to review, questions, investigate further, etc
Refer to Defect Summary tab for info on OUTSTANDING defects for more info on defect breakdown
| Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
| Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
| Ready for Review | - defect is ready for Temenos review
| In Development | - solution for defect is in development
| Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
| In Test | - with Temenos for their testing
| In UAT | - with CWB for their testing
| Done | - fix for defect has been validated working, issue is resolved, defect is closed

## Defect Summary Report
Summary of Outstanding Defects - logged by CWB QA Team - as of Jun 22
Assignee
| Issue key | Summary | Priority | Created | Reporter | Status | CWB | Temenos | Fix Version/s | Category
1 | CWBSB-1062 | SBDCO_Applicant_Login to CODAT page is missing | Medium | 2021-06-22 07:34 | karthik.padumati@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
2 | CWBSB-1054 | SBDCO_submission complete page_Alignment issue and Displays link for personal-onboarding@cwbank.com. | Medium | 2021-06-19 04:57 | karthik.padumati@cwbank.com | Approved |  | lucyliuxin |  | Bug-UI
3 | CWBSB-1053 | SBDCO- Funding - Save Email - Displays link for personal-onboarding@cwbank.com | Medium | 2021-06-19 03:12 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
4 | CWBSB-1049 | SBDCO - Workspaces - No Business Search Report | Medium | 2021-06-18 05:03 | cheryl.kirchmaier@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug
5 | CWBSB-1039 | SBDCO â€“ Okta â€“ Applicant â€“ Get Customer Details' (T24) Service (Prefill) - No Prefill | Medium | 2021-06-12 06:31 | cheryl.kirchmaier@cwbank.com | Awaiting Information | cheryl.kirchmaier@cwbank.com |  |  | Bug
6 | CWBSB-1034 | SBDCO_Funding_Method selection page_ Caption Text placement on Mobile is incorrect | Medium | 2021-06-12 01:58 | karthik.padumati@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug
7 | CWBSB-1007 | To complete your Application Model page- Product descriptions is missing the updated phone number according to ( Spec V1.7) | Medium | 2021-06-02 07:18 | Venkata.Cherukuri@cwbank.com | Ready for UAT | Venkata.Cherukuri@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-Text
8 | CWBSB-1005 | SBDCO - Mobile - Save Confirmation' Email - Resume button cleanup | Medium | 2021-06-02 04:04 | cheryl.kirchmaier@cwbank.com | Approved |  | manish.varia@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
9 | CWBSB-999 | SBDCO_Applicant_ Product summary page_Remove button is not working for Complementary Business Products | Medium | 2021-06-01 08:21 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  |  | Bug
10 | CWBSB-998 | SBDCO - Mobile - Android - Await Authorized Signer - Text on button for Proceed to next step is not centered | Medium | 2021-06-01 06:18 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
11 | CWBSB-994 | SBDCO - Online Banking & Delegates Page - Delete button does not appear to the right side of the page | Medium | 2021-05-29 06:31 | Yigal.Shinderman@cwbank.com | In Development |  | smatharu | Small Biz DCO R1 (F&F) | Bug-UI
12 | CWBSB-991 | SBDCO - Workspaces - Claim and Decision where MISMATCH, returns with error | Medium | 2021-05-29 05:26 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
13 | CWBSB-990 | SBDCO - Applicant - Save application page - incorrect verbiage | Medium | 2021-05-29 02:34 | Yigal.Shinderman@cwbank.com | Approved |  | llaurent | Small Biz DCO R1 (F&F) | Bug-Text
14 | CWBSB-989 | SMBDCO - Footer link for 'Careers' does not align with the links above | Low | 2021-05-28 07:54 | Yigal.Shinderman@cwbank.com | In Development |  | smatharu | Small Biz DCO R1 (F&F) | Bug-UI
15 | CWBSB-986 | SBDCO - Landing page of Auth-signer -Online and Mobile Banking text should be displayed as 'Digital Banking' as per the spec v1.7 | Medium | 2021-05-28 03:00 | Venkata.Cherukuri@cwbank.com | Awaiting Information | Venkata.Cherukuri@cwbank.com |  |  | Bug-Text
16 | CWBSB-984 | SBDCO_ Applicant_ Login to CODAT page static text missing. | Medium | 2021-05-27 08:52 | karthik.padumati@cwbank.com | Deployed to TEST |  | manish.varia@accutive.com | Small Biz DCO R1 (F&F) | Bug-Text
17 | CWBSB-964 | SBDCO - CODAT - prefill - receiving generic error message 'Something went wrong' | Medium | 2021-05-19 07:23 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
18 | CWBSB-954 | SBDCO - E2E - Corp â€“ Non-Signer not displayed in T24 for Small Business â€“ Basic Details, should be | Medium | 2021-05-14 07:52 | cheryl.kirchmaier@cwbank.com | Blocked |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
19 | CWBSB-953 | Codat page-Images of the accounting packages are not loading, when user clicked continue in the timeout modal popup | Medium | 2021-05-14 05:56 | Venkata.Cherukuri@cwbank.com | Awaiting Information |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
20 | CWBSB-940 | SBDCO - Application Approval Email - HTML coding in the email | Medium | 2021-05-11 08:17 | Yigal.Shinderman@cwbank.com | Approved | Yigal.Shinderman@cwbank.com |  |  | Bug
21 | CWBSB-939 | SBDCO - Dynamic Finish - Cheque - Motive Financial incorrect, should be CWB | Medium | 2021-05-11 07:19 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
22 | CWBSB-930 | About your Application- Product descriptions are missing when user clicked continue in the timeout modal popup | Medium | 2021-05-05 05:05 | Venkata.Cherukuri@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
23 | CWBSB-927 | SBDCO - Dynamic Finish page - Cheque - Spacing, Font, Buttons and Verbiage issues | Medium | 2021-05-04 04:54 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
24 | CWBSB-926 | SBDCO - Applicant - App - eConsent page - Hyperlink redirects user to google | Medium | 2021-05-04 03:14 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
25 | CWBSB-924 | SBDCO - Business Disclosures and Signature - Sole Prop - Back button â€“ Goes to App-Flinks page, should not | Medium | 2021-05-04 02:16 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
26 | CWBSB-923 | SBDCO - What you've Selected Page: Quantity number is missing inside the product card | Medium | 2021-05-01 08:25 | Sanju.Bhandoria@cwbank.com | Awaiting Information | Sanju.Bhandoria@cwbank.com |  |  | Bug
27 | CWBSB-878 | SBDCO - Samsung Tab S6 Lite - Portrait - Multiple issues on multiple pages | Medium | 2021-04-22 01:14 | cheryl.kirchmaier@cwbank.com | Backlog |  | llaurent |  | Bug
28 | CWBSB-864 | SBDCO - Account Selection - Back button â€“ Displays Something Went Wrong _ No modal message | Medium | 2021-04-17 07:39 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
29 | CWBSB-862 | SBDCO- A Convenient option page - Flinks Capital does not accept username or password - iPhone 11 Safari Browser | Medium | 2021-04-17 06:09 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
30 | CWBSB-860 | SBDCO-More Options- Help URL is showing page not found error | Medium | 2021-04-17 04:53 | Venkata.Cherukuri@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  |  | Bug
31 | CWBSB-852 | SBDCO â€“ Performance â€“ More About Your Business â€“ selecting from the Industry dropdowns is slow | Medium | 2021-04-16 08:38 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
32 | CWBSB-849 | SBDCO - Account Selection â€“ Displays Monthly Free Transactions when value = 0, should not | Medium | 2021-04-16 02:19 | cheryl.kirchmaier@cwbank.com | Approved |  | lucyliuxin |  | Bug
33 | CWBSB-813 | SBDCO - Applicant - Application Time Out Page - alignment issue with the Continue button | Medium | 2021-04-10 04:29 | Yigal.Shinderman@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
34 | CWBSB-812 | SBDCO - Owners, Directors and Signers Page - The word Delete is not fully displayed - MAC Safari | Medium | 2021-04-10 02:48 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
35 | CWBSB-811 | SBDCO â€“ Business Account Options â€“ More Options â€“ Cannot Save application | Medium | 2021-04-10 02:32 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug
36 | CWBSB-804 | SBDCO_Applicant_IDScan Page_The title of the ID uploaded is repeating | Medium | 2021-04-09 03:35 | Yigal.Shinderman@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  |  | Bug
37 | CWBSB-790 | SBDCO - Owners, Directors and Signers - Mandatory msg and caption for phone number does not match FS 2.7 | Medium | 2021-04-08 02:54 | cheryl.kirchmaier@cwbank.com | In UAT |  | lucyliuxin | Small Biz DCO R1 (F&F) | Bug-Text
38 | CWBSB-736 | SBDCO - Applicant - Non-Signer Owners Page - Validation message is displayed when quebec address is selected, but FS do not state any message for qc selection | Medium | 2021-03-27 11:15 | Yigal.Shinderman@cwbank.com | Backlog |  | lucyliuxin | Small Biz DCO R1 (F&F) | TBD
39 | CWBSB-727 | SBDCO â€“ Mobile â€“ Authorised Signer eConsent â€“ No error message header displayed | Medium | 2021-03-25 05:52 | cheryl.kirchmaier@cwbank.com | In Test |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
40 | CWBSB-724 | SBDCO - Applicant - Your Business Page - Use this as my business mailing address radio button group should be mandatory | Medium | 2021-03-25 03:14 | Yigal.Shinderman@cwbank.com | Ready for UAT | Yigal.Shinderman@cwbank.com |  | Small Biz DCO R1 (F&F) | Requirement-Defect
41 | CWBSB-721 | SBDCO - Applicant - Birthday & SIN page - on all iPhone devices for Safari - multiple inline messages stay open | Medium | 2021-03-23 08:51 | Yigal.Shinderman@cwbank.com | Awaiting Information |  | llaurent | Small Biz DCO R1 (F&F) | Bug-UI
42 | CWBSB-716 | SBDCO â€“ Mobile â€“ Pages for small business - Next button is displayed highlighted | Medium | 2021-03-20 07:26 | cheryl.kirchmaier@cwbank.com | Awaiting Information |  | rcurran | Small Biz DCO R1 (F&F) | Bug-UI
43 | CWBSB-705 | UX/UI: Email-spacing issue on top and bottom edge, top bar length | Medium | 2021-03-19 08:32 | karthik.padumati@cwbank.com | Approved |  | manish.varia@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
44 | CWBSB-698 | Owner & Director Page - Mobile View - Deleted Button Not Align to the Right per Figma | Medium | 2021-03-19 05:04 | Sanju.Bhandoria@cwbank.com | Ready for UAT | Sanju.Bhandoria@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
45 | CWBSB-697 | UX/UI: Step 1 - Let's get started - Horizontal radio buttons and selection | Medium | 2021-03-19 04:35 | Sanju.Bhandoria@cwbank.com | Awaiting Information | Sanju.Bhandoria@cwbank.com |  |  | Bug-UI
46 | CWBSB-696 | UX/UI: Access to Digital Banking Page - Missing and incorrect format | Medium | 2021-03-19 04:15 | Sanju.Bhandoria@cwbank.com | Backlog |  | dpoole | Small Biz DCO R1 (F&F) | Bug-UI
47 | CWBSB-694 | UX/UI: Step 13 - Funding Page - UI spacing issue | Medium | 2021-03-19 03:00 | Chix.DelaLuna@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
48 | CWBSB-637 | SBDCO - Security Question - Mobile - Display of two line question | Medium | 2021-03-10 10:24 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug-UI
49 | CWBSB-570 | SBDCO - Applicant & Authorized Signer - Flinks Page - Business Application Time Out | Medium | 2021-02-25 03:34 | Sanju.Bhandoria@cwbank.com | Ready for UAT | Chix.DelaLuna@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
50 | CWBSB-569 | SBDCO â€“ Authorized Signer â€“ Name & Address page â€“ Error message is displayed regarding dropdown (After Time Out) | Medium | 2021-02-24 12:13 | cheryl.kirchmaier@cwbank.com | Ready for UAT | cheryl.kirchmaier@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
51 | CWBSB-567 | SBDCO - Applicant and Authorized Signer - Security Question Page - Progressive Reveal and Fields behavior on navigation | Medium | 2021-02-24 06:45 | priya.chodha@cwbank.com | In UAT | Ian.Hicks@cwbank.com |  |  | CWB-BA-QA-Review
52 | CWBSB-565 | SBDCO - Authorized Signer & Applicant - Contact Info Page - Issue with Mobile Number field. | Medium | 2021-02-23 11:23 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | CWB-BA-QA-Review
53 | CWBSB-550 | SBDCO - Security questions Page - Special character â€˜ is not accepted in security answer field. | Medium | 2021-02-19 12:11 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
54 | CWBSB-547 | SBDCO - Your Business Page - Validation message not aligned with the message given in field spec | Medium | 2021-02-19 05:43 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Small Biz DCO R1 (F&F) | Bug-UI
55 | CWBSB-494 | SBDCO - Alternate IDV page - Radio button selection and Color issue. | Medium | 2021-02-10 11:08 | priya.chodha@cwbank.com | Awaiting Information | karthik.padumati@cwbank.com |  |  | Bug-UI
56 | CWBSB-470 | SBDCO- Disclosures - Tax Residency page- Validation Message Needs Verbiage change | Medium | 2021-02-06 06:47 | mary.pele@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  | Small Biz DCO R1 (F&F) | Requirement-Defect
57 | CWBSB-460 | SBDCO - Existing Customer page - Updates required for the form Values | Medium | 2021-02-05 02:45 | priya.chodha@cwbank.com | Ready for UAT | priya.chodha@cwbank.com |  | Small Biz DCO R1 (F&F) | Bug
58 | CWBSB-412 | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | Medium | 2021-01-27 07:48 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | CWB-BA-QA-Review
59 | CWBSB-395 | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue (Edge Browser) | Medium | 2021-01-22 07:31 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Bug
60 | CWBSB-394 | SBDCO - Qualifying questions page- Next and back button appearing twice when clicked | Medium | 2021-01-22 05:27 | mary.pele@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Small Biz DCO R1 (F&F) | Intermittent

## Sprint Report
Sprint 12 - Started Apr 28 - to complete May 11
Regression Testing Completed |  |  |  | Sprint Report - Sprint 12
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 18** | 12 | 5 | 7 | Defects logged
Failed Tests | - | % Failed | - | Number of Changes | 3 | 3 | 3 | - | All passed
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 2 | 2 | 1 | 1 | CWBSB-848 was taken out of Sprint 12
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 8 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
** Testing the rest of the stories will be covered during E2E
Sprint 13 - Started May 12 - to complete May 25
Regression Testing Completed |  |  |  | Sprint Report - Sprint 13
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 3* | 0 | 0 | 1 | Only 1 story was to be tested in Sprint 13, the rest are for E2E.
Failed Tests | - | % Failed | - | Number of Changes | 1 | 0 | 0 | 1 | Blocked due to test data not being available
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 8 | 7 | 7 | 1 | Untested story associated with a story is Backlog
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 11 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
* Testing the rest of the stories will be covered during E2E
Sprint 14 - Started May 26 - to complete Jun 7
Regression Testing Completed |  |  |  | Sprint Report - Sprint 14
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 8* | 3 | 1 | 4 | Failed and unexecuted tests will be done in Sprint 15
Failed Tests | - | % Failed | - | Number of Changes | 2 | 1 | 1 | 1 | 1 to be addressed in Sprint 15
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 8 | 7 | 7 | 1 | 7 closed defects, to be tested later
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 11 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
Sprint Report - Sprint 15
[5 empty] | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
|  |  |  | Number of Stories | 5* | 2 | 2 | 0
|  |  |  | Number of Changes | 1 | 1 | 1 | 0
|  |  |  | Number of Defects logged by CWB | 6 | 6 | 4 | 2 | Assigned back to Temenos
|  |  |  | Number Defects logged by Temenos | N/A | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
* Testing the rest of the stories will be covered during E2E