## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of July 7, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 16
Test Execution for Sprint 16 |  |  |  | Notes: 1. Day 11 of test execution 100.00% 2. Sprint 16 package includes: a. 17 stories: 2 will be validated, 2 will be validated during E2E b. 1 change requests c. 8 defect fixes – for defects logged by CWB QA Team 3. Refer to Defect Summary Report tab for information on defects
Total Tests Cases Developed | 384 | %
Passed Tests | 216 | % Passed | 56.25
Failed Tests | 74 | % Failed | 19.2708
Blocked Tests | 94 | % Blocked | 24.4792
Active/Unexecuted | 0 | % Unexecuted | 0
Total # of defects logged (outstanding) | 68
Defects logged from Sprint 16 | 12
Defects logged from previous sprints | 56

## Defects Status
Status of Defects logged by CWB QA Team - as of July 7, 2021
| Defects |  | Created vs. Resolved chart (Open/Closed rate)
[5 empty] | Created defects = | 165
[5 empty] | Resolved defects = | 122
[5 empty] | JIRA counts "Done" = | 97 | and "In UAT" = | 15 | as resolved
|  |  |  | 68 | outstanding defects* (defects not in "done" status) = |  |  |  |  | 165 | created defects less | 97 | defects in "done" status
Count by Defect Category
|  |  |  | 44 | Bug (functional issue - not working as specified)
|  |  |  | 3 | CWB-BA-QA-Review (to review and confirm with CWB BA or QA)
|  |  |  | 15 | Bug-UI (formatting or layout issues)
|  |  |  | 1 | Requirement-Defect (issue with functional specs that need to be corrected)
|  |  |  | 1 | Intermittent (intermittent issues, cannot reproduce, etc.)
|  |  |  | 4 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
|  |  |  | 0 | Change type
|  |  |  | 68 | Total matches count for outstanding defects
Count by Defect Assignee
|  |  |  | 35 | Assigned to Temenos/BIG to address
|  |  |  | 33 | Assigned to CWB to address, for retesting, field specs or requirement issue, to review, questions, investigate further, etc
Refer to Defect Summary tab for info on OUTSTANDING defects for more info on defect breakdown
| Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
| Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
| Ready for Review | - defect is ready for Temenos review
| In Development | - solution for defect is in development
| Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
| In Test | - with Temenos for their testing
| In UAT | - with CWB for their testing
| Done | - fix for defect has been validated working, issue is resolved, defect is closed

## Defect Summary Report
Summary of Outstanding Defects - logged by CWB QA Team - as of July 7
Assignee
| Issue key | Summary | Priority | Created | Reporter | Status | CWB | Temenos | Fix Version/s | Category
1 | CWBSB-1120 | The 'Resend Email' option in the Await Authorized Signers page should say 'Complete' once the auth signer completes his application | Medium | 2021-07-05 15:11 | Yigal.Shinderman@cwbank.com | Awaiting Information | Ian.Hicks@cwbank.com |  | Bug
2 | CWBSB-1119 | SBDCO - Next and Back button are not aligned on Samsung Galaxy Note 9 | Medium | 2021-07-05 14:52 | Sanju.Bhandoria@cwbank.com | Backlog |  | smatharu | Bug
3 | CWBSB-1118 | SBDCO_Auth Signer_ Contact Info page_Back button is not working as per the Field spec | Medium | 2021-07-05 13:39 | karthik.padumati@cwbank.com | Awaiting Information |  | dpoole | Bug
4 | CWBSB-1089 | SBDCO - Complementary Services - Back button to account options, Intended use setting is cleared | Medium | 2021-06-28 16:55 | cheryl.kirchmaier@cwbank.com | In Development |  | manish.varia@accutive.com | Bug
5 | CWBSB-1082 | SBDCO - MOBILE - Business eConsent and Applicant eConsent - error banner not displayed | Medium | 2021-06-28 13:06 | cheryl.kirchmaier@cwbank.com | In Test |  | angela.ahn@accutive.com | Bug
6 | CWBSB-1078 | SBDCO - Lending Decision - No mandatory message for the 'I agree' checkbox | Medium | 2021-06-25 16:49 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug
7 | CWBSB-1077 | SBDCO - Lending Decision - Mobile - hyperlinks should open in another tab | Medium | 2021-06-25 16:26 | cheryl.kirchmaier@cwbank.com | In Test |  | angela.ahn@accutive.com | Bug
8 | CWBSB-1076 | SBDCO - Lending Decision - Static text is not displayed as per Figma | Medium | 2021-06-25 16:10 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug
9 | CWBSB-1075 | SBDCO - Services Selection - Business Cheques - View Features link returns with about BlankBlocked page | Medium | 2021-06-25 10:12 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug
10 | CWBSB-1073 | SBDCO_ The Applicant and Co-applicant's birthday do not pre-populate when uploading a drivers license | Medium | 2021-06-24 18:06 | karthik.padumati@cwbank.com | Blocked | karthik.padumati@cwbank.com |  | Bug
11 | CWBSB-1072 | SBDCO_Applicat_ Applicant e-consent page_Text is not removed as per the updated Field spec. | Medium | 2021-06-24 17:35 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  | Bug
12 | CWBSB-1071 | SBDCO - Existing Customer Check - Radio button should be default No | Medium | 2021-06-24 14:38 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug
13 | CWBSB-1070 | SBDCO - Application with LOC cannot be completed, displays 'Something Went Wrong' | Critical | 2021-06-24 14:17 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug
14 | CWBSB-1062 | SBDCO_Applicant_Login to CODAT page is missing | Medium | 2021-06-21 17:34 | karthik.padumati@cwbank.com | In UAT | Brad.Miller@cwbank.com |  | Bug
15 | CWBSB-1054 | SBDCO_submission complete page_Alignment issue and Displays link for personal-onboarding@cwbank.com. | Medium | 2021-06-18 14:57 | karthik.padumati@cwbank.com | Ready for Review |  | angela.ahn@accutive.com | Bug-UI
16 | CWBSB-1053 | SBDCO- Funding - Save Email - Displays link for personal-onboarding@cwbank.com | Medium | 2021-06-18 13:12 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug
17 | CWBSB-1049 | SBDCO - Workspaces - No Business Search Report | Medium | 2021-06-17 15:03 | cheryl.kirchmaier@cwbank.com | In Development | cheryl.kirchmaier@cwbank.com |  | Bug
18 | CWBSB-1039 | SBDCO â€“ Okta â€“ Applicant â€“ Get Customer Details' (T24) Service (Prefill) - No Prefill | Medium | 2021-06-11 16:31 | cheryl.kirchmaier@cwbank.com | Awaiting Information | cheryl.kirchmaier@cwbank.com |  | Bug
19 | CWBSB-1034 | SBDCO_Funding_Method selection page_ Caption Text placement on Mobile is incorrect | Medium | 2021-06-11 11:58 | karthik.padumati@cwbank.com | Backlog |  | lucyliuxin | Bug
20 | CWBSB-1005 | SBDCO - Mobile - Save Confirmation' Email - Resume button cleanup | Medium | 2021-06-01 14:04 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug-UI
21 | CWBSB-999 | SBDCO_Applicant_ Product summary page_Remove button is not working for Complementary Business Products | Medium | 2021-05-31 18:21 | karthik.padumati@cwbank.com | Ready for UAT | karthik.padumati@cwbank.com |  | Bug
22 | CWBSB-994 | SBDCO - Online Banking & Delegates Page - Delete button does not appear to the right side of the page | Medium | 2021-05-28 16:31 | Yigal.Shinderman@cwbank.com | In Development |  | smatharu | Bug-UI
23 | CWBSB-991 | SBDCO - Workspaces - Claim and Decision where MISMATCH, returns with error | Medium | 2021-05-28 15:26 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  | Bug
24 | CWBSB-990 | SBDCO - Applicant - Save application page - incorrect verbiage | Medium | 2021-05-28 12:34 | Yigal.Shinderman@cwbank.com | Approved |  | llaurent | Bug-Text
25 | CWBSB-989 | SMBDCO - Footer link for 'Careers' does not align with the links above | Low | 2021-05-27 17:54 | Yigal.Shinderman@cwbank.com | In Development |  | smatharu | Bug-UI
26 | CWBSB-986 | SBDCO - Landing page of Auth-signer -Online and Mobile Banking text should be displayed as 'Digital Banking' as per the spec v1.7 | Medium | 2021-05-27 13:00 | Venkata.Cherukuri@cwbank.com | Awaiting Information | Venkata.Cherukuri@cwbank.com |  | Bug-Text
27 | CWBSB-984 | SBDCO_ Applicant_ Login to CODAT page static text missing. | Medium | 2021-05-26 18:52 | karthik.padumati@cwbank.com | In UAT | karthik.padumati@cwbank.com |  | Bug-Text
28 | CWBSB-964 | SBDCO - CODAT - prefill - receiving generic error message 'Something went wrong' | Medium | 2021-05-18 17:23 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com | Bug
29 | CWBSB-954 | SBDCO - E2E - Corp â€“ Non-Signer not displayed in T24 for Small Business â€“ Basic Details, should be | Medium | 2021-05-13 17:52 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug
30 | CWBSB-953 | TIMEOUT: Codat page-Images of the accounting packages are not loading, when user clicked continue in the timeout modal popup | Medium | 2021-05-13 15:56 | Venkata.Cherukuri@cwbank.com | Awaiting Information |  | angela.ahn@accutive.com | Bug
31 | CWBSB-940 | SBDCO - Application Approval Email - HTML coding in the email | Medium | 2021-05-10 18:17 | Yigal.Shinderman@cwbank.com | Approved | Yigal.Shinderman@cwbank.com |  | Bug
32 | CWBSB-939 | SBDCO - Dynamic Finish - Cheque - Motive Financial incorrect, should be CWB | Medium | 2021-05-10 17:19 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com | Bug
33 | CWBSB-930 | TIMEOUT: About your Application- Product descriptions are missing when user clicked continue in the timeout modal popup | Medium | 2021-05-04 15:05 | Venkata.Cherukuri@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Bug
34 | CWBSB-927 | SBDCO - Dynamic Finish page - Cheque - Spacing, Font, Buttons and Verbiage issues | Medium | 2021-05-03 14:54 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  | Bug-UI
35 | CWBSB-926 | SBDCO - Applicant - App - eConsent page - Hyperlink redirects user to google | Medium | 2021-05-03 13:14 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com | Bug
36 | CWBSB-924 | SBDCO - Business Disclosures and Signature - Sole Prop - Back button â€“ Goes to App-Flinks page, should not | Medium | 2021-05-03 12:16 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com | Bug
37 | CWBSB-923 | SBDCO - What you've Selected Page: Quantity number is missing inside the product card | Medium | 2021-04-30 18:25 | Sanju.Bhandoria@cwbank.com | In UAT | Sanju.Bhandoria@cwbank.com |  | Bug
38 | CWBSB-878 | SBDCO - Samsung Tab S6 Lite - Portrait - Multiple issues on multiple pages | Medium | 2021-04-21 11:14 | cheryl.kirchmaier@cwbank.com | Awaiting Information |  | dpoole | Bug
39 | CWBSB-864 | SBDCO - Account Selection - Back button â€“ Displays Something Went Wrong _ No modal message | Medium | 2021-04-16 17:39 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com | Bug
40 | CWBSB-862 | SBDCO- A Convenient option page - Flinks Capital does not accept username or password - iPhone 11 Safari Browser | Medium | 2021-04-16 16:09 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  | Bug
41 | CWBSB-860 | SBDCO-More Options- Help URL is showing page not found error | Medium | 2021-04-16 14:53 | Venkata.Cherukuri@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  | Bug
42 | CWBSB-852 | SBDCO â€“ Performance â€“ More About Your Business â€“ selecting from the Industry dropdowns is slow | Medium | 2021-04-15 18:38 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  | Bug
43 | CWBSB-849 | SBDCO - Account Selection â€“ Displays Monthly Free Transactions when value = 0, should not | Medium | 2021-04-15 12:19 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug
44 | CWBSB-813 | SBDCO - Applicant - Application Time Out Page - alignment issue with the Continue button | Medium | 2021-04-09 14:29 | Yigal.Shinderman@cwbank.com | Awaiting Information |  | smatharu | Bug-UI
45 | CWBSB-812 | SBDCO - Owners, Directors and Signers Page - The word Delete is not fully displayed - MAC Safari | Medium | 2021-04-09 12:48 | Yigal.Shinderman@cwbank.com | Backlog |  | angela.ahn@accutive.com | Bug
46 | CWBSB-811 | SBDCO â€“ Business Account Options â€“ More Options â€“ Cannot Save application | Medium | 2021-04-09 12:32 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com | Bug
47 | CWBSB-804 | SBDCO_Applicant_IDScan Page_The title of the ID uploaded is repeating | Medium | 2021-04-08 13:35 | Yigal.Shinderman@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  | Bug
48 | CWBSB-790 | SBDCO - Owners, Directors and Signers - Mandatory msg and caption for phone number does not match FS 2.7 | Medium | 2021-04-07 12:54 | cheryl.kirchmaier@cwbank.com | In UAT |  | lucyliuxin | Bug-Text
49 | CWBSB-736 | SBDCO - Applicant - Non-Signer Owners Page - Validation message is displayed when quebec address is selected, but FS do not state any message for qc selection | Medium | 2021-03-26 20:15 | Yigal.Shinderman@cwbank.com | Backlog |  | lucyliuxin | Bug
50 | CWBSB-727 | SBDCO â€“ Mobile â€“ Authorised Signer eConsent â€“ No error message header displayed | Medium | 2021-03-24 14:52 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  | Bug-UI
51 | CWBSB-721 | SBDCO - Applicant - Birthday & SIN page - on all iPhone devices for Safari - multiple inline messages stay open | Medium | 2021-03-22 17:51 | Yigal.Shinderman@cwbank.com | Awaiting Information |  | kendyl.bachelor | Bug-UI
52 | CWBSB-716 | SBDCO â€“ Mobile â€“ Pages for small business - Next button is displayed highlighted | Medium | 2021-03-19 16:26 | cheryl.kirchmaier@cwbank.com | Awaiting Information |  | rcurran | Bug-UI
53 | CWBSB-705 | UX/UI: Email-spacing issue on top and bottom edge, top bar length | Medium | 2021-03-18 17:32 | karthik.padumati@cwbank.com | In Development |  | smatharu | Bug-UI
54 | CWBSB-697 | UX/UI: Step 1 - Let's get started - Horizontal radio buttons and selection | Medium | 2021-03-18 13:35 | Sanju.Bhandoria@cwbank.com | Awaiting Information | Sanju.Bhandoria@cwbank.com |  | Bug-UI
55 | CWBSB-696 | UX/UI: Access to Digital Banking Page - Missing and incorrect format | Medium | 2021-03-18 13:15 | Sanju.Bhandoria@cwbank.com | Backlog |  | dpoole | Bug-UI
56 | CWBSB-694 | UX/UI: Step 13 - Funding Page - UI spacing issue | Medium | 2021-03-18 12:00 | Chix.DelaLuna@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  | Bug-UI
57 | CWBSB-637 | SBDCO - Security Question - Mobile - Display of two line question | Medium | 2021-03-09 18:24 | Yigal.Shinderman@cwbank.com | Backlog |  | smatharu | Bug-UI
58 | CWBSB-570 | SBDCO - Applicant & Authorized Signer - Flinks Page - Business Application Time Out | Medium | 2021-02-24 11:34 | Sanju.Bhandoria@cwbank.com | In UAT | Chix.DelaLuna@cwbank.com |  | Bug
59 | CWBSB-569 | SBDCO â€“ Authorized Signer â€“ Name & Address page â€“ Error message is displayed regarding dropdown (After Time Out) | Medium | 2021-02-23 20:13 | cheryl.kirchmaier@cwbank.com | Awaiting Information |  | balaji.vasudevan@accutive.com | Bug
60 | CWBSB-567 | SBDCO - Applicant and Authorized Signer - Security Question Page - Progressive Reveal and Fields behavior on navigation | Medium | 2021-02-23 14:45 | priya.chodha@cwbank.com | In UAT | Ian.Hicks@cwbank.com |  | CWB-BA-QA-Review
61 | CWBSB-565 | SBDCO - Authorized Signer & Applicant - Contact Info Page - Issue with Mobile Number field. | Medium | 2021-02-22 19:23 | priya.chodha@cwbank.com | Backlog |  | rcurran | CWB-BA-QA-Review
62 | CWBSB-550 | SBDCO - Security questions Page - Special character â€˜ is not accepted in security answer field. | Medium | 2021-02-18 20:11 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Bug
63 | CWBSB-547 | SBDCO - Your Business Page - Validation message not aligned with the message given in field spec | Medium | 2021-02-18 13:43 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | Bug-UI
64 | CWBSB-470 | SBDCO- Disclosures - Tax Residency page- Validation Message Needs Verbiage change | Medium | 2021-02-05 14:47 | mary.pele@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  | Requirement-Defect
65 | CWBSB-460 | SBDCO - Existing Customer page - Updates required for the form Values | Medium | 2021-02-04 10:45 | priya.chodha@cwbank.com | In UAT | priya.chodha@cwbank.com |  | Bug
66 | CWBSB-412 | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | Medium | 2021-01-26 15:48 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com | CWB-BA-QA-Review
67 | CWBSB-395 | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue (Edge Browser) | Medium | 2021-01-21 15:31 | priya.chodha@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com | Bug
68 | CWBSB-394 | SBDCO - Qualifying questions page- Next and back button appearing twice when clicked | Medium | 2021-01-21 13:27 | mary.pele@cwbank.com | Backlog |  | rcurran | Intermittent

## Sprint Report
Sprint 12 - Started Apr 28 - to complete May 11
Regression Testing Completed |  |  |  | Sprint Report - Sprint 12
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 18** | 12 | 5 | 7 | Defects logged
Failed Tests | - | % Failed | - | Number of Changes | 3 | 3 | 3 | - | All passed
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 2 | 2 | 1 | 1 | CWBSB-848 was taken out of Sprint 12
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 8 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
** Testing the rest of the stories will be covered during E2E
Sprint 13 - Started May 12 - to complete May 25
Regression Testing Completed |  |  |  | Sprint Report - Sprint 13
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 3* | 0 | 0 | 1 | Only 1 story was to be tested in Sprint 13, the rest are for E2E.
Failed Tests | - | % Failed | - | Number of Changes | 1 | 0 | 0 | 1 | Blocked due to test data not being available
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 8 | 7 | 7 | 1 | Untested story associated with a story is Backlog
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 11 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
* Testing the rest of the stories will be covered during E2E
Sprint 14 - Started May 26 - to complete Jun 7
Regression Testing Completed |  |  |  | Sprint Report - Sprint 14
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 8* | 3 | 1 | 4 | Failed and unexecuted tests will be done in Sprint 15
Failed Tests | - | % Failed | - | Number of Changes | 2 | 1 | 1 | 1 | 1 to be addressed in Sprint 15
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 8 | 7 | 7 | 1 | 7 closed defects, to be tested later
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 11 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
Sprint Report - Sprint 15
[5 empty] | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
|  |  |  | Number of Stories | 5* | 2 | 2 | 0
|  |  |  | Number of Changes | 1 | 1 | 1 | 0
|  |  |  | Number of Defects logged by CWB | 6 | 6 | 4 | 2 | Assigned back to Temenos
|  |  |  | Number Defects logged by Temenos | N/A | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
* Testing the rest of the stories will be covered during E2E
Sprint Report - Sprint 16
[5 empty] | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
|  |  |  | Number of Stories | 17* | 16 | 4 | 12 | Stories are either linked to Backlog items or Blocked because of Okta Login credentials
|  |  |  | Number of Changes | 1 | 1 | 1 | 0
|  |  |  | Number of Defects logged by CWB | 8 | 8 | 4 | 4 | Re-opened for Temenos to address
|  |  |  | Number Defects logged by Temenos | N/A | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos