## Small Biz DCO - Test Summary
CWB QA Team - Test Status Report
As of August 18, 2021
Project Name: Digital Program - Small Biz DCO - SIT Phase - Sprint 19
Test Execution for Sprint 19 |  |  |  | Notes: 1. Day 9 of test execution 100% 2. Sprint 19 package includes: a. 40 stories: 29 will be validated, 11 will be validated during E2E b. 1 change requests c. 14 defect fixes – for defects logged by CWB QA Team 3. Refer to Defect Summary Report tab for information on defects
Total Tests Cases Developed | 590 | %
Passed Tests | 487 | % Passed | 82.5424
Failed Tests | 39 | % Failed | 6.6102
Blocked Tests | 64 | % Blocked | 10.8475
Active/Unexecuted | 0 | % Unexecuted | 0
Total # of defects logged (outstanding) | 78
Defects logged from Sprint 19 | 17
Defects logged from previous sprints | 61 | 4 closed

## Defects Status
Status of Defects logged by CWB QA Team - as of August 18, 2021
Defects
|  |  |  | Created defects = | 208
|  |  |  | Resolved defects = | 169
|  |  |  | JIRA counts "Done" = | 130 | and "In UAT" = | 39 | as resolved
|  |  | 78 | outstanding defects* (defects not in "done" status) = |  |  |  |  | 208 | created defects less | 130 | defects in "done" status
Count by Defect Category
|  |  | 44 | Bug (functional issue - not working as specified)
|  |  | 3 | CWB-BA-QA-Review (to review and confirm with CWB BA or QA)
|  |  | 29 | Bug-UI (formatting or layout issues)
|  |  | 0 | Requirement-Defect (issue with functional specs that need to be corrected)
|  |  | 0 | Intermittent (intermittent issues, cannot reproduce, etc.)
|  |  | 2 | Bug-Text (issue with text: misspelling, different from what is in the functional specs)
|  |  | 0 | Change type
|  |  | 78 | Total matches count for outstanding defects
Count by Defect Assignee
|  |  | 30 | Assigned to Temenos/BIG to address
|  |  | 48 | Assigned to CWB to address, for retesting, field specs or requirement issue, to review, questions, investigate further, etc
Refer to Defect Summary tab for info on OUTSTANDING defects for more info on defect breakdown
| Backlog | - defects logged, need to be reviewed by CWB or by Temenos, work is in flight
| Ready for UAT | - defects have been fixed, CWB QA Team needs to validate
| Ready for Review | - defect is ready for Temenos review
| In Development | - solution for defect is in development
| Blocked | - waiting for questions/for confirmation, clarification of requirements, other issues impacting work to progress
| In Test | - with Temenos for their testing
| In UAT | - with CWB for their testing
| Done | - fix for defect has been validated working, issue is resolved, defect is closed

## Defect Summary Report
Summary of Outstanding Defects - logged by CWB QA Team - as of August 18
Assignee
| Issue key | Priority | Summary | Created | Reporter | Status | CWB | Temenos | Fix Version/s | Category
1 | CWBSB-395 | Medium | SBDCO- Contact Info Page - Auto Fill and Recaptcha Issue (Edge Browser) | 2021-01-22 07:31 | priya.chodha@cwbank.com | Backlog | priya.chodha@cwbank.com |  |  | Bug
2 | CWBSB-412 | Medium | SBDCO -Name and Address Page -Issue with Special Characters allowed in the fields | 2021-01-27 07:48 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | CWB-BA-QA-Review
3 | CWBSB-460 | Medium | SBDCO - Existing Customer page - Updates required for the form Values | 2021-02-05 02:45 | priya.chodha@cwbank.com | In UAT | priya.chodha@cwbank.com |  |  | Bug
4 | CWBSB-547 | Medium | SBDCO - Your Business Page - Validation message not aligned with the message given in field spec | 2021-02-19 05:43 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug-UI
5 | CWBSB-550 | Medium | SBDCO - Security questions Page - Special character â€˜ is not accepted in security answer field. | 2021-02-19 12:11 | priya.chodha@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
6 | CWBSB-570 | Medium | SBDCO - Applicant & Authorized Signer - Flinks Page - Business Application Time Out | 2021-02-25 03:34 | Sanju.Bhandoria@cwbank.com | In UAT | Chix.DelaLuna@cwbank.com |  |  | Bug
7 | CWBSB-637 | Medium | SBDCO - Security Question - Mobile - Display of two line question | 2021-03-10 10:24 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
8 | CWBSB-716 | Medium | SBDCO â€“ Mobile â€“ Pages for small business - Next button is displayed highlighted | 2021-03-20 07:26 | cheryl.kirchmaier@cwbank.com | Approved |  | smatharu |  | Bug-UI
9 | CWBSB-721 | Medium | SBDCO - Applicant - Birthday & SIN page - on all iPhone devices for Safari - multiple inline messages stay open | 2021-03-23 08:51 | Yigal.Shinderman@cwbank.com | Awaiting Information |  | gnunez |  | Bug-UI
10 | CWBSB-727 | Medium | SBDCO â€“ Mobile â€“ Authorised Signer eConsent â€“ No error message header displayed | 2021-03-25 05:52 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug-UI
11 | CWBSB-790 | Medium | SBDCO - Owners, Directors and Signers - Mandatory msg and caption for phone number does not match FS 2.7 | 2021-04-08 02:54 | cheryl.kirchmaier@cwbank.com | In UAT |  | lucyliuxin |  | Bug-Text
12 | CWBSB-804 | Medium | SBDCO_Applicant_IDScan Page_The title of the ID uploaded is repeating | 2021-04-09 03:35 | Yigal.Shinderman@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  |  | Bug
13 | CWBSB-811 | Medium | SBDCO â€“ Business Account Options â€“ More Options â€“ Cannot Save application | 2021-04-10 02:32 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
14 | CWBSB-812 | Medium | SBDCO - Owners, Directors and Signers Page - The word Delete is not fully displayed - MAC Safari | 2021-04-10 02:48 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug
15 | CWBSB-862 | Medium | SBDCO- A Convenient option page - Flinks Capital does not accept username or password - iPhone 11 Safari Browser | 2021-04-17 06:09 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug
16 | CWBSB-852 | Medium | SBDCO â€“ Performance â€“ More About Your Business â€“ selecting from the Industry dropdowns is slow | 2021-04-16 08:38 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
17 | CWBSB-864 | Medium | SBDCO - Account Selection - Back button â€“ Displays Something Went Wrong _ No modal message | 2021-04-17 07:39 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
18 | CWBSB-878 | Medium | SBDCO - Samsung Tab S6 Lite - Portrait - Multiple issues on multiple pages | 2021-04-22 01:14 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
19 | CWBSB-924 | Medium | SBDCO - Business Disclosures and Signature - Sole Prop - Back button â€“ Goes to App-Flinks page, should not | 2021-05-04 02:16 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
20 | CWBSB-939 | Medium | SBDCO - Dynamic Finish - Cheque - Motive Financial incorrect, should be CWB | 2021-05-11 07:19 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
21 | CWBSB-964 | Medium | SBDCO - CODAT - prefill - receiving generic error message 'Something went wrong' | 2021-05-19 07:23 | cheryl.kirchmaier@cwbank.com | In UAT |  | balaji.vasudevan@accutive.com |  | Bug
22 | CWBSB-986 | Medium | SBDCO - Landing page of Auth-signer -Online and Mobile Banking text should be displayed as 'Digital Banking' as per the spec v1.7 | 2021-05-28 03:00 | Venkata.Cherukuri@cwbank.com | Awaiting Information | Venkata.Cherukuri@cwbank.com |  |  | Bug-Text
23 | CWBSB-991 | Medium | SBDCO - Workspaces - Claim and Decision where MISMATCH, returns with error | 2021-05-29 05:26 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
24 | CWBSB-1039 | Medium | SBDCO â€“ Okta â€“ Applicant â€“ Get Customer Details' (T24) Service (Prefill) - No Prefill | 2021-06-12 06:31 | cheryl.kirchmaier@cwbank.com | Awaiting Information | Chix.DelaLuna@cwbank.com |  |  | Bug
25 | CWBSB-1078 | Medium | SBDCO - Lending Decision - No mandatory message for the 'I agree' checkbox | 2021-06-26 06:49 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
26 | CWBSB-1082 | Medium | SBDCO - MOBILE - Business eConsent and Applicant eConsent - error banner not displayed | 2021-06-29 03:06 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
27 | CWBSB-1222 | Medium | SBDCO - Services Selection - LOC - View Features link -incorrect URL | 2021-07-22 06:46 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
28 | CWBSB-1223 | Medium | SBDCO - Remove Confirmation modal is not as per Figma | 2021-07-22 08:53 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug-UI
29 | CWBSB-1230 | Medium | SBDCO - Authorized Signer - Lending Declined - Back - Start over does not cancel application | 2021-07-27 03:49 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug
30 | CWBSB-1235 | Medium | SBDCO - Product Review - Lending Product - No banner displayed, should be | 2021-07-28 04:11 | cheryl.kirchmaier@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug
31 | CWBSB-1248 | Medium | SBDCO - Applicant - ID Scan page - Back button - Confirmation Modal not displayed as per Figma | 2021-07-30 02:48 | cheryl.kirchmaier@cwbank.com | In UAT | Chix.DelaLuna@cwbank.com |  |  | Bug-UI
32 | CWBSB-1306 | Medium | SBDCO - Non-Signing Owners - Residential address - Manual - allows special characters - specifically \ | 2021-08-10 04:21 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
33 | CWBSB-1314 | Medium | SBDCO - Previously Submitted - Displays extra text, should not | 2021-08-12 00:22 | cheryl.kirchmaier@cwbank.com | Blocked | cheryl.kirchmaier@cwbank.com |  |  | Bug
34 | CWBSB-1317 | Medium | SBDCO - Authorized Signer - Name & Address - Address field line should be the same as applicant | 2021-08-12 02:31 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug-UI
35 | CWBSB-1347 | Medium | SBDCO - Await Authorized Signers' Page - Email launched from hyperlink should display the actual app ID, not html | 2021-08-19 07:13 | cheryl.kirchmaier@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug
36 | CWBSB-1341 | High | SBDCO - Authorized Signer - Lending Declined - personal hard pull failure - returns with Submission Complete | 2021-08-18 07:05 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug
37 | CWBSB-1336 | Medium | SBDCO - Lending Decision - Corp - Commercial and Personal Credit Bureau call failure | 2021-08-17 07:28 | cheryl.kirchmaier@cwbank.com | Backlog |  | andy.lepage@bitsinglass.com |  | Bug
38 | CWBSB-1329 | Low | SBDCO - More About Your Business - Validation messages do not match latest FS | 2021-08-14 06:06 | cheryl.kirchmaier@cwbank.com | Backlog | Ian.Hicks@cwbank.com |  |  | Bug
39 | CWBSB-1327 | Medium | SBDCO - Resume Business Form' Page - displays an X that is not in latest FS | 2021-08-14 03:15 | cheryl.kirchmaier@cwbank.com | Approved |  | lucyliuxin |  | Bug
40 | CWBSB-1325 | Medium | SBDCO - Workspaces - Login returns with error | 2021-08-13 06:15 | cheryl.kirchmaier@cwbank.com | Approved |  | balaji.vasudevan@accutive.com |  | Bug
41 | CWBSB-1305 | Medium | SBDCO_Auth signer_ e-consent page_Displays Digital lending agreement when no LOC selected | 2021-08-10 04:13 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  |  | Bug
42 | CWBSB-1289 | Medium | SBDCO - Business Disclosures and Signature - hyperlinks return with Page Not Found | 2021-08-07 03:29 | cheryl.kirchmaier@cwbank.com | Backlog |  | Ian.Hicks@cwbank.com |  | Bug
43 | CWBSB-1279 | Medium | SBDCO - Services Selection and Product Review - LOC banner has incorrect verbiage | 2021-08-06 08:43 | cheryl.kirchmaier@cwbank.com | Approved |  | lucyliuxin |  | Bug
44 | CWBSB-1234 | Medium | SBDCO - Business eConsent Page - static text appears for non LOC | 2021-07-28 03:47 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug
45 | CWBSB-1232 | Medium | SBDCO - Not Qualified info page - Timeout screen does not appear | 2021-07-28 01:42 | Yigal.Shinderman@cwbank.com | Backlog | Yigal.Shinderman@cwbank.com |  |  | Bug
46 | CWBSB-1195 | Medium | SBDCO - Saved Application Email - Forward Email - the Resume button duplicates | 2021-07-21 01:47 | cheryl.kirchmaier@cwbank.com | Backlog |  | manish.varia@accutive.com |  | Bug
47 | CWBSB-1073 | Medium | SBDCO_ The Applicant and Co-applicant's birthday do not pre-populate when uploading a drivers license | 2021-06-25 08:06 | karthik.padumati@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug
48 | CWBSB-1072 | Medium | SBDCO_Applicat_ Applicant e-consent page_Text is not removed as per the updated Field spec. | 2021-06-25 07:35 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  |  | Bug
49 | CWBSB-1062 | Medium | SBDCO_Applicant_Login to CODAT page is missing | 2021-06-22 07:34 | karthik.padumati@cwbank.com | In UAT | Brad.Miller@cwbank.com |  |  | Bug
50 | CWBSB-1034 | Medium | SBDCO_Funding_Method selection page_ Caption Text placement on Mobile is incorrect | 2021-06-12 01:58 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  |  | Bug
51 | CWBSB-999 | Medium | SBDCO_Applicant_ Product summary page_Remove button is not working for Complementary Business Products | 2021-06-01 08:21 | karthik.padumati@cwbank.com | In UAT |  | nurzhamal.crutchfield |  | Bug
52 | CWBSB-953 | Medium | TIMEOUT: Codat page-Images of the accounting packages are not loading, when user clicked continue in the timeout modal popup | 2021-05-14 05:56 | Venkata.Cherukuri@cwbank.com | In UAT | Venkata.Cherukuri@cwbank.com |  |  | Bug
53 | CWBSB-940 | Medium | SBDCO - Application Approval Email - HTML coding in the email | 2021-05-11 08:17 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug
54 | CWBSB-926 | Medium | SBDCO - Applicant - App - eConsent page - Hyperlink redirects user to google | 2021-05-04 03:14 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug
55 | CWBSB-860 | Medium | SBDCO-More Options- Help URL is showing page not found error | 2021-04-17 04:53 | Venkata.Cherukuri@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  |  | Bug
56 | CWBSB-1332 | Medium | SBDCO_Applicant_ App Alternate IDV page_Manual IDV modal "No,goback" button issue. | 2021-08-14 07:54 | karthik.padumati@cwbank.com | Backlog |  | smatharu |  | Bug-UI
57 | CWBSB-1330 | Medium | SBDCO_Applicant_ Owners directors+signers page_Delete modal issue. | 2021-08-14 06:25 | karthik.padumati@cwbank.com | Backlog | karthik.padumati@cwbank.com |  |  | Bug-UI
58 | CWBSB-1328 | Medium | SBDCO_Applicant_Existing customer check page_Log into digital banking hyperlink error. | 2021-08-14 06:05 | karthik.padumati@cwbank.com | Blocked | Ian.Hicks@cwbank.com |  |  | Bug-UI
59 | CWBSB-1321 | Low | SBDCO - Authorized Signer -Submission Complete page- text not centered as per Figma | 2021-08-12 09:31 | cheryl.kirchmaier@cwbank.com | Backlog |  | lucyliuxin |  | Bug-UI
60 | CWBSB-1276 | Medium | SBDCO - Mobile - 'Form Error' Page - UI/UX issues | 2021-08-06 02:00 | cheryl.kirchmaier@cwbank.com | Backlog |  | balaji.vasudevan@accutive.com |  | Bug-UI
61 | CWBSB-1253 | Medium | SBDCO - 'Previously Submitted' Page - Alignment is not as per Figma | 2021-07-31 04:30 | cheryl.kirchmaier@cwbank.com | Backlog | cheryl.kirchmaier@cwbank.com |  |  | Bug-UI
62 | CWBSB-1252 | Medium | SBDCO - Applicant - Modal not aligned on devices | 2021-07-31 04:08 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
63 | CWBSB-1233 | Medium | SBDCO_Applicant_ Manual IDV Page_Alignment issue (Heading) in Mobile | 2021-07-28 03:10 | karthik.padumati@cwbank.com | Backlog |  | angela.ahn@accutive.com |  | Bug-UI
64 | CWBSB-1225 | Medium | SBDCO - App - IDScan Page - Mobile - Error message display - Questions | 2021-07-23 05:49 | cheryl.kirchmaier@cwbank.com | Blocked | Kelvin.Fernando@cwbank.com |  |  | Bug-UI
65 | CWBSB-1213 | Medium | SBDCO - Applicant and Authorized Signer- Flinks page - Inconsistent margin & Spacing | 2021-07-21 09:05 | Venkata.Cherukuri@cwbank.com | In UAT | Chix.DelaLuna@cwbank.com |  |  | Bug-UI
66 | CWBSB-1211 | Medium | SBDCO - Lending Decision - Tight spacing | 2021-07-21 08:45 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug-UI
67 | CWBSB-1209 | Medium | SBDCO - More About Your Business - Icon alignment | 2021-07-21 08:32 | cheryl.kirchmaier@cwbank.com | In UAT | cheryl.kirchmaier@cwbank.com |  |  | Bug-UI
68 | CWBSB-1207 | Medium | SBDCO - Applicant and Authorized Signer flow- Lets get started page - Font size is inconsistent | 2021-07-21 08:13 | Venkata.Cherukuri@cwbank.com | Backlog |  | lucyliuxin |  | Bug-UI
69 | CWBSB-1201 | Medium | SBDCO - Applicant and Authorized Signer- Name and Address page - Font size inconsistency | 2021-07-21 07:48 | cheryl.kirchmaier@cwbank.com | Approved |  | smatharu |  | Bug-UI
70 | CWBSB-1054 | Medium | SBDCO_submission complete page_Alignment issue and Displays link for personal-onboarding@cwbank.com. | 2021-06-19 04:57 | karthik.padumati@cwbank.com | In UAT |  | angela.ahn@accutive.com |  | Bug-UI
71 | CWBSB-989 | Low | SMBDCO - Footer link for 'Careers' does not align with the links above | 2021-05-28 07:54 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
72 | CWBSB-927 | Medium | SBDCO - Dynamic Finish page - Cheque - Spacing, Font, Buttons and Verbiage issues | 2021-05-04 04:54 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
73 | CWBSB-813 | Medium | SBDCO - Applicant Time Out Page- Alignment issue with the Continue button | 2021-04-10 04:29 | Yigal.Shinderman@cwbank.com | In UAT | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
74 | CWBSB-697 | Medium | UX/UI: Step 1 - Let's get started - Horizontal radio buttons and selection | 2021-03-19 04:35 | Sanju.Bhandoria@cwbank.com | Awaiting Information | Sanju.Bhandoria@cwbank.com |  |  | Bug-UI
75 | CWBSB-696 | Medium | UX/UI: Access to Digital Banking Page - Missing and incorrect format | 2021-03-19 04:15 | Sanju.Bhandoria@cwbank.com | In Test | Sanju.Bhandoria@cwbank.com |  |  | Bug-UI
76 | CWBSB-694 | Medium | UX/UI: Step 13 - Funding Page - UI spacing issue | 2021-03-19 03:00 | Chix.DelaLuna@cwbank.com | Awaiting Information | Yigal.Shinderman@cwbank.com |  |  | Bug-UI
77 | CWBSB-567 | Medium | SBDCO - Applicant and Authorized Signer - Security Question Page - Progressive Reveal and Fields behavior on navigation | 2021-02-24 06:45 | priya.chodha@cwbank.com | In UAT | Ian.Hicks@cwbank.com |  |  | CWB-BA-QA-Review
78 | CWBSB-565 | Medium | SBDCO - Authorized Signer & Applicant - Contact Info Page - Issue with Mobile Number field. | 2021-02-23 11:23 | priya.chodha@cwbank.com | Blocked |  | gnunez |  | CWB-BA-QA-Review

## Sprint Report
Sprint 12 - Started Apr 28 - to complete May 11
Regression Testing Completed |  |  |  | Sprint Report - Sprint 12
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 18** | 12 | 5 | 7 | Defects logged
Failed Tests | - | % Failed | - | Number of Changes | 3 | 3 | 3 | - | All passed
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 2 | 2 | 1 | 1 | CWBSB-848 was taken out of Sprint 12
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 8 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
** Testing the rest of the stories will be covered during E2E
Sprint 13 - Started May 12 - to complete May 25
Regression Testing Completed |  |  |  | Sprint Report - Sprint 13
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 3* | 0 | 0 | 1 | Only 1 story was to be tested in Sprint 13, the rest are for E2E.
Failed Tests | - | % Failed | - | Number of Changes | 1 | 0 | 0 | 1 | Blocked due to test data not being available
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 8 | 7 | 7 | 1 | Untested story associated with a story is Backlog
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 11 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
* Testing the rest of the stories will be covered during E2E
Sprint 14 - Started May 26 - to complete Jun 7
Regression Testing Completed |  |  |  | Sprint Report - Sprint 14
Total Regression Test Cases To Date | TBD | % |  |  | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
Passed Tests | - | % Passed | - | Number of Stories | 8* | 3 | 1 | 4 | Failed and unexecuted tests will be done in Sprint 15
Failed Tests | - | % Failed | - | Number of Changes | 2 | 1 | 1 | 1 | 1 to be addressed in Sprint 15
Blocked Tests | - | % Blocked | - | Number of Defects logged by CWB | 8 | 7 | 7 | 1 | 7 closed defects, to be tested later
Active/Unexecuted | - | % Unexecuted | - | Number Defects logged by Temenos | 11 | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
Sprint Report - Sprint 15
[5 empty] | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
|  |  |  | Number of Stories | 5* | 2 | 2 | 0
|  |  |  | Number of Changes | 1 | 1 | 1 | 0
|  |  |  | Number of Defects logged by CWB | 6 | 6 | 4 | 2 | Assigned back to Temenos
|  |  |  | Number Defects logged by Temenos | N/A | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
* Testing the rest of the stories will be covered during E2E
Sprint Report - Sprint 16
[5 empty] | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
|  |  |  | Number of Stories | 17* | 16 | 4 | 12 | Stories are either linked to Backlog items or Blocked because of Okta Login credentials
|  |  |  | Number of Changes | 1 | 1 | 1 | 0
|  |  |  | Number of Defects logged by CWB | 8 | 8 | 4 | 4 | Re-opened for Temenos to address
|  |  |  | Number Defects logged by Temenos | N/A | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
Sprint Report - Sprint 17
[5 empty] | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
|  |  |  | Number of Stories | 5* | 5 | 0 | 5 | Stories are either linked to Backlog items or in UAT ready to test for next sprint
|  |  |  | Number of Changes | 0 | 0 | 0 | 0
|  |  |  | Number of Defects logged by CWB | 12 | 12 | 9 | 3 | Re-opened for Temenos to address/ Prefill issues still not resolved
|  |  |  | Number Defects logged by Temenos | N/A | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos
Sprint Report - Sprint 18
[5 empty] | Planned/Delivered | Tested | Passed | Failed/ Not Tested | Notes
|  |  |  | Number of Stories | 15* | 15 | 6 | 9 | Stories are either linked to Backlog items or in UAT ready to test for next sprint
|  |  |  | Number of Changes | 3 | 3 | 0 | 3 | In review with Temenos or Blocked
|  |  |  | Number of Defects logged by CWB | 11 | 11 | 6 | 5 | Re-opened for Temenos to address/ Prefill issues still not resolved
|  |  |  | Number Defects logged by Temenos | N/A | N/A | N/A | N/A | CWB QA Team does not test defects logged by Temenos