## SB DCO form
Small Business DCO checklist - Small Business+Applicant form
Current spec | v2.7 | Includes text updates from CS
WIP spec | v2.8
Journey Flow page | Base field spec | Jira story | Base wireframe | Digital team review | Final wireframe | Development approved | Wording Jira story | Wording review (CS) | Final approval (CM/SS) | Notes / other work required
1. Qualifying Questions | Done | CWBSB-12 | Done | Done | Done | Done | CWBSB-174 | Done
1a. Not Qualified Info Page | Done | CWBSB-13 | Done | Done | Done | Done | CWBSB-176 | Done |  | Email and contact info to be added
2. Existing Customer Check | Done | CWBSB-175 | Done | Done | Done | Done | CWBSB-219 | Done |  | Temenos pulled into sprint 3, although was not approved for dev. CWBSB-271 for content/link/control updates (auth path).
Existing Customer Check - update for authenticated path |  | CWBSB-271
3. Contact Info | Done | CWBSB-14 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-74 | Done
4. Verify Mobile | Done | CWBSB-16 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-75 | Done |  | Uses standard Resume page - see tab F. (CWBSB-53)
5. Business eConsent | Done | CWBSB-19 | Done | Done | Done | Done | CWBSB-171 | Done
6. About Your Business-Codat |  | CWBSB-20 | [7 empty] | Deprecated - single page now - see below
7. Log into Codat | Done | CWBSB-192 | Done | Done | Done | Done | CWBSB-180 | Done
8. Your Business | Done | CWBSB-24 | Done | Done | Done | Done | CWBSB-305 | Done
9. More About Your Business | Done | CWBSB-25 | Done | Done | Done | Done | CWBSB-306 | Done
10. Applicant-ID Scan | Done | CWBSB-38 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-76 | Done
11. Applicant-Name & Address | Done | CWBSB-39 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-77 | Done
12. Applicant-Birthday, SIN & Occupation | Done | CWBSB-40 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-78 | Done
12a. Security Question | Done | CWBSB-480 | Done | Done | Done | Done | CWBSB-646 | Done |  | Net new page as question did not previously have a home in the JF
13. Applicant-eConsent | Done | CWBSB-41 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-90 | Done |  | CWBSB-485 update to include debit card+move checkbox
14. Applicant-Alternate IDV | Done | CWBSB-182 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-183 | Done
15. Applicant-Flinks | Done | CWBSB-42 | n/a (reused) | n/a (reused) | n/a (reused) | Done | no changes | Done
16. Applicant-Manual IDV | Done | CWBSB-220 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-221 | Done
17. Your Role | Done | CWBSB-295 | Done | Done | Done | Done | CWBSB-307 | Done
18. Owners, Directors & Signers | Done | CWBSB-294 | Done | Done | Done | Done | CWBSB-308 | Done
18a. Non-signing Owners | Done | CWBSB-324 | Done | Done | Done | Done | CWBSB-429 | Done
19a. Disclosures-Tax Residency | Done | CWBSB-190 | Done | Done | Done | Done | CWBSB-191 | Done
19. Business Disclosures | Done | CWBSB-44 | Done | Done | Done | Done | CWBSB-181 | Done |  | Add links to all referenced docs (disclosures, T&C)
20. Await Auth Signers info page | Done | CWBSB-254 | Done | Done | Done | Done | CWBSB-393 | Done |  | New page - info to tell the applicant what happens next.
21. Account Options | Done | CWBSB-45 | Done | Done | Done | Done | CWBSB-390 | Done
22. Complementary Services | Done | CWBSB-46 | Done | Done | Done | Done | CWBSB-428 | Done
23. Online Banking+Delegates | Done | CWBSB-388 | Done | Done | Done | Done | CWBSB-662 | Done
A. Generic Error | Done | CWBSB-48 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-92 | Done
B. Manual Review | Done | CWBSB-49 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-93 | Done
C. Decline | Done | CWBSB-50 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-94 | Done
D. Cancel | Done | CWBSB-55 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-213 | Done
E. Save | Done | CWBSB-52 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-177 | Done
F. Resume | Done | CWBSB-53 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-178 | Done
G. Time Out | Done | CWBSB-56 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-197 | Done |  | CWBSB-196 NFR time out parameters. No changes from implemented version, deprecated verbiage story
H. Progress | Done | CWBSB-243 | n/a (reused) | n/a (reused) | n/a (reused)
I. Previously Submitted | Done | CWBSB-57 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-95 | Done
J. Concurrent App | Done | CWBSB-263 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-436 | Done
K. Unable to Resume | Deprecated | CWBSB-255 |  |  |  |  | CWBSB-396 |  |  | Not needed
L. Submission Complete | Done | CWBSB-521 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-533 | Done |  | Based on I. Previously Submitted - used for exit from "Not Qualified Info Page"
M. Await Auth Signers modal | Done | CWBSB-690 |  |  |  |  | CWBSB-723
Not Qualified | Deprecated
Failed Screening | Deprecated
Authorized Signers | Deprecated | CWBSB-43 | [7 empty] | Deprecated in favour of Owners, Directors and Signers CWBSB-294
Navigation - progress bar
Progress bar - step names | Done | [8 empty] | Step names CWBSB-575 2021-03-15

## Auth Signer form
Small Business DCO checklist - Auth Signer form
Current spec | v1.6
WIP spec | v1.7
Journey Flow page | Base field spec | Jira story | Base wireframe | Digital team review | Final wireframe | Development approved | Wording Jira story | Wording review (CS) | Final approval (CM/SS) | Notes / other work required
1. Entry page | Done | CWBSB-60 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-96 | Done |  | Uses standard Resume page - see tab F. (CWBSB-240)
2. Landing Page | Done | CWBSB-61 | Done | Done | Done | Done | CWBSB-279 | Done
3. Existing Customer Check | Done | CWBSB-245 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-616 | Done
Existing Customer Check - update for authenticated path |  | CWBSB-317
4. Contact Info | Done | CWBSB-166 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-172 | Done
4a. Mobile Verify | Done | CWBSB-167 | n/a (reused) | n/a (reused) | n/a (reused) | Done |  | Done |  | Uses standard Resume page - see tab F. (CWBSB-240)
5. Qualifying Questions | Done | CWBSB-63 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-222 | Done
6. IDScan | Done | CWBSB-62 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-97 | Done
7. Name & Address | Done | CWBSB-64 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-173 | Done
8. Birthday, SIN & Occupation | Done | CWBSB-71 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-98 | Done |  | CS reviewed - no wording updates - moved CWBSB-98 to OOS
9. Security Question | Done | CWBSB-481 | Done | Done | Done | Done | CWBSB-647 | Done
10. eConsent | Done | CWBSB-72 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-223 | Done |  | CWBSB-486 update to include debit card+move checkbox
11. Alternate IDV | Done | CWBSB-228 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-635 | Done
12. Flinks | Done | CWBSB-229 | n/a (reused) | n/a (reused) | n/a (reused) | Done | n/a | Done |  | No wording changes
13. Manual IDV | Done | CWBSB-230 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-636 | Done
14. Dynamic Disclosures | Deprecated | CWBSB-73 | [7 empty] | No disclosures/T&C required (confirmed with Legal)
A. Generic Error | Done | CWBSB-235 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-92 | Done |  | Reusing verbiage story for both main form and Auth Signer
B. Manual Review | Deprecated | CWBSB-236 | n/a (reused) | n/a (reused) | n/a (reused) |  | n/a |  |  | Deprecated as no decisioning in Auth Signer form to generate this page
C. Decline | Done | CWBSB-237 | n/a (reused) | n/a (reused) | n/a (reused) | Done | n/a | Done |  | No changes to verbiage from implemented version
D. Cancel | Done | CWBSB-238 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-213 | Done |  | Reusing verbiage story for both main form and Auth Signer
E. Save | Done | CWBSB-239 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-177 | Done |  | Reusing verbiage story for both main form and Auth Signer
F. Resume | Done | CWBSB-240 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-178 | Done |  | Reusing verbiage story for both main form and Auth Signer
G. Time Out | Done | CWBSB-241 | n/a (reused) | n/a (reused) | n/a (reused) | Done | n/a | Done |  | No changes to verbiage from implemented version
H. Progress | Done | CWBSB-244 | n/a (reused) | n/a (reused) | n/a (reused) | Done | n/a |  |  | Cloned from CWBSB-243
I. Previously Submitted | Done | CWBSB-242 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-95 | Done |  | Reusing verbiage story for both main form and Auth Signer
J. Submission Complete | Done | CWBSB-522 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-533 | Done |  | Based on I. Previously Submitted. Use for exit (end of Auth Signer form). Reusing verbiage story for both main form and Auth Signer
9. Account Options | DEPRECATED | CWBSB-246 | [7 empty] | Confirmed deprecated 1/22 - nothing to put on this page.
Navigation - progress bar
Progress bar - step names | Done | [8 empty] | Step names CWBSB-575 2021-03-15

## Funding form
Small Business DCO checklist - Funding form
Current spec | v1.1
WIP spec
Journey Flow page | Base field spec | Jira story | Base wireframe | Digital team review | Final wireframe | Development approved | Wording story | Wording review (CS) | Final approval (CM/SS) | Notes / other work required
SmallBiz Funding Form |  | CWBSB-156 (Epic)
1. Application Approval | Done | CWBSB-248 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-450 | Done
Application Approval - update for authenticated path | WIP
1a. PAN Confirmation (modal) | Done | CWBSB-267 | n/a (reused) | n/a (reused) | n/a (reused) | Done |  |  |  | Need for this page depends on whether PAN being exposed to users
2. Method Selection | Done | CWBSB-249 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-437 | Done
3. Me-to-Me Session Management (Flinks) | Done | CWBSB-250 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-457 | Done
4. Funds Transfer | Done | CWBSB-251 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-453 | Done
4a. Transfer Error | Done | CWBSB-252 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-454 | Done
5. Dynamic Finish | Done | CWBSB-253 | n/a (reused) | n/a (reused) | n/a (reused) | Done | CWBSB-456 | Done

## Product Selector
Small Business DCO checklist - Product Selector
Current spec | DCO Product Selector Field Spec v2.3
WIP spec | v2.4
Journey flow / page sequence
Journey Flow page | Base field spec | Jira story | Base wireframe | Digital team review | Final wireframe | Development approved | Wording review (CS) | Final approval (CM/SS) | Notes / other work required
1. Welcome page-Business | Deprecated | CWBSB-201
Question SB1 (Product Category) | Deprecated | CWBSB-198
Question SB2 | Deprecated
2. Account Selection (Product List) | Done | CWBSB-200 | Done | Done | Done | Done
2a. Account Details (modal) | Deprecated | CWBSB-204 | [6 empty] | Confirmed 2/12 we will direct to CWB website for "learn more" details
Question SB3 | Deprecated
Question SB4 | Deprecated
3. Service Selection (Complementary Product) | Done | CWBSB-592 | Done | Done | Done | Done |  |  | Original story CWBSB-202 replaced with 592
3a. Service Details (modal) | Deprecated | CWBSB-511
4. Checkout | Deprecated
5. Account Details (Product Review) | Done | CWBSB-199 | Done | Done | Done | Done
Final verbiage updates | WIP | CWBSB-938 | [6 empty] | Wording updates combined in one story for product selection pages
Product cards revised UX |  | CWBSB-658 |  |  |  | Done
Product Catalogue Field Matrix (accounts) | Done | See Temenos tab
Product Specification (accounts) | WIP | See Temenos tab
Product Catalogue Field Matrix (complementary) | Done
Product Specification (complementary) | WIP
UX pending
Guided questions, handling of Complementary Products/Services

## Integration
Small Business DCO checklist - Integration
Description | System/vendor | Requirements | Spec document | Jira story | Digital team review | Temenos review | Notes / other work required
T24 integration via Mulesoft | T24 |  |  | CWBSB-35 (Epic) | WIP | WIP | Total 37 stories in this Epic
T24-Dupe CIF check | T24 | Email confirmation | IRD-CH-33 Small Business DCO Part 1 v2 | CWBSB-36 CWBSB-37 | Done
T24-Create CIF (non-personal) | T24 | Business CIF reqts |  | CWBSB-99 CWBSB-100 CWBSB-101 | Done
T24-Create/update CIF (personal) | T24 | Personal CIF reqts |  | CWBSB-109 CWBSB-110 CWBSB-121 CWBSB-122 | Done
T24-Create business account | T24 | Business Account reqts | IRD-CH-33 Small Business DCO Part 2 | CWBSB-105 CWBSB-106 CWBSB-107 | Done
T24-PAN create (business / applicant / auth signers) | T24 |  | IRD-CH-33 Small Business DCO Part 3 | CWBSB-115 CWBSB-116 CWBSB-126 CWBSB-127 CWBSB-128 | Done
T24-Contact Log | T24 |  |  | CWBSB-102 CWBSB-103 CWBSB-104 CWBSB-112 CWBSB-124 | Done
T24-PAC create (business / applicant / auth signers) |  |  |  | CWBSB-117 CWBSB-118 CWBSB-119 CWBSB-130 CWBSB-131 | Deprecated |  | No PAC services required - replaced by Okta authentication
T24-Posting Restriction | [6 empty] | SAS AML not in scope for R1
Canada Post Address Complete | Canada Post | No change from personal/Motive |  | CWBSB-66 (Epic) | WIP | Done
Canada Post-SmallBiz Full Service Integration | Canada Post | No change from personal/Motive |  | CWBSB-67 | n/a | Done
Canada Post-Auth Signer Full Service Integration | Canada Post | No change from personal/Motive |  | CWBSB-68 | n/a | Done
Canada Post-Auth Signer Form Integration | Canada Post | No change from personal/Motive |  | CWBSB-70 | n/a | Done
Canada Post-SmallBiz Form integration | Canada Post | No change from personal/Motive |  | CWBSB-69 | n/a | Done
Business Search | ThirdStream |  |  | CWBSB-26 (Epic) | WIP | WIP
Business Search-Full Service Integration | ThirdStream |  |  | CWBSB-28 | n/a | Done
Business Search-data for comparison | ThirdStream | SB DCO Business data elements for Workspaces 2021-03-08 |  | CWBSB-329 | Done | Done
Business Search-offline handling | ThirdStream | Business Search-decision tree-draft | Business Search-Polling Rules v1.1 2021-02-24 |  | Done | Done | Document process & requirements for offline handling
Codat-business prefill | Codat |  |  | CWBSB-21 (Epic) | WIP | WIP
Fraud Check for business (Threatmetrix) | Threatmetrix | No change from personal/Motive |  | CWBSB-29 (Epic) CWBSB-31 CWBSB-32 | Done | Done
Individual-IDScan | ID Scan | No change from personal/Motive |  | CWBSB-86 (Epic) | Done | Done
Individual AML-IDV (Equifax, Enstream) | Equifax | No change from personal/Motive |  | CWBSB-205 (Epic) CWBSB-206 CWBSB-207 | Done | Done
Individual Fraud check (Citadel, Threatmetrix) | Equifax | No change from personal/Motive |  | CWBSB-211 (Epic) CWBSB-216 CWBSB-217 | Done | Done
Individual Credit Bureau | Equifax | No change from personal/Motive |  | CWBSB-212 (Epic) CWBSB-214 CWBSB-215 | Done | Done
Individual Alternate IDV (Flinks) | Flinks | No change from personal/Motive |  | CWBSB-218 (Epic) CWBSB-224 CWBSB-225 | Done | Done
SAS AML for business |  |  |  | CWBSB-30 (Epic) CWBSB-33 CWBSB-34 | Deprecated |  | SAS AML not in scope for R1
Application delivery (Filenet) | Temenos |  |  | CWBSB-80 (Epic) | Not started | Not started
Application delivery-Small Business complete | Temenos |  |  | CWBSB-168 | Not started | Not started
Application delivery-Small Business abandoned | Temenos |  |  | CWBSB-170 | Not started | Not started
Application delivery-Auth Signer complete | Temenos |  |  | CWBSB-169 | Not started | Not started
Application delivery-Auth Signer abandoned | Temenos |  |  | CWBSB-151 | Not started | Not started
Okta - provision new credentials | Okta | SB DCO-Infinity+Okta Provisioning-proposed 2021-04-06 |  | CWBSB-277 (Epic) CWBSB-492 CWBSB-493 CWBSB-732 | Done | WIP
Okta - authenticated path - existing personal or Motive client | Okta |  |  | CWBSB-577 | WIP | WIP
Provision online banking profiles | Temenos (Infinity) | SB DCO-Infinity+Okta Provisioning-proposed 2021-04-06 |  | CWBSB-579 CWBSB-582 | Done | WIP

## Temenos components
Small Business DCO checklist - Temenos components
Component | Requirements/Specs document | Jira story | Digital team review | Temenos review | Notes / other work required
Journey Flow updates | SB DCO Journey Flow |  | WIP | WIP | See working doc (Visio) JF updates for Nov restart
Email Specification | CWB Small Business DCO Email Specification v1.3 | CWBSB-5 (Epic) | Done | Done
Email-Application Approval | Email spec 3.1 | CWBSB-138 | WIP | WIP
Email-Pending Review (business) | Email spec 3.2 | CWBSB-516 | Done | Done
Email-Pending Review (Applicant) | Email spec 3.2a | CWBSB-136 | Done | Done
Email-Pending Review (Auth Signer) | Email spec 3.2a | CWBSB-517 | Done | Done
Email-Review Complete | Email spec 3.3 | CWBSB-137 | Done | Done
Email-Declined | Email spec 3.4 | CWBSB-505 | Done | Done
Email-Saved Application | Email spec 3.5 | CWBSB-134 | Done | Done
Email-Withdrawn Application | Email spec 3.6 | CWBSB-135 | Done | Done
Email-Nurture (Applicant) | Email spec 3.7 | CWBSB-157 | Done | Done
Email-Nurture (Auth Signer) | Email spec 3.7 | CWBSB-278 | Done | Done
Email-Manual IDV Instructions | Email spec 3.8 | CWBSB-258 | Done | Done
Email-Auth Signer Invitation | Email spec 3.9 | CWBSB-139 | Done | Done
Email-Application Complete | Email spec 3.10 | CWBSB-158 | WIP | WIP
Email-Concurrent Application | Email spec 3.11 | CWBSB-259 | Done | Done | Add Concurrent App check to JF - after More About Your Business
Email-Await Auth Signers | Email spec 3.12 | CWBSB-260 | Done | Done
Email-Auth Signers Complete | Email spec 3.13 | CWBSB-261 | Done | Done
Email-Complementary Products | Email spec 3.14 | CWBSB-262 | Done | Done
Email-Complementary Products-INTERNAL follow-up | Email spec 3.15 | CWBSB-434 | Done | Done
Email-Non-qualified Business-INTERNAL follow-up | Email spec 3.16 | CWBSB-613 | Done | Done
Email-Auth Signers Online Access/Debit Card |  |  | Deprecated
Sender address for system generated email |  | CWBSB-160 | Done | Done
Business decisioning engine rules | Small Business DCO Decision Logic v1.4 2021-03-30 | CWBSB-47 (Epic) | Done | Done
Decisioning-non-happy path | See above | CWBSB-149 | Done | WIP
Decisioning-happy path | See above | CWBSB-408 | Done | WIP
Cancel/abandon/save/resume form logic | Small Business DCO User Initiated Form Behaviour v1.0 2021-02-05 | CWBSB-268 | WIP | WIP
Workspaces |  | CWBSB-81 (Epic) | WIP | WIP
Workspaces-update for SB DCO | SB DCO Business data elements for Workspaces 2021-03-08 | CWBSB-83 CWBSB-290 | Done | WIP | Need to include config for comparison of Business Search data - see also Integration tab
Workspaces-update for Auth Signers |  | CWBSB-150 | Deprecated |  | Not required - no decisioning in Auth Signer form
Product specification-business accounts | CWB Business Accounts Product Specification v1.0 WIP | CWBSB-432 | WIP | WIP
Product specification-complementary (cash mgmt) products | CWB Cash Management Product Specification v1.0 WIP | CWBSB-433 | WIP | WIP
Product catalogue field matrix-business accounts | Product Catalogue Field Matrix Business Accounts v1.0 WIP | CWBSB-87 (Epic) | Done | WIP
Product catalogue field matrix-complementary (cash mgmt) products | Product Catalogue Field Matrix Cash Management Products v1.0 WIP | CWBSB-87 (Epic) | Done | WIP
Product catalogue integration |  | CWBSB-154 | Done | WIP | Placeholder story
Template and styling | With UX | CWBSB-3 (Epic) | WIP | WIP
Template-implement for SB | With UX | CWBSB-91 | WIP | WIP
Template-update | With UX | CWBSB-187 | WIP | WIP
Insights and analytics |  | CWBSB-88 (Epic) | WIP | WIP
Insights-configure for SB form |  | CWBSB-82 | WIP | WIP
Insights-configure for Auth Signer form |  | CWBSB-161 | WIP | WIP

## SB DCO In Branch
Small Business DCO checklist - Small Business In Branch form
Current spec
WIP spec
Journey Flow page | Base field spec | Jira story | Base wireframe | Digital team review | Final wireframe | Development approved | Wording review (CS) | Final approval (CM/SS) | In sprint | Notes / other work required
1. Landing Page (new) | Not started | [8 empty] | New page, possibly based on Personal In Branch
6. About Your Business-Codat | Not started
7. Log into Codat | Not started
8. Your Business | Not started
9. More About Your Business | Not started
Supporting Documents (new) | Not started | [8 empty] | Net new page - deal with physical supporting docs
17. Authorized Signers | Not started
Business Search Results/Compare (new) | Not started | [8 empty] | Net new page - review COVR / compare with provided info
3. Applicant-Contact Info | Not started
11. Applicant-Name & Address | Not started
12. Applicant-Birthday, SIN & Occupation | Not started
In Branch Customer Info-Applicant (new) | Not started | [8 empty] | New page, assume based on Personal In Branch
Credit Bureau results-Applicant (new) | Not started | [8 empty] | New page, assume based on Personal In Branch
Save Application+Email Auth Signers (new) | Not started
20. Account Options | Not started
21. Complementary Products | Not started
Finish+Notifications page (new) | Not started | [8 empty] | New page, assume based on Personal In Branch
A. Generic Error | Not started
F. Resume | Not started

## Auth Signer In Branch
Small Business DCO checklist - In Branch Auth Signer form
Current spec
WIP spec
Journey Flow page | Base field spec | Jira story | Base wireframe | Digital team review | Final wireframe | Development approved | Wording review (CS) | Final approval (CM/SS) | In sprint | Notes / other work required
1. Entry page | Not started
2. Landing Page | Not started
4. Contact Info | Not started
7. Name & Address | Not started
8. Birthday, SIN & Occupation | Not started
In Branch Customer Info (new) | Not started | [8 empty] | New page, assume based on Personal In Branch
A. Generic Error | Not started
B. Manual Review | Not started
E. Save | Not started
F. Resume | Not started
G. Time Out | Not started
H. Progress | Not started
J. Concurrent App | Not started