## Sheet1
13 | Light Blue Shaded Items : | Test Motive NTB as part M2 Opreation Release, and then test Motive Authenticated as part of Motive Compatility Project.
12 | Light Grey Shaded Items: | OKTA related - cannot be fixed by JM- DCO - (Either Cancelled or will be reviewed after OIE Upgrade)
# | Channel | Users | Number and description of issue on the audit list | DCO Ticket
1 | All Channels | NTB and Authenticated | 1. Timeout extension | DCO-2417
2 | All Channels | Authenticated | 2. Authenticated Signers Password must be actioned using keyboard | DCO-2418
3 | All Channels | Authenticated | 3. Authenticated Signers Show Password fields Contrast Issues | DCO-2419
4 | All Channels | NTB and Authenticated | 4. Heading Order | DCO-2420
5 | All Channels | NTB and Authenticated | 5. Items with Insufficient contrast | DCO-2421
6 | All Channels | NTB and Authenticated | 6. Application in "Waiting State" Notification | DCO-2422
7 | All Channels | NTB and Authenticated | 7. Progress Bar feeback from Screen Reader users | DCO-2423
8 | Motive | NTB and Authenticated | 8. Replace WAI-ARIA instead of alert in footer link | DCO-2424
9 | Motive | NTB and Authenticated | 9. Anchor “cdic sadc” contains nested actionable controls | DCO-2425
10 | Motive | NTB and Authenticated | 10. Page lacks h1 heading | DCO-2426
11 | Motive | NTB and Authenticated | 11. Heading not part of heading order | DCO-2427
12 | Motive | NTB and Authenticated | 12. "More Options" control fails must present visible focus | DCO-2428
13 | Motive | NTB and Authenticated | 13. Radio Button must provide a visible focus indicator | DCO-2429
14 | Motive | NTB and Authenticated | 14. “More options” control exists within a <div> with an invalid WAI-ARIA attribute | DCO-2430
15 | Motive | NTB and Authenticated | 15. Significance of Astrick | DCO-2431
16 | Motive | NTB and Authenticated | 16. Questions exist within a <fieldset> with a role="radiogroup" | DCO-2432
17 | Motive | NTB | 17. Text Added manually to focus order of the page | DCO-2433
18 | Motive | NTB | 18. "Additional Information" control must present a visible focus | DCO-2434
19 | Motive | NTB | 19. Input fields lack proper input identification | DCO-2435
20 | Motive | NTB | 20. “Motive Savvy Savings Account” control | DCO-2436
21 | Motive | NTB | 21. "No, go back" control must present a visible focus | DCO-2437
22 | Motive | NTB | 22. List items must be programmatically implemented as a list | DCO-2438
23 | Motive | NTB | 23. Example Image encapsulated within attributes causing content to be ignored | DCO-2439
24 | Motive | NTB | 24. Input fields lack proper input identification | DCO-2440
25 | Motive | NTB | 25. "Select a province" dropdown must present a visible focus indicator | DCO-2441
26 | Motive | NTB | 26. Next control after postal code field | DCO-2442
27 | Motive | NTB and Authenticated | 27. "Waiting State" feedback | DCO-2443
28 | Motive | NTB | 28. Confirmation message contrast | DCO-2444
29 | Motive | NTB | 29. Email contrast issues | DCO-2445
30 | Motive | NTB and Authenticated | 30. Display Name in email | DCO-2446
31 | Motive | Authenticated | 31. Activation Screen Landing page contains multiple h1 headings | DCO-2447
32 | Motive | Authenticated | 32. Activate new customer Blue anchor text insufficient contrast | DCO-2448
33 | Motive | Authenticated | 33. Infinity Forgot Password and Add Phone number control fail to present visible focus | DCO-2449
34 | Motive | Authenticated | 34. Authenticated Customer "Add Phone Number" lacks sufficient contrast | DCO-2450
35 | Motive | Authenticated | 35. Fields lack with proper input identification | DCO-2451
36 | Motive | Authenticated | 36. Authenticated signers "New Password" field requirements | DCO-2453
37 | Motive | Authenticated | 37. Authenticated Signer Activation Multi factor authentication | DCO-2454
38 | Motive | Authenticated | 38. Authenticated Signers Functional accessibility issues with "Next/Call" controls | DCO-2455
39 | Motive | Authenticated | 39. Authenticated Customer login "Username" Label | DCO-2456
40 | Motive | Authenticated | 40. Dropdowns on the form fail to present a visible focus indicator | DCO-2457
41 | Motive | Authenticated | 41. Authenticated customer close action popup model lacking associated label | DCO-2458
42 | Motive | Authenticated | 42. Close control modal fails to present visible focus indicator | DCO-2459
43 | Motive | Authenticated | 43. log in screen | DCO-2460
44 | Motive | Authenticated | 44. Functional Accessibility issue in security question | DCO-2461
45 | Personal | NTB and Authenticated | 45. All page must have h1 heading | DCO-2462
46 | Personal | NTB and Authenticated | 46. Page shares Identical page titles | DCO-2463
47 | Personal | NTB and Authenticated | 47. "More Options" modal contains fails to present a visible focus | DCO-2464
48 | Personal | NTB and Authenticated | 48. "Two Factor authentication" message to new Screen reader users | DCO-2465
49 | Personal | NTB | 49. Account Options appear radiobutton instead of checkbox | DCO-2466
50 | Personal | NTB and Authenticated | 50. "More Information" icon contrast issues | DCO-2467
51 | Personal | NTB and Authenticated | 51. Authenticated Signers applying for GIC - "Interest Rate" anchor lacks contrast | DCO-2468
52 | Personal | NTB | 52. "Interest Rate" anchor fails to present an underline | DCO-2469
53 | Personal | NTB and Authenticated | 53. Email address anchor lacks contrast | DCO-2470
54 | Business | NTB and Authenticated | 54. Emails delivered with a "from" line fails to mention the product | DCO-2471
55 | Business | NTB and Authenticated | 55. Anchor lack visible focus | DCO-2472
56 | Business | NTB | 56. Expandable content regions cannot be actioned using keyboard | DCO-2473
57 | Business | NTB | 57. Expandable content control fail to indicate current state | DCO-2474
58 | Business | NTB and Authenticated | 58. Page Sharing identical page title | DCO-2475
59 | Business | NTB and Authenticated | 59. "With your permission" checkbox is part of radio button label | DCO-2476
60 | Business | NTB and Authenticated | 60. "Close" button on "More Options" fails to get visible focus indicator | DCO-2477
61 | Business | NTB | 61. Account Type control uses checkbox but visible as radio button | DCO-2478
62 | Business | NTB | 62. "Let's Get Started" contains h5 heading rather than h1 | DCO-2479
63 | Business | NTB | 63. "Let's get started" page fieldset - announce issue to screen recorder | DCO-2480
64 | Business | NTB | 64. Quantity control increase and decrease - No announcement to screen readers | DCO-2481
65 | Business | NTB | 65. "Pre-fill your business information" contains radio buttons with no labels | DCO-2482
66 | Business | NTB | 66. “Legal entity name / Business number / Corporate Access Number etc” text lacks sufficient contrast | DCO-2483
67 | Business | NTB | 67. “About your business” contains a multitude of inconsistent heading levels | DCO-2484
68 | Business | NTB | 68. With your permission" checkbox include the bulleted points as part of the radio button label | DCO-2485
69 | Business | NTB | 69. “About your Associates” visual list of items not implemented programmatically as a list | DCO-2486
70 | Business | NTB | 70. “Role(s)” grouping fails to indicate set of controls | DCO-2487
71 | Business | NTB | 71. “Role” option “Director” UI contrast issues | DCO-2488
72 | Business | NTB | 72. PDF file “CWBCashManagementOnlineServicesAgreement.pdf” fails to conform with accessibility standards | DCO-2489
73 | Business | NTB | 73. “Let’s get started” page for joint account holder contains visual list that is not programmatically implemented | DCO-2490
74 | Business | NTB | 74. “Your associates will join us soon” page contains series of anchors | DCO-2491
75 | Business | NTB | 75. "About your account" screen | DCO-2492
76 | Business | NTB | 76. Incorrect Error not visible to screen reader users | DCO-2493
77 | Business | Authenticated | 77. Authenticated customer login Username contrast issues | DCO-2494