## Sheet1
Channel | Number and description of issue on the audit list | DCO Ticket | Assigned to | Status of the ticket
All Channels | 1. Timeout extension | DCO-2417 | Accutive | To-do
All Channels | 2. Authenticated Signers Password must be actioned using keyboard | DCO-2418 | Fusi Olateru | External Review | Okta focus
All Channels | 3. Authenticated Signers Show Password fields Contrast Issues | DCO-2419 | Fusi Olateru | External Review | Okta contrast
All Channels | 4. Heading Order | DCO-2420 | Accutive | To-do
All Channels | 5. Items with Insufficient contrast | DCO-2421 | Ian Hicks | External Review | Contrast
All Channels | 6. Application in "Waiting State" Notification | DCO-2422 | Accutive | To-do
All Channels | 7. Progress Bar feeback from Screen Reader users | DCO-2423 | Accutive | To-do
Motive | 8. Replace WAI-ARIA instead of alert in footer link | DCO-2424 | Accutive | To-do
Motive | 9. Anchor “cdic sadc” contains nested actionable controls | DCO-2425 | Accutive | To-do
Motive | 10. Page lacks h1 heading | DCO-2426 | Accutive | To-do
Motive | 11. Heading not part of heading order | DCO-2427 | Accutive | To-do
Motive | 12. "More Options" control fails must present visible focus | DCO-2428 | Ian Hicks | External Review | Focus
Motive | 13. Radio Button must provide a visible focus indicator | DCO-2429 | Ian Hicks | External Review | Focus
Motive | 14. “More options” control exists within a <div> with an invalid WAI-ARIA attribute | DCO-2430 | Accutive | To-do
Motive | 15. Significance of Astrick | DCO-2431 | Ian Hicks | External Review | Mandatory field - message or ??
Motive | 16. Questions exist within a <fieldset> with a role="radiogroup" | DCO-2432 | Accutive | To-do
Motive | 17. Text Added manually to focus order of the page | DCO-2433 | Accutive | To-do
Motive | 18. "Additional Information" control must present a visible focus | DCO-2434 | Ian Hicks | External Review | Focus
Motive | 19. Input fields lack proper input identification | DCO-2435 | Accutive | To-do
Motive | 20. “Motive Savvy Savings Account” control | DCO-2436 | Ian Hicks | External Review | Check box styled as radio button
Motive | 21. "No, go back" control must present a visible focus | DCO-2437 | Accutive | To-do
Motive | 22. List items must be programmatically implemented as a list | DCO-2438 | Accutive | To-do
Motive | 23. Example Image encapsulated within attributes causing content to be ignored | DCO-2439 | Accutive | To-do
Motive | 24. Input fields lack proper input identification | DCO-2440 | Accutive | To-do
Motive | 25. "Select a province" dropdown must present a visible focus indicator | DCO-2441 | Accutive | To-do
Motive | 26. Next control after postal code field | DCO-2442 | Accutive | To-do
Motive | 27. "Waiting State" feedback | DCO-2443 | Accutive | To-do
Motive | 28. Confirmation message contrast | DCO-2444 | Ian Hicks | External Review | Contrast
Motive | 29. Email contrast issues | DCO-2445 | Ian Hicks | External Review | Emails contrast
Motive | 30. Display Name in email | DCO-2446 | Ian Hicks | External Review | Email addressing
Motive | 31. Activation Screen Landing page contains multiple h1 headings | DCO-2447 | Fusi Olateru | External Review | Okta
Motive | 32. Activate new customer Blue anchor text insufficient contrast | DCO-2448 |  | Cancelled | INVALID - this is only in sandbox site, will not be visible in production
Motive | 33. Infinity Forgot Password and Add Phone number control fail to present visible focus | DCO-2449 | Fusi Olateru | External Review | Okta focus
Motive | 34. Authenticated Customer "Add Phone Number" lacks sufficient contrast | DCO-2450 | Fusi Olateru | External Review | Okta contrast
Motive | 35. Fields lack with proper input identification | DCO-2451 | Sanya Khandhuja | To-do
Motive | 36. Authenticated signers "New Password" field requirements | DCO-2453 | Fusi Olateru | External Review | Okta
Motive | 37. Authenticated Signer Activation Multi factor authentication | DCO-2454 | Fusi Olateru | External Review | Okta
Motive | 38. Authenticated Signers Functional accessibility issues with "Next/Call" controls | DCO-2455 | Sanya Khandhuja | To-do
Motive | 39. Authenticated Customer login "Username" Label | DCO-2456 | Fusi Olateru | External Review | Okta contrast
Motive | 40. Dropdowns on the form fail to present a visible focus indicator | DCO-2457 | Accutive | To-do
Motive | 41. Authenticated customer close action popup model lacking associated label | DCO-2458 | Accutive | To-do
Motive | 42. Close control modal fails to present visible focus indicator | DCO-2459 | Accutive | To-do
Motive | 43. log in screen | DCO-2460 | Fusi Olateru | External Review | Okta
Motive | 44. Functional Accessibility issue in security question | DCO-2461 | Fusi Olateru | External Review | Okta contrast
Personal | 45. All page must have h1 heading | DCO-2462 | Accutive | To-do
Personal | 46. Page shares Identical page titles | DCO-2463 | Sanya Khandhuja | To-do
Personal | 47. "More Options" modal contains fails to present a visible focus | DCO-2464 | Ian Hicks | External Review | Focus
Personal | 48. "Two Factor authentication" message to new Screen reader users | DCO-2465 | Accutive | To-do
Personal | 49. Account Options appear radiobutton instead of checkbox | DCO-2466 | Ian Hicks | External Review | Check box styled as radio button
Personal | 50. "More Information" icon contrast issues | DCO-2467 | Ian Hicks | External Review | Contrast
Personal | 51. Authenticated Signers applying for GIC - "Interest Rate" anchor lacks contrast | DCO-2468 | Ian Hicks | External Review | Contrast
Personal | 52. "Interest Rate" anchor fails to present an underline | DCO-2469 | Accutive | To-do
Personal | 53. Email address anchor lacks contrast | DCO-2470 | Ian Hicks | External Review | Contrast
Business | 54. Emails delivered with a "from" line fails to mention the product | DCO-2471 | Ian Hicks | External Review | Email addressing
Business | 55. Anchor lack visible focus | DCO-2472 | Accutive | To-do
Business | 56. Expandable content regions cannot be actioned using keyboard | DCO-2473 | Accutive | To-do
Business | 57. Expandable content control fail to indicate current state | DCO-2474 | Accutive | To-do
Business | 58. Page Sharing identical page title | DCO-2475 | Accutive | To-do
Business | 59. "With your permission" checkbox is part of radio button label | DCO-2476 | Accutive | To-do
Business | 60. "Close" button on "More Options" fails to get visible focus indicator | DCO-2477 | Ian Hicks | External Review | Focus
Business | 61. Account Type control uses checkbox but visible as radio button | DCO-2478 | Ian Hicks | External Review | Check box styled as radio button
Business | 62. "Let's Get Started" contains h5 heading rather than h1 | DCO-2479 | Accutive | To-do
Business | 63. "Let's get started" page fieldset - announce issue to screen recorder | DCO-2480 | Accutive | To-do
Business | 64. Quantity control increase and decrease - No announcement to screen readers | DCO-2481 | Accutive | To-do
Business | 65. "Pre-fill your business information" contains radio buttons with no labels | DCO-2482 | Sanya Khandhuja | To-do
Business | 66. “Legal entity name / Business number / Corporate Access Number etc” text lacks sufficient contrast | DCO-2483 | Ian Hicks | External Review | Contrast
Business | 67. “About your business” contains a multitude of inconsistent heading levels | DCO-2484 | Accutive | To-do
Business | 68. With your permission" checkbox include the bulleted points as part of the radio button label | DCO-2485 | Accutive | To-do
Business | 69. “About your Associates” visual list of items not implemented programmatically as a list | DCO-2486 | Accutive | To-do
Business | 70. “Role(s)” grouping fails to indicate set of controls | DCO-2487 | Accutive | To-do
Business | 71. “Role” option “Director” UI contrast issues | DCO-2488 | Ian Hicks | External Review | Contrast
Business | 72. PDF file “CWBCashManagementOnlineServicesAgreement.pdf” fails to conform with accessibility standards | DCO-2489 | Ian Hicks | External Review | Non-accessible PDF
Business | 73. “Let’s get started” page for joint account holder contains visual list that is not programmatically implemented | DCO-2490 | Accutive | To-do
Business | 74. “Your associates will join us soon” page contains series of anchors | DCO-2491 | Accutive | To-do
Business | 75. "About your account" screen | DCO-2492 | Accutive | To-do
Business | 76. Incorrect Error not visible to screen reader users | DCO-2493 | Accutive | To-do
Business | 77. Authenticated customer login Username contrast issues | DCO-2494 | Fusi Olateru | External Review | Okta contrast
Business | 78. "Revolving Line of Credit" contains bulleted list items in unordered list | DCO-2495 | Accutive | To-do