## Projects
Initiative | Key Team members | State | Tasks to do
VCOO | Business: Edmund Architecture: Jose Sec Architecture: Joanne P Infra: Andrew P Tech Lead: Mark D Program: Alvin, Dilshad | - Development and project management was outsourced to Deloitte by Temenos - Deloitte team has rolled off the project and we have no visibility of the new development team and where they stand - Dev Complete - but haven't seen the working version yet - QA - Lined up for functional testing and working on test scripts - Performance QA- lined up and working on test scripts - Penetration QA - Joanne K working with a vendor - Look at the plan excel sheet to see all the activities pending - Shakedown plan for post Beta is already shared with Program team | - Help all QA teams with the knowledge they need for there testing - Get the environments going to end-to-end testing can be done - Help dev team to perform end to end testing once the environments are available - Transition to operations for initial launch - More phases to follow after initial launch. Expected engagement for an additional 8-12 months from now (July 21).
XAI Dashboard | Business: Edmund Architecture: OLB architect(Prakhar) Infra: Andrew P Program: Nadeem, Dilshad | Story review in progress. | - Dev to be started - QA and rest of the steps to follow. - No need for separate transition to operations as this is part of OLB
Fraud | Vendor: Navaera (Rotter, Luke (US) <lrotter@navaera.com>) Architecture: Prakhar Mulesoft Dev: Pavan Reddy Program: Alvin | - The original scope was to offer like-for-like replacement of FAS(C1's Fraud solution) - Dev complete at Temenos, Navaera and CWB end, - Environment ready, - QA and Business training completed by the vendor, - QA is working on the test cases | - Navaera to finish configuring the rules for CWB by 9th July - QA will commence on the 12th July - UAT by the business will be done between 19th and 23rd
Chatbot | Vendor: Ficanex(Colleen Morrow) Business: Adam S Marketing: Samantha Russel Program: Dino Sitecore Dev: Mythi Lam, Ashish Sabharawal | - All development done by the vendor. We have only inserted a script within our websites(public) to provide the chatbot. - The bot is available on both web and mobile web and not on the mobile app and is focused more towards the business clients - The testing was done by Adam, Me and Samantha- so no involvement of QA | - There is a need to capture the complete details of the flow as the final flow documents we have were not updated to reflect the customizations we did during the project - Phase 2 will include offering financial transactions to the customers and might also extend to incldue retail and commercial customers

## Documents List
Initiative | Document Name | Description | URL
VCOO | XAI Model Features - Codat Feedback | The document list all the datapoints also known as features that are being used by the data models being produced by XAI
VCOO | Healthscore Calculation Proposed v4.3 | This document list the current and future expecations of the healthscore model. The healthscore model today is not based on self learning so the document was created to share expert rules to train that model.
VCOO | Insights Directory v0.2 | This document list all the insights about financial data that can be produced by VCOO.
VCOO | Codat Categorisation 11 June (version 1) | CODAT has an upcoming feature called Categorization that will allow CODAT to share more granular data with us. This document contain all the data points that are available through CODAT, with an emphasis on whether or not they are available without Categorization support on CODAT.
VCOO | Enrollment & Funding for VCOO | This document was created to capture our business requirements for enrollment and funding flows and share that understanding with Temenos and Deloitte.
VCOO | Funding Flow | This document was created to capture the screen design requirement to explain to the Temenos team
VCOO | Automation Scenarios | Automation is a next phase feature. This document captures possible scenarios we can automate
VCOO | Strategic indicators & Measures for growth | A brainstorming doc created by Temenos to capture business goals (future scope)
VCOO | XAI vs VCOO | A high level plan of XAI and VCOO rollout plan
VCOO | XAI Business Requirements | An itemized list of requirements for VCOO. Not being followed
VCOO | Architecture | All the architecture artifacts are captured in this folder. Most of these were prepared by Temenos
VCOO | Plan | The folder contains high level plans. 1 created by me and the other by Temenos
VCOO | Solution Documents from Temenos | Solution documents for all the data models available within XAI
VCOO | XAI Cash Flow Feature in DBX BRD | BRD draft created by Hoa. Not applicable anymore
XAI Dashboard | Data Mapping XAI Account Dashboard v1 MT | A document created by the tech team to capture the API end points that can help develop the XAI dashboards
XAI Dashboard | [17th Sept] TemenosInfinity_CWB_Accounting Dashboard
XAI Dashboard | XAI for Cash Flow - Internal Kickoff
XAI Dashboard | XAI Dashboard- Use Cases Anchor Doc
XAI Dashboard | XAI Cash Flow Feature in DBX BRD
XAI Dashboard | High-level Digital Project Use Cases for TDL-XAI-Analytics Platform