## CWB Deployment Plan VCOO
[7 empty] | Display Week: | 1 |  |  |  |  | -5 | [6 empty] | 1900-01-01 | [6 empty] | 1900-01-08 | [6 empty] | 1900-01-15 | [6 empty] | 1900-01-22 | [6 empty] | 1900-01-29 | [6 empty] | 1900-02-05 | [6 empty] | 1900-02-12 | [6 empty] | 1900-02-19 | [6 empty] | 1900-02-26 | [6 empty] | 1900-03-05 | [6 empty] | 1900-03-12 | [6 empty] | 1900-03-19
[13 empty] | -5 | -4 | -3 | -2 | -1 | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23 | 1900-03-24 | 1900-03-25
Task ID | TASK | Scheduled START | Scheduled END | Status | ASSIGNED/CONFIRMATION GROUP | PROGRESS (%) | Duration (H or M) | Scheduled START | Scheduled END | Estimated/Actual START | Estimated/Actual END | DAYS | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
CWB
SMTP Services
SMTP.1 | Confirm exception to allow SMTP traffic outside of CWB network - currently limited to cwbank.com emails. | 2022-07-22 | 2022-07-22 | Completed | Adam / Stacy
SMTP.2 | Confirm email address proxy for all outgoing emails from Infinity. E.g. no-reply.cwb.digital@cwbank.com | 2022-07-22 | 2022-07-22 | Completed | Adam / Stacy
SMTP.3 | Send email address proxy to Temenos for inclusion in the runbook | 2022-07-22 | 2022-07-22 | Completed | Andrew / Alvin
SMTP.4 | Provide confirmation to CWB Infrastructure (Ryan Mah) to update the SMTP traffic rule in production | 2022-07-22 | 2022-07-22 | Completed | Andrew / Alvin
SMTP.5 | Implement SMTP rule change in production (update email to approved value) | 2022-07-28 | 2022-07-28 | Pending | Ryan Mah/Vijay
SMTP.6 | Smoketest SMTP Services | 2022-07-28 | 2022-07-28 | Pending | Temenos | [98 empty] | send test email
T24
T24.1 | Identify R1.1 T24 code dependencies prior to launch | 2022-06-30 | 2022-06-30 | Completed | Charlotte
T24.2 | Deploy R1.0 to OPSIT2 for Pre-Production Regression Testing | 2022-07-11 | 2022-07-11 | Completed | Sundhar
T24.3 | Deploy T24 code to OPSIT2 for Pre-Production Regression Testing (R1.1) | 2022-07-03 | 2022-07-03 | Completed | Charlotte
T24.4 | Pre-Production Regression Testing | 2022-07-12 | 2022-07-13 | Completed | Operational QA (Trisha)
T24.5 | Pre-Production Regression Defect Fixes and Re-test (if applicable) | 2022-07-14 | 2022-07-15 | Completed | Charlotte/Trisha
T24.6 | T24 Production Deployment | 2022-07-17 | 2022-07-17 | Completed | RM (Release Management)
T24.7 | 2 defects remaining for T24 only | 2022-07-28 | 2022-07-28 | Pending | RM (Release Management)
Data Migration
DM.1 | Confirm signoff for C1 CR - submittance. (Profile E impact - early November) - may need to include in VCOO/FF release |  |  | In Progress | Dapo / Braydon |  | 0
DM.1 | Deploy final DM process code to production - updating ETL code in PROD | 2022-07-19 | 2022-07-19 | Completed | Dapo / Henry |  | 0
DM.2 | [Not required] Reset password hook on dedicated C1 production test account to specifically test password hook APIs | 2022-07-20 | 2022-07-20 | Pending | Tony
DM.3 | Test Password hook API | 2022-07-23 | 2022-07-23 | Pending | Adam
DM.4 | [Not required until after go-live] Infinity to validate connection to DM load tables | 2022-07-23 | 2022-07-23 | Pending | Vijaya/Satish
Third-Party Applications
Celero
CEL.1 | No deployments required for R1.1 |  |  | Completed | Mark D |  | 0
Central1 - CRA Deployment
C1.1 | QA signoff of CRA API | 2022-07-15 | 2022-07-15 | Completed | Adrian
C1.2 | Notify C1 to stand-up API from non-prod env to prod | 2022-07-15 | 2022-07-15 | Completed | Mark D
C1.3 | Stand-up Mule API into Prod - requires CR approval | 2022-07-19 | 2022-07-19 | Completed | Mark D / Alex / CAB
C1.4 | Confirm CRA API connectivity CWB & C1 | 2022-07-22 | 2022-07-22 | Completed | CWB and C1
OKTA
OK.1 | Confirm tasks with Tony regarding outstanding actions for pre-prod/prod |  |  |  | Tony Fang / Andrew | 100% | 0 | 2021-11-01 | 2021-11-01
OK.2 | Provide change details to the CWB IAM Team (IAM = Identity Access Management) |  |  |  | Tony Fang |  | 0.5 | 2021-11-02 | 2021-11-02
OK.3 | Create and submit Change Requests for Okta production |  |  |  | CWB IAM Team |  | 0.5 | 2021-11-03 | 2021-11-03
OK.4 | Approve CRs for change |  |  |  | Thomas Matthew |  | 0.5 | 2021-11-04 | 2021-11-04
OK.5 | Complete production deployment for Okta (Date to align once new go-live has been established) |  |  |  | Tony Fang/Rajiv Sharma |  | 0.5
OK.6 | CR#1: Update Sign In Page to 5.latest SIW Version, Configure Headings/Labels/Customized Help Links |  |  | Completed | Tony Fang/Rajiv Sharma
OK.7 | CR#1: Enable Global Default Redirect EA Feature, Configure Default app for Okta SIW to https://www.cwb.digital/apps/cwbDigital/ |  |  | Completed | Tony Fang/Rajiv Sharma
OK.8 | CR#1: Add Sentry Groups for Spotlight, Add CIAM Okta group rule for Spotlight, Assign Spotlight Group to Spotlight app |  |  | Completed | Tony Fang/Rajiv Sharma
OK.9 | CR#1: Add claims (location, city, first_name, street_Address, province, last_name, country_code) to CWB Digital Authorization Server |  |  | Completed | Tony Fang/Rajiv Sharma
OK.10 | CR#2: Update custom sign in to enable credential recovery for Infinity Mobile (Must go with R1.1) | 2022-07-23 | 2022-07-23 | Completed | Mohammed |  | 0.5 | 2021-12-11 | 2021-12-11
OK.11 | Update redirect URI in OKTA | 2022-07-23 | 2022-07-23 | Completed | Tony Fang/Mohammed
OK.12 | Approve CR #2 | 2022-07-26 | 2022-07-26 | Completed | Thomas Matthew
OK.13 | Implement CR #2 | 2022-07-28 | 2022-07-28 | Pending | Tony Fang/Mohammed
BRIM
BR.1 | Provide Okta setting for production (client_id, secret, metadata URL) |  |  | Completed | Tony Fang | 100%
| Copy files and integrate with production APIs - | 2022-07-14 | 2022-07-18 | Pending | Fayez Alameddine
| Shakedown testing with BRIM - web portal, transactions, receiving emails |  |  | Pending | Adam
BR.2 | Provide BRIM redirect URLs to Okta (pre-production confirmation) |  |  | In Progress | Fayez Alameddine
| Infinity: Confirm BRIM Prod SSO Link | 2022-07-21 | 2022-07-22
| Infinity: MasterCard Link for Prod | 2022-07-21 | 2022-07-22
| Infinity: Confirm the prod key is the correct one | 2022-07-21 | 2022-07-22
| CWB: 1) Brim API Key 2) Brim Hostname | 2022-07-21 | 2022-07-22 | Completed | Roney, Prakhar
BR.5 | Whitelist IPs |  |  | Completed | Fayez Alameddine
MuleSoft
MS.1 | BRIM Configurations (keys/secrets) for Prod updated in Mule Prod environment | 2022-07-21 | 2022-07-22 | Completed | Alex
MS.2 | OKTA details for Spotlight and BRIM to be confirmed | 2022-07-21 | 2022-07-22 | Completed | Tony/Alex
MS.3 | Planning to rollout out all DB R1.1 APIs and complete smoke testing. Completed Celero and Helix | 2022-07-18 | 2022-07-19 | Completed | Alex/Andy |  | 0 | 2021-12-06 | 2021-12-10
MS.4 | BiG Review and Validation to ensure correct versions are deployed | 2022-07-20 | 2022-07-22 | Completed | Andy LePage
MS.5 | Submit Mule CR for Production Deployment | 2022-07-26 | 2022-07-26 | Completed | Alex
MS.6 | Deploy DB R1.1 Mulesoft APIs to Production | 2022-07-29 | 2022-07-29 | Pending | RM
MS.7 | Configuration of app key/secrets for Alerts, DCO. Navaera from Temenos (just pending DCO) | 2022-07-29 | 2022-07-29 | Pending | Alex
CloudFlare
CF.1 | No deployments required for R1.1 |  |  | Confirmed | Mark D |  | 0
CF.2 | Confirmation for outage pages and messaging - HotFix update will be required to remove 1 outage page | 2022-07-15 | 2022-07-15 | Completed | Paul Sarna | 50%
CF.3 | Sign-off for outage pages | 2022-07-18 | 2022-07-18 | Completed | Trish/Adam/Stacy
CF.4 | Submit ticket for outage page window | 2022-07-26 | 2022-07-26 | Completed | Andrew
CF.5 | Activate Outage Page | 2022-07-28 22:30 | 2022-07-29 05:30 | Pending | Kris Aloisio
CF.6 | De-activate Outage Page for CWB OLB Testing | 2022-07-29 05:30 | 2022-07-29 06:30 | Pending | Kris Aloisio
CF.7 | Activate Outage Page | 2022-07-29 06:30 | 2022-07-29 08:30 | Pending | Kris Aloisio
CF.8 | De-activate Outage Page for CWB MB Testing | 2022-07-29 08:30 | 2022-07-29 09:30 | Pending | Kris Aloisio
Navaera
NV.1 | No deployments required for R1.1 |  |  | Confirmed | Alex |  | 0
CRA Direct Deposit (need review/updating)
CRA.1 | Ensure production database updates have been propagated (CRA DD Database Availability Group) |  |  | Completed | Dave Barrett/Brian Coghlan |  | 0
CRA.2 | Confirm firewall routing for Azure (DB is located here) | 2022-07-14 | 2022-07-14 | Completed | Dave Barrett/Braydon |  | 0
CRA.3 | QA signoff on CRA direct deposit | 2022-07-15 | 2022-07-15 | Completed | Adrian & Carmela
CRA.4 | Notify CRA of Go-Live (endpoint confirmed. Production files to be sent) | 2022-07-15 | 2022-07-15 | Completed | Mark D
Helix
HEL.1 | No deployments required for R1.1 |  |  | Confirmed | Alex |  | 0
Mobile App
MB.1 | Confirm backwards-compatability - R1.0 app still works with R1.1 code - Not backwards compatible | 2022-07-15 | 2022-07-15 | Completed | QA Team
MB.2 | Confirm QA sign-off of Android Production Build | 2022-07-29 | 2022-07-29 | Pending | QA Team
MB.3 | Confirm QA sign-off of iOS Production Build - confirm it's built with most up-to-date XCODE | 2022-07-29 | 2022-07-29 | Pending | QA Team
MB.4 | Confirm UX artifacts for app deployment (Android) - icons/release text/screenshots/video | 2022-07-26 | 2022-07-26 | Completed | UX Team
MB.5 | Confirm UX artifacts for app deployment (iOS) - icons/release text/screenshots/video | 2022-07-26 | 2022-07-26 | Completed | UX Team
MB.6 | Ensure test account is active and working in prod (T24) - already confirmed |  |  | Completed | Mark D |  | 0
MB.7 | Confirm Android developer accounts are in place - already confirmed |  |  | Completed | Mark D |  | 0
MB.8 | Confirm iOS developer accounts are in place - already confirmed |  |  | Completed | Mark D |  | 0
MB.9 | Submission to Google Play Store (1-3 days) - force upgrade | 2022-07-29 | 2022-07-29 | Pending | Mark D
MB.10 | Submission to Apple Store (1-5 days) - place message on R1.0 iOS application to force upgrade | 2022-07-29 | 2022-07-29 | Pending | Mark D
Data Extracts
DE.1 | No deployments required for R1.1 |  |  | Confirmed | DM |  | 0
Shakedown Testing
TEST.1 | CWB VCOO + Infinity Application Testing post LB Upgrade | 2022-07-27 22:00 | 2022-07-27 22:30 | Pending | Edmund/Shanny/Vivian
TEST.2 | Provide LB Upgrade Sign-Off | 2022-07-27 22:30 | 2022-07-27 22:30 | Pending | Edmund/Shanny/Vivian
TEST.3 | CWB OLB Testing | 2022-07-28 05:30 | 2022-07-28 06:30 | Pending | Adam/Edmund/Christina/CWB
TEST.4 | CWB OLB Sign-off | 2022-07-28 06:30 | 2022-07-28 06:30 | Pending | Adam/Edmund/Christina/CWB
TEST.5 | CWB MB Testing | 2022-07-28 08:30 | 2022-07-28 09:30 | Pending | Adam/Edmund/Christina/CWB
TEST.6 | CWB MB Testing Sign-off | 2022-07-28 09:30 | 2022-07-28 09:30 | Pending | Adam/Edmund/Christina/CWB
Temenos |  | 2022-07-28 | 2022-07-29
Initial Config & ISO/API Test
TEM.1 | Upgrade LB to Standard - Infinity R1.1 & INFINITY VCOO | 2022-07-28 21:00 | 2022-07-28 21:30 | Pending | Marlon/Robert
TEM.2 | Upgrade Validation INFINITY and VCOO validation | 2022-07-28 21:30 | 2022-07-28 22:00 | Pending | Vijaya/VCOO team/hosting/Rod/carlos |  |  | 1H
TEM.3 | Application Testing Validation | 2022-07-28 22:00 | 2022-07-28 22:30 |  | CWB/Temenos (VCOO/R1.1) |  |  | 0.5H
TEM.4 | Create an instance of the DB backup. Hosting to share the DB details (conn. url, username, password) | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Temenos Hosting Team |  |  | 0.5H
TEM.5 | Request analytics certificate | 2022-07-20 | 2022-07-20 | Completed | Vijaya/Pavani/Satish
TEM.6 | Request domain certificate (*.temenoscloudna.com, temenoscloudna.com) | 2022-07-21 | 2022-07-21 | Completed | Vijaya/Pavani/Satish
TEM.7 | Installing SSL Certificate for Production domain- Analytics certificate (cwb.ca.pem) | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Vijaya/Pavani/Satish
TEM.8 | Installing SSL Certificate for Production domain-(*.temenoscloudna.com, temenoscloudna.com) | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Vijaya/Pavani/Satish
TEM.9 | Need to get required url's and CONSENT_MICROSERVICE_URL, CONSENT_CODAT_URL, CONSENT_ANALYTICS_URL - Consent is Pending | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Vijaya/Pavani/Satish/Marlon/Manni |  |  | 0.5H
TEM.10 | Analytics Microservice Setup | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Vijaya/Pavani/Satish
TEM.11 | Receiving Microservices details from Hosting/cloud team | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending
TEM.12 | Dashboard - Connection MicroService deployment | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Pavani/Gowthami
TEM.13 | Dashboard - Fabric configuration for the Consent API URL and auth details | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Pavani/Gowthami
TEM.14 | Dashboard - Fabric XAI URLs and auth details | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Pavani/Gowthami
TEM.15 | Dashboard - Fabric Codat URLs and auth details | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Pavani/Gowthami
TEM.16 | Dashboard - Consent Timeout environment variable in Fabric | 2022-07-28 22:30 | 2022-07-28 23:30 | Pending | Pavani/Gowthami |  |  | 0.5H
TEM.17 | Share the Production domain details with Okta | 2022-07-23 | 2022-07-23 | Completed | Pavani/Vijaya |  |  | 6H
TEM.18 | Get -OLB & MB - Okta Config update to enable Additional Options like forgot pwd , unlock account in OKTA hosted site | 2022-07-28 |  | Pending (should be combined CWB/Temenos) | Tony
TEM.19 | Get Spotlight - Provide authorise URL, signout URL, issuer ID, scope, clientID & secretKey | 2022-07-21 | 2022-07-21 | Completed | Tony/Pavani/Gowthami
TEM.20 | Spotlight - Okta team will Provide call back URL to Temenos Team | 2022-07-21 | 2022-07-21 | Completed | Pavani/Gowthami |  |  | 5Min
TEM.21 | Spotlight - Configure OKTA SSO - authorise URL, signout URL, issuer ID, scope, callback URL, Client-ID & SecretKey | 7/28/2022: 11:30 MT | 7/28/2022: 11:40 MT | Pending | Tony/Pavani/Gowthami |  |  | 0.5H
TEM.22 | Spotlight - Add admin/default user in Okta |  |  | Pending | Tony
TEM.23 | Configuration check for SBDCO APP deployment - Receive App details and configure | 7/28/2022: 11:30 MT | 7/29/2022: 00:00MT | Pending | Pavani/Vijaya/Satish
TEM.24 | Upload cwbServices.jar before doing integration changes(includes processor changes) | 7/29/2022: 00:00MT | 7/29/2022: 00:20MT | Pending | Pavani/Gowthami
TEM.25 | Temenos - ENCRYPTION PUBLICKEY for Card linking | 7/29/2022: 00:00MT | 7/29/2022: 00:20MT | Pending | Vijaya
TEM.26 | BRIM - External URL to apply for new CWB Master Card | 7/29/2022: 00:00MT | 7/29/2022: 00:20MT | Pending | Vijaya
TEM.27 | BRIM - SSO LINK | 7/29/2022: 00:00MT | 7/29/2022: 00:20MT | Pending | Vijaya
TEM.28 | Mule Deployment in Production for R1.1 | 7/29/2022:00:00 MT | 7/28/2022:01:00 MT | Pending | CWB
TEM.29 | Backend API Testing and Smoke Test in the Prod environment | 7/28/2022: 01:00 MT | 7/23/2022: 1:15 MT | Pending | Vijaya/Satish |  |  | 15Min
TEM.30 | OLB Production Deployment
TEM.31 | Backup the existing Fabric apps (DBPLocalServices, KonyBankingAdminConsole, EventsManager and AlertsEngine ) from Target environment. | 7/28/2022: 10:30 MT | 7/28/2022:11:00 MT | Pending | Pavani/Gowthami |  |  | 2H
TEM.32 | Export the Fabric Apps from the source environment. | 7/28/2022: 11:00 MT | 7/28/2022: 11:30 MT | Pending | Pavani/Gowthami |  |  | 2H
TEM.33 | Import the Fabric apps into Target environment. | 7/28/2022: 11:30 MT | 7/29/2022: 00:00 MT | Pending | Pavani/Gowthami |  |  | 2H
TEM.34 | Update the Identity Service (DbxUserLogin) URL to map with target environment. | 7/29/2022: 00:00 MT | 7/29/2022: 00:10 MT | Pending | Pavani/Gowthami |  |  | 15M
TEM.35 | Update the Identity Service (OktaOAuthIdentityProvider) - OktaOAuthIdentityProvider - Authorize Endpoint, Token Endpoint, Callback URL, Logout Url, Client ID, Client Secret | 7/29/2022: 00:10 MT | 7/29/2022: 00:25 MT | Pending | Pavani/Gowthami |  |  | 0.5H
TEM.36 | Update DB configuration with the Target database credentials in the Integration Services,Object services and in configuration parameters (dbpRbLocalServicesdb & CRUDLayer) for all the applicable apps(DBPLocalservices,KonyBankingAdminConsole,DBPEventManager) | 7/29/2022: 00:25 MT | 7/29/2022:12:40 MT | Pending | Pavani/Gowthami |  |  | 1H
TEM.37 | Update MuleSoft endpoints with the correct environment URL & credentials. | 7/29/2022:12:40 MT | 7/29/2022: 01:10 MT | Pending | Pavani/Gowthami |  |  | 0.5H
TEM.38 | Compare & merge Server Properties with source environment and, update the values which are target env specific. | 7/29/2022: 01:10 MT | 7/29/2022: 01:30 MT | Pending | Pavani/Gowthami
TEM.39 | Compare & merge Client Properties with source environment and, update the values which are target env specific. | 7/29/2022: 01:10 MT | 7/29/2022: 01:30 MT | Pending | Pavani/Gowthami |  |  | 1H
TEM.40 | Configure Engagement App in Fabric | 7/29/2022: 01:30 MT | 7/29/2022: 01:40 MT | Pending | Pavani/Gowthami |  |  | 1H
TEM.41 | Export & import Event manager app from source to target - Navaera | 7/29/2022: 01:40 MT | 7/29/2022: 01:50 MT | Pending | Pavani/Gowthami
TEM.42 | Creating userid and password on dbpEventManager userstore | 7/29/2022: 01:50 MT | 7/29/2022: 02:00 MT | Pending | Pavani/Gowthami |  |  | 0.5H
TEM.43 | App Security Configuration - HTTP Integrity | 7/29/2022: 02:00 MT | 7/29/2022: 02:10 MT | Pending | Pavani/Gowthami |  |  | 10M
TEM.44 | Execute R1.1 DB scripts | 7/29/2022: 02:10 MT | 7/29/2022: 04:40 MT | Pending | Pavani/Gowthami |  |  | 8H
TEM.45 | DCO URL - Open New Account - Sharing with CWB/Mule Team | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami
TEM.46 | Dashboard - Update Connection Microservice BaseURL in Fabric | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami |  |  | 10M
TEM.47 | Dashboard - Fabric config update for the Consent API | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami |  |  | Repeated as above
TEM.48 | Dashboard - Update Fabric XAI URLs | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami
TEM.49 | Dashboard - Update Fabric Codat URLs | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami
TEM.50 | Dashboard - Validate Analytics API and TDL | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami
TEM.51 | Configure in fabric - Consent | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Vijaya/Satish |  |  | 1M
TEM.52 | Configure DM Database and Test connectivity | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Vijaya/Satish |  |  | 20M
TEM.53 | Update Okta SSO config into Fabric for Spotlight | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami |  |  | 10M
TEM.54 | Configure in fabric - Spotlight SSO auth url | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami |  |  | 10M
TEM.55 | Confugure in fabric - Spotlight SSO client Id | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami |  |  | 10M
TEM.56 | Confugure in fabric - Spotlight SSO logout URLclient Id | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Gowthami |  |  | 1M
TEM.57 | Configure in Fabric - External URL for the new card | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Vijaya/Satish |  |  | 1M
TEM.58 | Configure the external URL Cert for app pinning | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Pavani/Vijaya/Satish |  |  | 1M
TEM.59 | Configure BRIM - SSO LINK | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Vijaya/Satish |  |  | 1M
TEM.60 | Configure BRIM encryption public key | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Vijaya/Satish |  |  | 1M
TEM.61 | Confugure in fabric - BRIM apply for new card link | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Vijaya/Satish |  |  | 1M
TEM.62 | Configure the Fabric log levels & log masking for sensitive info | 7/29/2022: 02:00 MT | 7/29/2022: 03:00 MT | Pending | Vijaya/Satish |  |  | 0.5H
TEM.63 | Upload the custom code jars (cwbservices, eventdispatcher, migration ) for pre or post processor changes | 7/29/2022: 03:00 MT | 7/29/2022: 04:00 MT | Pending | Pavani/Gowthami |  |  | 1H
TEM.64 | Configure Campaign MS - Campaign Engine, KonyBankingAdminConsole, ODataCampaign | 7/29/2022: 03:00 MT | 7/29/2022: 04:00 MT | Pending | Pavani/Gowthami |  |  | 1H
TEM.65 | Publish Fabric apps (KonyBankingAdminConsole) | 7/29/2022: 03:00 MT | 7/29/2022: 04:00 MT | Pending | Pavani/Gowthami |  |  | 2H
TEM.66 | Publish Fabric apps (DBPLocalServices, event manager,odatacampaign,limitsengine and campaign engine). | 7/29/2022: 03:00 MT | 7/29/2022: 04:00 MT | Pending | Pavani/Gowthami |  |  | 0.5H
TEM.67 | Download the web applications (cwbDigital.zip & Spotlight.zip) from source environment. | 7/29/2022: 03:00 MT | 7/29/2022: 04:00 MT | Pending | Pavani/Gowthami |  |  | 0.5H
TEM.68 | Extract the downloaded zip files with the same name. | 7/29/2022: 03:00 MT | 7/29/2022: 04:00 MT | Pending | Pavani/Gowthami |  |  | 0.5H
TEM.69 | In app.js, update URLs, appkey and appsecret with the specific target environment. | 7/29/2022: 03:00 MT | 7/29/2022: 04:00 MT | Pending | Pavani/Gowthami |  |  | 0.5H
TEM.70 | Compress back the folder again into zip files with the same names. | 7/29/2022: 03:00 MT | 7/29/2022: 04:00 MT | Pending | Pavani/Gowthami |  |  | 2H
TEM.71 | Upload the cwbDigital.zip to Fabric DBPLocalServices app and publish. | 7/29/2022: 04:00 MT | 7/29/2022: 04:30 MT | Pending | Pavani/Gowthami |  |  | 1H
TEM.72 | Upload the Spotlight.zip to KonBankingAdminConsole Fabric app and publish. | 7/29/2022: 04:30 MT | 7/29/2022: 05:00 MT | Pending | Pavani/Gowthami
TEM.73 | Spotlight- Configurations related to limits,features,roles,alerts |  |  | Pending | CWB
TEM.74 | CWB Sign-off - After Prod binaries submitted to app store - Test Flight |  |  | Pending | CWB
TEM.75 | Share Release notes | 7/29/2022: 04:00 MT | 7/29/2022: 05:00 MT | Pending | Anil/Arindam
TEM.76 | Client testing in the target environment |  |  | Pending | CWB
TEM.77 | Client Sign-off |  |  | Pending | CWB
PROD OLB Launch
TEM.76 | Rollback - Use the same steps above to deploy the backed up apps. | 4 hours |  | Pending
Mobile Native Apps Production Deployment
TEM.77 | App version numbers for Ios and Android <Mark 07/26)> Version 4.0 | 2022-07-26 | 2022-07-26 | Completed | CWB
TEM.78 | Version code for Android <Mark 07/26)> Version 4.0 |  |  | Pending | CWB
TEM.79 | Any changes to the Application screens and Icons (If Any) | 2022-07-26 | 2022-07-26 | Completed | CWB
TEM.80 | Commit the App Icon changes in the production code base | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Pavani/Gowthami
TEM.81 | Clone the mobile code from the Target release branch in Source Tree | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam
TEM.82 | Import the source code in Visualizer (9.1.49) | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam
TEM.83 | Associate with target Fabric environment | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam |  | 2H | 2hrs
TEM.84 | Configure project settings in Visualizer - App version, Android Target SDK, Android Signing details. (ID and Company name same as R1.0) | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam |  | 1H | 1hr
TEM.85 | In Project Settings - verify public & private keys to make binary in the Protected mode | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam |  | 0.5H | 0.5hr
TEM.86 | Associate with Target Fabric App - DBPLocalServices & generate object model. | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam |  | 0.5H | 0.5hr
TEM.87 | Build native local for Android & iOS in the protected mode | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam |  | 0.5H | 0.5hr
TEM.88 | AAB file for Android generated successfully | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam |  | 0.5H | 0.5hr
TEM.89 | KAR file for iOS generated local successfully | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam |  | 2H | 2hrs
TEM.90 | Generate IPA from Xcode 13.2 using the generated KAR file - following the strict guidelines in Temenos Binary Generation doc | 7/29/2022: 05:30 MT | 7/29/2022: 08:30 MT | Pending | Anil/Arindam |  | 0.5H | 0.5hr
TEM.91 | App testing in target environment + C1 Go/No-Go |  |  | Pending | CWB |  | 0.5H | 0.5hr
TEM.92 | Receive App Store + Play Store contents (Description, Any Latest Images, What's new etc..) |  |  | Pending | CWB |  | 2H | 2hrs
TEM.93 | Prepare Google App Store listing for Android |  |  | Pending | CWB
TEM.94. | Upgrade confirmation message is going to be the same | 2022-07-28 | 2022-07-28
TEM.94 | Upload Android App for App Submission |  |  | Pending | CWB |  | 3H | 3hrs
TEM.95 | Upload iOS App to App Submission |  |  | Pending | CWB
TEM.96 | Client App testing |  |  | Pending | CWB
PROD App Release
TEM.97 | Rollback - Restart the app submission into respective stores with the previous version of the android and iOS apps. |  |  | Pending
Production - All tasks to be completed for the go-live event
Draft list:
| Final code rollouts (if any) |  |  |  | CWB
| Data migration run - create friends and family users - TBD |  |  |  | CWB
First FF tester runs through - reports any issues
Second FF tester runs through - reports any issues
Third FF tester runs through - reports any issues
| Send out "we are live" communication |  |  |  | OCM
| Update OAS Links (EMT) in produciton (night of ) for Migrated users |  |  |  | MarkD/C1
Post-Production Validation
PP.1
PP.2
PP.3
PP.4
PP.5
PP.6
PP.7
PP.8
PP.9
PP.10
PP.11
PP.12
PP.13
Backout Plan
| Revert to R1.0.x |  |  |  | Temenos
| Revert Mobile Apps to Version x.y.z (Android and iOS) |  |  |  | Temenos
Post-Production - All tasks to be completed following go-live
| Draft list: |  |  |  |  | 0% | 0
| Setup daily check-in for 10 business days - technical and business - tech goes first and drops off while business continues on |  |  |  |  | 0% | 10
| Send out OCM post-prod comms |  |  |  |  | 0% | 10
| Send out project stream completion |  |  |  | Dilshad | 0% | 2

## RollBackActivities
Task ID | TASK | Scheduled START | Scheduled END | Status | ASSIGNED/CONFIRMATION GROUP | PROGRESS (%) | Duration (Days)
Rollback Activities
TEM.1 | Export the Fabric Apps((DBPLocalServices, KonyBankingAdminConsole, EventsManager and AlertsEngine ) from the backup. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 2H
TEM.2 | Import the Fabric apps into Target environment. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 2H
TEM.3 | Update the Identity Service (DbxUserLogin) URL to map with target environment. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 15M
TEM.4 | Update the Identity Service (OktaOAuthIdentityProvider) - OktaOAuthIdentityProvider - Authorize Endpoint, Token Endpoint, Callback URL, Logout Url, Client ID, Client Secret | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 0.5H
TEM.5 | Update DB configuration with the backup instance database credentials in the Integration Services,Object services and in configuration parameters (dbpRbLocalServicesdb & CRUDLayer) for all the applicable apps(DBPLocalservices,KonyBankingAdminConsole,DBPEventManager) | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 1H
TEM.6 | Update MuleSoft endpoints with the correct environment URL & credentials. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 0.5H
TEM.7 | Compare & merge Server Properties with source environment and, update the values which are target env specific. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 1H
TEM.8 | Compare & merge Client Properties with source environment and, update the values which are target env specific. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 1H
TEM.9 | Upload the custom code jars (cwbservices, eventdispatcher, migration ) for pre or post processor changes from the backup | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 0.5H
TEM.10 | Configure Campaign MS - Campaign Engine, KonyBankingAdminConsole, ODataCampaign | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 1H
TEM.11 | Publish Fabric apps (KonyBankingAdminConsole) | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 1H
TEM.12 | Publish Fabric apps (DBPLocalServices, event manager,odatacampaign,limitsengine and campaign engine). | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 2H
TEM.13 | Download the web applications (cwbDigital.zip & Spotlight.zip) from backup environment. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 0.5H
TEM.14 | Extract the downloaded zip files from the backup with the same name. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 0.5H
TEM.15 | In app.js, update URLs, appkey and appsecret with the specific target environment. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 0.5H
TEM.16 | Compress back the folder again into zip files with the same names. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 0.5H
TEM.17 | Upload the cwbDigital.zip to Fabric DBPLocalServices app and publish. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 2H
TEM.18 | Upload the Spotlight.zip to KonBankingAdminConsole Fabric app and publish. | 2022-07-27 | 2022-07-27 | Pending | Pavani/Gowthami |  | 1H

## Apps list
Systesm / 3rd Party Deploys |  | Update/deployment Required? Yes/No
| T24 | YES | Charlotte has provided R1.1 code dependencies. T24 currently set as pre-production release.
| Data Migration | TBD | Follow-up with Dapo and Henry to see if there is anything specific to R1.1 DM the requires promotion
| Celero | NO
| Central1 | YES | CRA Deployment
| Okta | YES | OLB R1.1 will require some updates to the Okta-hosted Sign In Widget (for mobile) to enable Forgot PW/Unlock.
| MuleSoft | YES
| CloudFlare | YES | Latest outage pages, planned and unplanned, to be deployed. Can be done in advance of R1.1 go-live.
| Navaera | NO
| CRA Direct Deposit | YES
| Helix | NO
| Mobile App | YES
| BRIM | YES
| XAI / TDL / TDH | YES | Confirm with Temenos
| Dashboard | YES
| Spotlight | YES
| Forgot password | YES | CR#2
| Encryption Keys | YES
| Codat | YES

## Contact list
Contact List
Organization | Name | Phone | Home phone | Email | Role | Notes
BRIM | Fayez Alameddine | 4168268160 |  | fayez.alameddine@brimfinancial.com | BRIM Lead
BRIM | Kevin Kim | 9053203031 |  | kevin.kim@brimfinancial.com | BRIM Lead
BRIM | Mo Zubby |  |  | mo.zubby@brimfinancial.com | Technical Support
BRIM | Thomas Patterson | 6473381468 |  | thomas.patterson@brimfinancial.com | BRIM Lead
CWB | Adam Skoreyko | 7809748010 |  | Adam.skoreyko@cwbank.com | DBX Business Lead
CWB | Alex Yakovenko | 2368335251 |  | alex.yakovenko@cwbank.com | Mulesoft/DTS Lead
CWB | Alvin Quach | 7809347087 |  | Alvin.quach@cwbank.com | Project Manager
CWB | Andrew Petesky | 7807204226 |  | andrew.petesky@cwbank.com | Project Manager
CWB | Carmela Pucci | 7809835216 |  | Carmela.pucci@cwbank.com | QA Lead
CWB | Carmen Girardin | 2045584669 |  | carmen.girardin@cwbank.com | IAM Lead
CWB | Christina Mullin |  |  | christina.mullin@cwbank.com | Digital Program Owner
CWB | Dilshad Bhatti |  |  | dilshad.bhatti@cwbank.com | Program Manager
CWB | Dino Noce | 7806863285 |  | dino.noce@cwbank.com | Project Manager
CWB | Edmund Chua | 7809194664 |  | Edmund.chua@cwbank.com | VCOO Business Lead
CWB | Gerry Weber | 2369912757 |  | gerry.weber@cwbank.com | Technical lead
CWB | Jason Bond |  |  | Jason.bond@cwbank.com | Digital Program Owner
CWB | Kris Aloisio | 7809646957 |  | kris.aloisio@cwbank.com | BAS Support
CWB | Mark Doubinin | 5879879460 |  | mark.doubinin@cwbank.com | DTS Lead
CWB | Mohammed Yahya | 7806193224 |  | mohammed.yahya@cwbank.com | IAM Technical Support
CWB | Tony Fang |  |  | tony.fang@techjutsu.com | IAM Consultant
Temenos | Ahmed Tawfik | 6478938908 |  | atawfik@temenos.com | Digital Program Owner
Temenos | Niel Colinares | 4167990798 |  | Niel.colinares@cwbank.com | Program Manager
Temenos | Sundhar Sangaranarayanan | 6472126477 |  | s.sundhar@temenos.com | Project Manager
Temenos | Hemantha kallathi |  |  | hemantha.kallati@temenos.com | Senior Solution Architect
Temenos | Vijay Parella | 2054276587 |  | p.vijayalakshmi@temenos.com | Architect/Tech Lead
Temenos | Satish Kolkunda | 6475760345 |  | satish.kolkunda@contractor.temenos.com | TL
Temenos | Kalin Todorov |  |  | ktodorov@temenos.com | VCOO Tech Lead
Temenos | Karthikeyan Koothan |  |  | karthikeyank@temenos.com | Infinity
Temenos | Goutham Sahu | 9989475327 |  | goutam.sahu@temenos.com | Product Development
Temenos | Krupal Chennuri | 8978306909 |  | krupal.chennuri@temenos.com | Visualizer
Temenos | Lakshmankumar | 7893149141 |  | Lakshmankumar Kothagundla | Visualizer
Temenos | Veera Nagireddy | 9886054926 |  | veeravsn@temenos.com | Cloud Operations / Hosting
Temenos | Vani Tiruveedhula | 9490793420 |  | vani.tiruveedhula@temenos.com | PACS
Temenos | Kanuru Lokesh | 9948053807 |  | kanuru.lokesh@temenos.com | IT
Temenos | Satya Tammana | 9885052849 |  | satya.tammana@temenos.com | Delivery Manager
Temenos | Vamsi Chilukuri | 9866273937 |  | vamsikrishna.c@temenos.com | Delivery Manager
Temenos | Srikanth Sriramoji | 9908225443 |  | srikanth.sriramoji@temenos.com | Architect
Temenos | Pavani Challa | 9059282576 |  | pavani.challa@temenos.com | Tech Lead
Temenos | Gowthami Murugadass | 8220933442 |  | m.gowthami@temenos.com | Developer
Temenos | Divya Bysani | 9553752419 |  | divya.bysani@temenos.com | Developer
Temenos | Chennoju Suraj | 8464912238 |  | chennoju.suraj@temenos.com | Developer
Temenos | Raineesh Shaik | 9100331704 |  | raineesh.shaik@temenos.com | Developer
Temenos | Uday Kumar Rapolu | 8801091876 |  | udaykumar.rapolu@temenos.com | Developer
Temenos | Kavya Monisha | 9791152624 |  | kavya.monisha@contractor.temenos.com | Developer
Temenos | Santosh Thogiti | 9160467047 |  | santhosh.thogiti@temenos.com | Developer
Temenos | Gayathri Maku | 6301215082 |  | gayathri.maku@contractor.temenos.com | Developer
Temenos | Anil Kesanupalli | 9866224712 |  | anil.kesanupalli@temenos.com | QA Lead
Temenos | Arindam Bose | 7893501919 |  | arindam.bose@temenos.com | QA Lead
Temenos | Chandrakanth Ramayanapu | 7569096888 |  | chandra.ramayanapu@temenos.com | Test Engineer
Temenos | Jahnavi Banavatu | 9030138256 |  | banavatu.jahnavi@temenos.com | Test Engineer
Temenos | Mansoor Hussain | 8157930268 |  | mansoor.hussain@contractor.temenos.com | CDB
Temenos | Robert Kingsly |  |  | grobertkingsly@temenos.com | Engineering Manager
Temenos | Marlon | 593990361401 |  | marlon.ruiz@temenos.com | Senior cloud

## Indicative Timeline (hidden)
[6 empty] | 2021-01-01 | [51 empty] | 2022-01-01
[6 empty] | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | 2022-01-03 |  |  |  |  | 2022-02-07 |  |  |  | 2022-03-07 |  |  |  | 2022-04-04 |  |  |  | 2022-05-02 |  |  |  |  | 2022-06-06 |  |  |  | 2022-07-04 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-05 |  |  |  | 2022-10-03 |  |  |  |  | 2022-11-07 |  |  |  | 2022-12-05
|  | Assignee | Progress | Task Start | Task End | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
Public Website (PWS) | Readiness
| Project Plan & Governance |  | 0% | 2021-01-04 | 2021-02-18
| Training |  | 0% | 2021-01-04 | 2021-01-18
Mobile App & Online Banking (OLB) | OLB and Mobile App1
| Initial Config & ISO/API Test |  | 0% | 0 | 0
| Data Seeding |  | 0% | 0 | 0
Mobile App Only
| TEST Config & Test (Mobile) |  | #N/A | #N/A | #N/A
| UAT Config & Test (Mobile) |  | #N/A | #N/A | #N/A
| Client UAT (Mobile) |  | #N/A | #N/A | #N/A
| Client BETA F&F/Pilot (Mobile) |  | #N/A | #N/A | #N/A
| PROD App Release |  | 0% | 2022-04-02 | 2022-04-02
OLB Only
| TEST Config & Test (OLB) |  | #N/A | #N/A | #N/A
| UAT Config & Test (OLB) |  | #N/A | #N/A | #N/A
| Client UAT (OLB) |  | #N/A | #N/A | #N/A
| Client BETA F&F/Pilot (OLB) |  | #N/A | #N/A | #N/A
| PROD OLB Launch |  | 0% | 2022-03-26 | 2022-03-26
Notes

## Project Readiness (hidden)
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Kick-off Date: | 2021-01-04 |  | Display Week: | 1 | [5 empty] | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-01-04 to 2021-02-28
JIRA # | TASK | Description | ASSIGNED GROUP | PROGRESS (%) | Duration (Days) | Scheduled START | Scheduled END | Estimated/Actual START | Estimated/Actual END | DAYS | time axis 2021-01-04 to 2021-02-28
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Readiness
| Project Plan & Governance |  | C1/Client | 0% | 34 | 2021-01-04 | 2021-02-18
| Executive Onboarding - Senior Level | CU onboarding by RM | C1/Client | 0% | 0 | 2021-01-04 | 2021-01-04 |  |  | 1
| Project Kick Off with Credit Union Project Team | First touchpoint with FIT Team | C1 | 0% | 0 | 2021-01-04 | 2021-01-04 |  |  | 1
| Follow-up Touchpoint and Setup Weekly Cadence | Second touchpoinit with FIT Team | C1 | 0% | 5 | 2021-01-04 | 2021-01-11 |  |  | 8
| Create Gap Analysis | Identify feature gap analysis between MD and Forge | C1 | 0% | 10 | 2021-01-12 | 2021-01-26
| Gap Analysis: Sign-off | Client signs off on gap analysis | Client | 0% | 0 | 2021-01-26 | 2021-01-26
| Determine channel strategy (PWS, Mobile and OLB) | Determine the launch order for the channels | C1/Client | 0% | 10 | 2021-01-12 | 2021-01-26 |  |  | 15
| Determine Launch Strategies for each Channel | Determine the launch dates for each channel's Beta and Market Launch | C1/Client | 0% | 10 | 2021-01-12 | 2021-01-26 |  |  | 15
| Develop Project Plan with Schedule Estimates | Add estimates for duration and dates for all actvities | C1/Client | 0% | 10 | 2021-01-12 | 2021-01-26
| Project SoW: Draft Development | Develop the draft copy of SoW for review | C1 | 0% | 5 | 2021-01-27 | 2021-02-03
| Project SoW: Sign-off | Client and C1 sign off on SoW | C1/Client | 0% | 10 | 2021-02-04 | 2021-02-18
| Training |  | Client | 0% | 11 | 2021-01-04 | 2021-01-18
| Spark Learning | Complete Training on https://sparklearning.central1.com/ | Client | 0% | 10 | 2021-01-04 | 2021-01-18
| Webinar | Complete viewing the Webinar on https://www.youtube.com/watch?v=X7E96Zkmnxo&feature=youtu.be | C1/Client | 0% | 10 | 2021-01-04 | 2021-01-18
Insert new rows ABOVE this one

## Infinity OLB & Mob App (hidden)
OLB & Mobile Start Date: | [5 empty] | Display Week: | 1 |  |  |  |  | -5 | [6 empty] | 1900-01-01 | [6 empty] | 1900-01-08 | [6 empty] | 1900-01-15 | [6 empty] | 1900-01-22 | [6 empty] | 1900-01-29 | [6 empty] | 1900-02-05 | [6 empty] | 1900-02-12
[12 empty] | -5 | -4 | -3 | -2 | -1 | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18
JIRA# | Required/Not Required | TASK | Description | ASSIGNED GROUP | PROGRESS (%) | Duration (Days) | Scheduled START | Scheduled END | Estimated/Actual START | Estimated/Actual END | DAYS | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Mobile + OLB
CU Engaged
Obtain Implementation Requirement Document
Initial Config & ISO/API Test
| Not Required | Raise request with AzureCloud Hosting for Fabric environment with base Infinity 2020.07 Apps & Campaign MS | Pre-req to start | Temenos
| Not Required | Procure Environment with credentials |  | Temenos
| Not Required | Cloud Flare (prod) - provided initial cert info - secure domain (completed) - cert to follow |  | CWB
| Not Required | Production Site URL, app names and version numbers (iOS & Android) - Production Checklist |  | CWB (Mark)
| Not Required | Whitelist Temenos public IP Address to CWB environment - MuleSoft, SMTP, Migration Database |  | CWB
| Not Required | Twilio Credentials from CWB for SMS alerts |  | CWB(Mark/DTS)
| Not Required | SMTP credentials for Email messaging |  | CWB (Braydon)
| Not Required | SSL Certificate for Production domain |  | CWB
| Not Required | Base URL and credentials for Mule endpoints |  | CWB (Brad)
| Not Required | Okta credentials for authentication |  | Okta (Tony, Rajiv)
| Not Required | Provide Redirect URIs for OLB and MB |  | Temenos
| Not Required | Configure the Redirect URIs in Okta |  | CWB & Okta (Tony)
| Not Required | Public keys for the Password Encryption |  | CWB (Brad)
| Not Required | Production VPN |  | CWB (Brad)
| Not Required | Jfrog Artefactory credentials |  | CWB (Brad)
| Not Required | Apple Developer account credentials for iOS signing |  | CWB (Mark)
| Not Required | Android credentials for Android signing |  | CWB (Mark)
| Not Required | Meta Data for Production Profile - Production Checklist |  | CWB (Mark)
| Not Required | Android & Apple app icons |  | CWB (Mark)
| Not Required | Create Production Profiles for iOS and Android |  | CWB (Brad)
| Not Required | Migration Database credentials |  | CWB (Braydon)
| Not Required | Navera Site URLs & keys |  | CWB (Alvin)
| Not Required | C1- Standup and test CRA Services |  | CWB (Mark)
| Not Required | Campaign images |  | CWB (Dino)
| Not Required | Test customer account(s) for production (Okta Provisioning) |  | CWB (Adam)
| Not Required | Mule Connectivity Test |  | Temenos
| Not Required | Okta Connectivity Test |  | Temenos
| Not Required | Migration Database Connectivity Test |  | Temenos
| Not Required | E-transfer Redirect Page configurations |  | CWB (Mark)
| Not Required | IP Whitelisting on C1 for e-Transfer |  | CWB (Mark)
| Not Required | Configure Fabric server and client properties |  | Temenos
| Required | Dashboard - Connection MicroService deployment |  | Temenos |  |  | 2021-10-27 | 2022-02-24
| Required | Dashboard - Fabric configuration for the Consent API URL and auth details |  | Temenos |  |  | 2021-10-27 | 2022-02-24
| Required | Dashboard - Fabric XAI URLs and auth details |  | Temenos |  |  | 2021-10-27 | 2022-02-24
| Required | Dashboard - Fabric Codat URLs and auth details |  | Temenos |  |  | 2021-10-27 | 2022-02-24
| Required | Dashboard - Consent Timeout environment variable in Fabric |  | Temenos |  |  | 2021-10-27 | 2022-02-24
| Required | OLB & MB - Okta Config update to enable Additional Options like forgot pwd , unlock account in OKTA hosted site |  | Okta (Tony, Rajiv) | 100% |  |  | 2021-11-12
| Required | Spotlight - Provide authorise URL, signout URL, issuer ID, scope, clientID & secretKey |  | Okta (Tony, Rajiv) | 100% |  |  | 2021-11-12
| Required | Spotlight - Provide call back URL |  | Temenos |  |  | 2021-10-27 | 2021-11-12
| Required | Spotlight - Configure OKTA SSO - authorise URL, signout URL, issuer ID, scope, callback URL, Client-ID & SecretKey |  | Okta (Tony, Rajiv) | 100% |  |  | 2021-11-12
| Required | Spotlight - Add admin/default user in Okta |  | Okta (Tony, Rajiv) | 100% |  |  | 2021-11-12
| Required | Upload cwbServices.jar before doing integration changes(includes processor changes) |  | Temenos
| Required | CONSENT_MICROSERVICE_URL, CONSENT_CODAT_URL, CONSENT_ANALYTICS_URL |  | Temenos
| Required | BRIM - ENCRYPTION PRIVATEKEY for Card linking |  | CWB (Roney) | 100% |  |  | 2021-11-12
| Required | Temenos - ENCRYPTION PUBLICKEY for Card linking |  | CWB (Roney) | 100% |  |  | 2021-11-12
| Required | BRIM - External URL to apply for new CWB Master Card |  | BRIM (Fayez) |  |  |  | 2021-11-12
| Required | BRIM - SSO LINK |  | BRIM (Fayez) |  |  |  | 2021-11-12
| Required | BRIM - Test Cards |  | BRIM (Fayez) |  |  |  | 2021-11-12
| Required | Mule Deployment in Production for R1.1 |  | CWB |  |  |  | 2021-11-12
| Required | Backend API Testing and Smoke Test in the Prod environment |  | Temenos |  |  |  | 2022-03-26
| Required | Repeat above steps which required to setup the other Production site for DR ? |  | Temenos (Ram) |  |  |  | 2022-03-26
|  | Data Seeding |  |  | 0%
| Not Required | Create customers in Migration DB (flush out further with Dapo) |  | CWB
| Not Required | Obtain business customers to migrate in the Migration Database |  |  | 0%
| Not Required | Migrate Retail Customers Profiles in Okta |  |  | 0%
OLB Production Deployment
| Required | Backup the existing Fabric apps (DBPLocalServices, KonyBankingAdminConsole, EventsManager and AlertsEngine ) from Target environment. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Export the Fabric Apps from the source environment. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Import the Fabric apps into Target environment. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Update the Identity Service (DbxUserLogin) URL to map with target environment. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Update the Identity Service (OktaOAuthIdentityProvider) - OktaOAuthIdentityProvider - Authorize Endpoint, Token Endpoint, Callback URL, Logout Url, Client ID, Client Secret |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Update DB configuration with the Target database credentials in the Integration Services (dbpRbLocalServicesdb & CRUDLayer) |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Not Required | Execute the DB Scripts (initial setup - all scripts) Scripts location - https://bitbucket.org/konykps/cwb_processsors/src/master/resources/DBQueires/
| Required | Update MuleSoft endpoints with the correct environment URL & credentials. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Compare & merge Server Properties with source environment and, update the values which are target env specific. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Compare & merge Client Properties with source environment and, update the values which are target env specific. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Configure Engagement App in Fabric |  | Temenos
| Required | Export & import Event manager app from source to target - Navera |  | Temenos
| Required | App Security Configuration - HTTP Integrity |  | Temenos
| Not Required | Global limits for throttling
| Required | Execute R1.1 DB scripts |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | DCO URL - Open New Account |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Dashboard - Update Connection Microservice BaseURL in Fabric |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Dashboard - Fabric config update for the Consent API |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Dashboard - Update Fabric XAI URLs |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Dashboard - Update Fabric Codat URLs |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Dashboard - Validate Analytics API and TDL |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Confugure in fabric - Consent |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Update Okta SSO config into Fabric for Spotlight |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Confugure in fabric - Spotlight SSO auth url |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Confugure in fabric - Spotlight SSO client Id |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Confugure in fabric - Spotlight SSO logout URLclient Id |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Configure in Fabric - External URL for the new card |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Configure the external URL Cert for app pinning |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Configure BRIM - SSO LINK |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Configure BRIM encryption public key |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Confugure in fabric - BRIM apply for new card link |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Configure the Fabric log levels & log masking for sensitive info |  | Temenos
| Required | Upload the custom code jars (cwbservices, eventdispatcher, migration ) for pre or post processor changes |  | Temenos
| Required | Configure Campaign MS - Campaign Engine, KonyBankingAdminConsole, ODataCampaign |  | Temenos
| Required | Publish Fabric apps (KonyBankingAdminConsole) |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Publish Fabric apps (DBPLocalServices). |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Download the web applications (cwbDigital.zip & Spotlight.zip) from source environment. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Extract the downloaded zip files with the same name. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | In app.js, update URLs, appkey and appsecret with the specific target environment. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Compress back the folder again into zip files with the same names. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Upload the cwbDigital.zip to Fabric DBPLocalServices app and publish. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Upload the Spotlight.zip to KonBankingAdminConsole Fabric app and publish. |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Internal QA Sign-off |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Share Release notes |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Required | Client testing in the target environment |  | CWB |  |  | 2022-03-26 | 2022-03-26
| Required | Client Sign-off |  | CWB |  |  | 2022-03-26 | 2022-03-26
| Not Required | Initial Theming - OAuth pushed to Prod (Mobile and OLB)
| Not Required | Export OLB Portal from UAT and import to Editorial
| Not Required | Create CloudFront distribution for www and beta
| Not Required | Prepare DNS change for Friends & Family Beta Launch
| Not Required | Setup NGINX Redirects for Prod
| Not Required | Publish OLB portal and pages to Staging and Live
| Not Required | Friends & Family Beta Launch
| Not Required | Client OLB testing for F&F/Pilot
| Required | PROD OLB Launch |  | Temenos |  |  | 2022-03-26 | 2022-03-26
| Optional | Rollback - Use the same steps above to deploy the backed up apps.
Insert new rows ABOVE this one
Mobile Native Apps Production Deployment
| Required | Any changes to the Application screens and Icons |  | CWB
| Required | Commit the App Icon changes in the production code base |  | Temenos
| Required | Clone the mobile code from the Target release branch in Source Tree |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | Import the source code in Visualizer (9.1.49) |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | Associate with target Fabric environment |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | Configure project settings in Visualizer - App version, Android Target SDK, Android Signing details. |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | In Project Settings - verify public & private keys to make binary in the Protected mode |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | Associate with Target Fabric App - DBPLocalServices & generate object model. |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | Build native local for Android & iOS in the protected mode |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | Need Credentials for App Store (ios&android) for Temenos QA access |  | CWB
| Required | App version numbers for Ios and Android |  | CWB
| Required | Version code for Android |  | CWB
| Required | APK file for Android generated successfully |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | KAR file for iOS generated local successfully |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | Generate IPA from Xcode using the generated KAR file - following the strict guidelines in Temenos Binary Generation doc |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | Mobile App target environment build |  | Temenos |  |  | 2022-07-11 | 2022-07-11
| Required | App testing in target environment + C1 Go/No-Go |  |  |  |  | 2022-03-26 | 2022-03-26
| Required | Receive App Store + Play Store contents (Description) |  |  |  |  | 2022-03-26 | 2022-03-26
| Required | Prepare Google App Store listing for Android |  |  |  |  | 2022-03-26 | 2022-03-26
| Required | Upload Android App for App Submission |  | CWB (DTS Team) |  |  | 2022-03-26 | 2022-03-26
| Required | Upload iOS App to App Submission |  | CWB (DTS Team) |  |  | 2022-03-26 | 2022-03-26
| Required | Client App testing |  | CWB (DTS Team) |  |  | 2022-03-26 | 2022-03-26
| Required | PROD App Release |  | Temenos |  |  | 2022-04-02 | 2022-04-02
| Optional | Rollback - Restart the app submission into respective stores with the previous version of the android and iOS apps. |  |  |  |  | 2022-04-02 | 2022-04-02

## CWB Deployment Plan (hidden)
CWB Start Date: |  | 2021-06-15 |  |  | Display Week: | 1 |  |  |  |  | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06
 | time axis 2021-06-14 to 2021-09-12
JIRA# | TASK | Description | ASSIGNED GROUP | PROGRESS (%) | Duration (Days) | Scheduled START | Scheduled END | Estimated/Actual START | Estimated/Actual END | DAYS | time axis 2021-06-14 to 2021-09-12
Pre-Production - All tasks that can be completed prior to go-live weekend
| T24 |  |  | 93.1%
| T24 R1 deployment analysis and package deployment list |  | Charlotte | 100% | 0 | 2021-06-15 | 2021-06-15
| Analyze required changes and time estimate for T24 Infinity container for web services |  | Braydon | 100% | 0 | 2021-06-17 | 2021-06-17
| Complete release management analysis |  | Charlotte | 100% | 0 | 2021-06-17 | 2021-06-17
| Deploy R1 to operational SIT1 env |  | RM Team | 100% | 0 | 2021-06-17 | 2021-06-17
| Test Digital T24 changes in SIT1 |  | QA Team | 100% | 12 | 2021-06-17 | 2021-07-05
| Config / complete T24 Infinity container in SIT1 |  | Braydon | 100% | 0 | 2021-06-17 | 2021-06-17
| Config / complete T24 Infinity container in SIT2 |  | Braydon | 100% | 0 | 2021-07-12 | 2021-07-12
| Deploy R1 to operational SIT2 env |  | RM Team | 100% | 0 | 2021-07-12 | 2021-07-12
| Regression test T24 in SIT2 |  | QA Team | 100% | 3 | 2021-07-12 | 2021-07-15
| Determine go/no-go for T24 R1 into production |  | CAS Team, QA Team | 100% | 0 | 2021-07-14 | 2021-07-14
| Determine go/no-go for T24 Infinity container as a part of the release |  | RM Team / Braydon | 100% | 0 | 2021-07-14 | 2021-07-14
| Deploy T24 R1 into production |  | RM Team / Braydon | 100% | 0 | 2021-07-18 | 2021-07-18
| Deploy T24 Infinity container |  | Braydon | 100% | 0 | 2021-07-18 | 2021-07-18
Data Migration
| Confirm signoff for CR submittance. |  | Dapo / Braydon | 100% | 0 | 2021-07-13 | 2021-07-13
| Submit CR for production change Includes: all config required for SFTP, the production DM database, as well as the private VPN between Temenos and CWB to provide read access to the required tables in the DB database |  | Dapo | 100% | 0 | 2021-07-22 | 2021-07-22
| Perform smoke test of setup |  | Dapo | 100% | 0 | 2021-07-23 | 2021-07-23
| Perform smoke test of VPN setup Dependency: This will require Temenos Infinity to be up and running. |  | Temenos | 0% | 2 | 2021-08-18 | 2021-08-20
| Deploy final DM process code to production |  | Dapo / Braydon | 0% | 0 | 2021-08-18 | 2021-08-18
Celero
| VPN Setup |  | Mark D / Brad | 100% | 0 | 2021-07-13 | 2021-07-13
| Confirm build by Celero for prod |  | Mark D | 100% | 0 | 2021-07-16 | 2021-07-16
| Mark to review with Brad regarding Celero and testing pre-prod using PostMan |  | Mark D / Brad |  | 1 | 2021-08-05 | 2021-08-06
| Config update for estatements and cheque images |  | Mark D |  | 0 | 2021-08-05 | 2021-08-05
Central1
| Meeting with C1 on timing of sign-off and go-ahead plan |  | Mark D | 100% | 0 | 2021-07-15 | 2021-07-15
| Confirm build by Celero for prod |  | Mark D | 100% | 0 | 2021-07-16 | 2021-07-16
| Mark to review with Brad regarding Celero and testing pre-prod using PostMan |  | Mark D / Brad |  | 1 | 2021-08-05 | 2021-08-06
| Config update for estatements and cheque images |  | Mark D |  | 0 | 2021-08-05 | 2021-08-05
| Submit CR for production change - Latest this can be submitted is 26-Aug. |  | Mark D |  | 0 | 2021-08-26 | 2021-08-26
| Config update for estatements and cheque images - Smoke test C1 connectivity. |  | Mark D |  | 0 | 2021-08-27 | 2021-08-27
Okta
| Confirm tasks with Tony regarding outstanding actions for pre-prod/prod |  | CWB |  | 0 | 2021-08-05 | 2021-08-05
| [Okta task] - flush out with Tony Fang |  |  |  | 0 | 2021-08-05 | 2021-08-05
| Add groups (Infinity Users, Infinity Users - Suspended) |  | Tony | 100%
| Add custom attributes (cif, pan, identityProvider) |  | Tony | 100%
| Add applications (Infinity (Mobile), Infinity (Online Banking)) |  | Tony | 75%
| Disable application self service |  | Tony | 100%
| Enable Security Notification Emails |  | Tony | 100%
| Enable Okta ThreatInsight to Log and block |  | Tony | 100%
| Configure Password policy |  | Tony | 100%
| Configure Sign On poicy |  | Tony | 100%
| Configure Multifactor Factor Types |  | Tony | 100%
| Configure Multifactor Factor Enrollment policies |  | Tony | 100%
| Configure Identity Providers for Sentry |  | Tony | 100%
| Configure Identity Providers routing rule for Sentry |  | Tony | 100%
| Configure Networks (Block List Countries, Tor Anonymizer Block) |  | Tony | 100%
| Configure custom authorization server |  | Tony | 100%
| Configure API tokens for Mule, Migration |  | Tony | 100%
| Add workflow to keep API tokens alive |  | Tony | 100%
| Configure Trusted Origins for Infinity OLB |  | Tony | 0%
| Configure Inline Hook Password Import |  | Tony | 75%
| Enable Client-based rate limiting to Enforce |  | Tony | 100%
| Configure Logo URL |  | Tony | 100%
| Configure Organization Logo |  | Tony | 100%
| Disable Optional User Account Fields |  | Tony | 100%
| Configure Custom URL Domain |  | Tony | 100%
| Configure Custom Sign In |  | Tony | 100%
| Configure Custom email domain |  | Tony | 100%
| Configure custom email templates |  | Tony | 100%
| [Okta task] |  |  |  | 0 | 2021-08-05 | 2021-08-05
MuleSoft
| Planning to rollout out all DB R1 APIs and complete smoke testing. Completed Celero and Helix |  | Brad M | 100% | 0 | 2021-07-22 | 2021-07-22
| Rollout remaining DB R1 APIs - Dependency: Code freeze 25-Aug |  | Brad M |  | 0 | 2021-08-26 | 2021-08-26
CloudFlare
| Confirm if non-prod is running through Akamai with Temenos team |  | Mark D | 100% | 0 | 2021-07-09 | 2021-07-09
| Dependency: Require production URL for online banking. Provide DCO non-prod and production URLs |  | Andrew P | 100% | 0 | 2021-07-19 | 2021-07-19
| Confirm if we need to exchange certs for enabling SSL comms. |  | Andrew P | 100% | 0 | 2021-07-20 | 2021-07-20
| Generate certs for DB prod |  | Kris A / Braydon |  | 0 | 2021-08-18 | 2021-08-18
| Confirm non-prod is working through CloudFlare for DB - target Data Migration |  | QA Team |  | 4 | 2021-08-09 | 2021-08-13
Navaera
| Prod VPN setup with vendor and CWB in advance - connectivity test only. |  | Brad M |  | 0 | 2021-08-16 | 2021-08-16
CRA Direct Deposit
| Setup test and production database (look for ETA for the Prod DB from Brad M.) |  | Brad M | 100% | 0 | 2021-07-14 | 2021-07-14
| Add firewall routing for Azure (DB is located here) |  | Braydon |  | 0 | 2021-08-20 | 2021-08-20
| New interface for DD (ready to test in prod when CRA is good and QA is good) |  | Chix / Brad |  | 0 | 2021-08-23 | 2021-08-23
Helix
| Submit CR for Helix changes - APIs required for deployment. |  | Brad M | 100% | 0 | 2021-07-22 | 2021-07-22
| Rollout APIs to production. |  | Brad M | 100% | 0 | 2021-07-22 | 2021-07-22
Mobile App
| Application profile (icons, screen shots, verbage - UX team) |  | UX Team | 50% | 0 | 2021-07-13 | 2021-07-13
| Ensure test account is activity working in prod (T24) |  | Mark D |  | 0 | 2021-08-03 | 2021-08-03
| Create account for Android |  | Mark D | 100% | 0 | 2021-07-08 | 2021-07-08
| Create account for iOS |  | Mark D | 100% | 0 | 2021-07-26 | 2021-07-26
| Need full QA sign-off before release to Apple or Android |  | QA Team |  | 0 | 2021-08-24 | 2021-08-24
| Licensing with Temenos for prod |  | Mark D |  | 0 | 2021-08-04 | 2021-08-04
| Create 2 additional test accounts (MFA enabled) - will have 2 with MFA and 2 without in production |  | Mark D |  | 0 | 2021-08-05 | 2021-08-05
0%
| Production go/no-go |  | CWB | 0%
Production - All tasks to be completed for the go-live event
| Draft list: |  |  | 0%
| Final code rollouts (if any) |  | CWB | 0%
| Data migration run - create friends and family users - TBD |  | CWB | 0%
| First FF tester runs through - reports any issues |  |  | 0%
Second FF tester runs through - reports any issues
| Third FF tester runs through - reports any issues |  |  | 0%
| Send out "we are live" communication |  | OCM | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
|  |  |  | 0% | 0 | 1900-01-01 | 1900-01-01
|  |  |  | 0% | 13 | 1900-01-02 | 1900-01-18
|  |  |  | 0% | 0 | 1900-01-02 | 1900-01-02
|  |  |  | 0% | 10 | 1900-01-03 | 1900-01-17
|  |  |  | 0% | 0 | 1900-01-18 | 1900-01-18
|  |  |  | 0% | 24 | 1900-01-19 | 1900-02-21
|  |  |  | 0% | 5 | 1900-01-19 | 1900-01-26
|  |  |  | 0% | 5 | 1900-01-19 | 1900-01-26
|  |  |  | 0% | 10 | 1900-01-19 | 1900-02-02
|  |  |  | 0% | 5 | 1900-01-19 | 1900-01-26
|  |  |  | 0% | 5 | 1900-01-19 | 1900-01-26
|  |  |  | 0% | 5 | 1900-01-29 | 1900-02-05
|  |  |  | 0% | 5 | 1900-01-19 | 1900-01-26
|  |  |  | 0% | 5 | 1900-01-29 | 1900-02-05
|  |  |  | 0% | 0 | 1900-02-06 | 1900-02-06
|  |  |  | 0% | 10 | 1900-02-07 | 1900-02-21
|  |  |  | 0% | 17 | 1900-02-07 | 1900-03-01
|  |  |  | 0% | 5 | 1900-02-07 | 1900-02-14
|  |  |  | 0% | 5 | 1900-02-22 | 1900-03-01
Insert new rows ABOVE this one
Post-Production - All tasks to be completed following go-live
| Draft list: |  |  | 0% | #REF! | #REF! | #REF!
| Setup daily check-in for 10 business days - technical and business - tech goes first and drops off while business continues on |  |  | 0% | 10 | #REF! | #REF!
| Send out OCM post-prod comms |  |  | 0% | 10 | #REF! | #REF!
| Send out project stream completion |  | Dilshad | 0% | 2 |  | 1900-01-02
|  |  |  | 0% | 20 |  | 1900-01-26
|  |  |  | 0% | 17 | 1900-01-29 | 1900-02-20
|  |  |  | 0% | 5 | 1900-01-29 | 1900-02-05
|  |  |  | 0% | 5 | 1900-01-29 | 1900-02-05
|  |  |  | 0% | 5 | 1900-01-29 | 1900-02-05
0%
0%
0%
0%
0%
0%
0%
|  |  |  | 0% | 5 | 1900-01-29 | 1900-02-05
|  |  |  | 0% | 10 | 1900-02-06 | 1900-02-20
|  |  |  | 0% | 20 | 1900-02-21 | 1900-03-20
|  |  |  | 0% | 2 | 1900-02-21 | 1900-02-23
|  |  |  | 0% | 0 | 1900-02-26 | 1900-02-26
|  |  |  | 0% | 10 | 1900-02-27 | 1900-03-13
|  |  |  | 0% | 0 | 1900-03-14 | 1900-03-14
|  |  |  | 0% | 15 | 1900-02-27 | 1900-03-20
|  |  |  | 0% | #REF! | #REF! | #REF!
|  |  |  | 0% | 5 | 1900-03-15 | 1900-03-22
|  |  |  | 0% | 5 | 1900-03-15 | 1900-03-22
|  |  |  | 0% | 2 | 1900-03-23 | 1900-03-27
|  |  |  | 0% | 2 | #REF! | #REF!
|  |  |  | 0% | 5 | 1900-03-15 | 1900-03-22
|  |  |  | 0% | 5 | 1900-03-28 | 1900-04-04
|  |  |  | 0% | 5 | 1900-03-28 | 1900-04-04
|  |  |  | 0% | 0 | 1900-04-05 | 1900-04-05
|  |  |  | 0% | 10 | 1900-04-06 | 1900-04-20
|  |  |  | 0% | 18 | 1900-04-06 | 1900-05-01
|  |  |  | 0% | 5 | 1900-04-06 | 1900-04-13
|  |  |  | 0% | 5 | 1900-04-23 | 1900-04-30
|  |  |  | 0% | 0 | 1900-05-01 | 1900-05-01

## Sheet2 (hidden)
1 | CU Engaged | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1001 | FIT-1001
2 | Obtain Implementation Requirement Document | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1835 | FIT-1835
3 | =======ONBOARDING FOR MOBILE OR OLB======= | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10262 | IT-10262
4 | CU making BH changes (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1003 | FIT-1003
5 | Setup BH Connectivity (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1005 | FIT-1005
6 | Import latest MD properties (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1800 | FIT-1800
7 | ISO testing in local Dev (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1164 | FIT-1164
8 | Setup Client JIRA Project and Access (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1320 | FIT-1320
9 | Obtain SSL Certificate for auth and forge subdomains (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-7939 | FIT-7939
10 | Add ID Mapper | OPEN | Christina Chan | Actions | https://jira.central1.com/browse/FIT-14954 | IT-14954
11 | Create DB & Tenant for DTAP (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1010 | FIT-1010
12 | Create AWS Role for CU (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1801 | FIT-1801
13 | Create AWS SQS queue for seeding and setup SCC for feature-auth (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1802 | FIT-1802
14 | Shape Security Setup (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1007 | FIT-1007
15 | OAuth Configuration in Dev & Test (Mobile and OLB) | OPEN | Joe Cheng | Actions | https://jira.central1.com/browse/FIT-5667 | FIT-5667
16 | Backend Configuration for DEV & TEST environment (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1836 | FIT-1836
17 | Product Mapping Configuration for DEV & TEST environment (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-2303 | FIT-2303
18 | E-transfer Configuration for DEV & TEST environment (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1837 | FIT-1837
19 | Configure DSA in Dev & Test (Mobile App and OLB) | OPEN | Joe Cheng | Actions | https://jira.central1.com/browse/FIT-6999 | FIT-6999
20 | Backend API Testing in TEST environment (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1840 | FIT-1840
21 | OAuth Configuration in Prod | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-14122 | IT-14122
22 | ========DATA SEEDING======= | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10265 | IT-10265
23 | Obtain Cursory QA seeding file from CU | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-3930 | FIT-3930
24 | Data Seeding Cursory Test in TEST | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1844 | FIT-1844
25 | Obtain QA seeding file from CU | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-3936 | FIT-3936
26 | Data Seeding Test in UAT | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1852 | FIT-1852
27 | Obtain Production seeding file & info from CU and schedule production seeding test | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-3937 | FIT-3937
28 | Data Seeding in Prod | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1859 | FIT-1859
29 | =======MOBILE ONLY======= | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10263 | IT-10263
30 | Mobile Environmental Setup (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1841 | FIT-1841
31 | Clone CXP Mobile Portal in TEST environment (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1016 | FIT-1016
32 | Update CXP Mobile Portal in TEST environment (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1017 | FIT-1017
33 | RDC Configuration in DEV & TEST environment (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1838 | FIT-1838
34 | Initial Theming - Webview, Native, OAuth (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1846 | FIT-1846
35 | Mobile App build in TEST environment (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1842 | FIT-1842
36 | App testing in TEST environment (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1843 | FIT-1843
37 | Deploy All Configuration from TEST to UAT (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1845 | FIT-1845
38 | Export Mobile Portal from TEST and import to UAT (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1851 | FIT-1851
39 | Create IOS / Android Store Project (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1030 | FIT-1030
40 | Mobile App internal UAT build (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1853 | FIT-1853
41 | App testing in UAT environment (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1854 | FIT-1854
42 | Mobile App external UAT build and upload (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1855 | FIT-1855
43 | Notify client of the UAT apps (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1032 | FIT-1032
44 | Client App testing in UAT environment (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-9768 | FIT-9768
45 | Deploy all config from UAT to Prod (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1858 | FIT-1858
46 | Initial Theming - OAuth pushed to Prod (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-14124 | IT-14124
47 | Export Mobile Portal from UAT and import to Editorial (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1856 | FIT-1856
48 | Mobile App Prod build (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1860 | FIT-1860
49 | Sync Mobile Portal to Staging and Live (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1857 | FIT-1857
50 | Prepare Google App Store listing for Android (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1867 | FIT-1867
51 | Receive App Store + Play Store contents (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1035 | FIT-1035
52 | Upload Android App for Alpha Testing (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1863 | FIT-1863
53 | Upload iOS App to TestFlight (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1864 | FIT-1864
54 | Notify clients of the Friends & Family Beta App (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1036 | FIT-1036
55 | Client App testing for F&F/Pilot (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1865 | FIT-1865
56 | Submit iOS App for Review (Mobile) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1866 | FIT-1866
57 | Prod App Release | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-1037 | FIT-1037
58 | =======ONLINE BANKING ONLY======= | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10266 | IT-10266
59 | MDi Lite Setup (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10229 | IT-10229
60 | Setup Auth Subdomain for OAuth (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-13411 | IT-13411
61 | Point forge subdomain to MemberDirect | OPEN | Christina Chan | Actions | https://jira.central1.com/browse/FIT-14955 | IT-14955
62 | Create OLB CXP Portal in TEST environment (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10259 | IT-10259
63 | Populate OLB pages in the CXP Portal (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10261 | IT-10261
64 | Initial Theming - OLB, OAuth, and e-Transfer (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10290 | IT-10290
65 | OLB Testing in TEST environment (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10291 | IT-10291
66 | Deploy All Configuration from TEST to UAT (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10316 | IT-10316
67 | Export OLB Portal from TEST and import to UAT (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10317 | IT-10317
68 | OLB Internal UAT | OPEN | Ciara Whelan | Actions | https://jira.central1.com/browse/FIT-13566 | IT-13566
69 | Internal QA Sign-off (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10318 | IT-10318
70 | Provide OLB URL to client for UAT (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10319 | IT-10319
71 | Client testing in UAT environment (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10321 | IT-10321
72 | Client UAT Sign-off (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10320 | IT-10320
73 | Deploy all config from UAT to Prod (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10322 | IT-10322
74 | Initial Theming - OAuth pushed to Prod (Mobile and OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-14123 | IT-14123
75 | Export OLB Portal from UAT and import to Editorial (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10323 | IT-10323
76 | Create CloudFront distribution for www and beta (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10338 | IT-10338
77 | Prepare DNS change for Friends & Family Beta Launch (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10339 | IT-10339
78 | Setup NGINX Redirects for Prod (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10337 | IT-10337
79 | Publish OLB portal and pages to Staging and Live (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10324 | IT-10324
80 | Friends & Family Beta Launch (OLB) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10340 | IT-10340
81 | =======ONBOARDING FOR PUBLIC ======= | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10289 | FIT-10289
82 | Obtain SSL Certificate for www and beta subdomains (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10348 | FIT-10348
83 | Portal Creation in DTAP (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10349 | FIT-10349
84 | Initial Theming for Public Site (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10350 | FIT-10350
85 | FULL LAUNCH - Create Change Order for CAB Approval (At least a week prior to launch) (PWS) | OPEN | Amr Fadl | Actions | https://jira.central1.com/browse/FIT-13815 | FIT-13815
86 | Setup PWS Functional Widget (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10351 | FIT-10351
87 | Content Population (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10352 | FIT-10352
88 | MDI Lite Web Development | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-11342 | FIT-11342
89 | BETA - Create Change Order for CAB Approval (At least a week prior to launch) (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10397 | FIT-10397
90 | BETA - Checklist for CXP Portal to prepare for Beta Launch (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10354 | FIT-10354
91 | BETA - NGINX Configuration (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10355 | FIT-10355
92 | BETA - Purchase/Acquire SSL Cert for the beta subdomain (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10356 | FIT-10356
93 | BETA - Installing the SSL Cert in AWS (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10364 | FIT-10364
94 | BETA - Create CloudFront Distribution (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10365 | FIT-10365
95 | BETA - Create Change Order to Network Team (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10359 | FIT-10359
96 | Beta Launched!! (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10360 | FIT-10360
97 | FULL LAUNCH - Create Change Order for CAB Approval (At least a week prior to launch) (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10398 | FIT-10398
98 | FULL LAUNCH - NGINX Configuration (301 Redirects, Robots.txt & sitemap.xml, non-www redirect, portal mapping) (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10362 | FIT-10362
99 | FULL LAUNCH - Purchase/Acquire SSL Cert for the www subdomain (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10363 | FIT-10363
100 | FULL LAUNCH - Installing the SSL Cert in AWS (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10357 | FIT-10357
101 | FULL LAUNCH - Create CloudFront Distribution (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10358 | FIT-10358
102 | FULL LAUNCH - Create Change Order to Network Team (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10366 | FIT-10366
103 | FULL LAUNCH - Day before Full Launch Preparation (PWS) | OPEN | Unassigned | Actions | https://jira.central1.com/browse/FIT-10367 | FIT-10367
104 | Member Full Launch!! (PWS) | OPEN | Unassigned |  | https://jira.central1.com/browse/FIT-10368 | FIT-10368

## OLB & Mob App (OLD) (hidden)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Conexus Forge Implementation |  |  | All Products |  | PWS | OLB | Mobile
Enter Company Name in cell B2. | Conexus
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  |  | Project Start: |  |  | 2020-01-01
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  |  | Display Week: |  |  | 1 |  |  |  |  | 2019-12-30 | [6 empty] | 2020-01-06 | [6 empty] | 2020-01-13 | [6 empty] | 2020-01-20 | [6 empty] | 2020-01-27 | [6 empty] | 2020-02-03 | [6 empty] | 2020-02-10 | [6 empty] | 2020-02-17
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2019-12-30 to 2020-02-23
Task ID | TASK | Description | Product | ASSIGNED GROUP | Duration (Days) | PROGRESS | Scheduled START | Scheduled END | Estimated/Actual START | Estimated/Actual END | DAYS | time axis 2019-12-30 to 2020-02-23
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Readiness
R01 | Executive Onboarding - Senior Level | CU onboarding by RM | All | C1/Client | 1
R02 | Project Kick Off with Credit Union Project Team | First touchpoint with FIT Team | All | C1 | 1
R03 | Follow-up Touchpoint and Setup Weekly Cadence | Second touchpoinit with FIT Team | All | C1 | 1
R04 | Determine channel strategy (PWS, Mobile and OLB) and MD sunset timelines | Determine the launch order for the channels and timeline to retire MD | All | C1/Client | 5
R05 | Determine Launch Strategies for each Channel | Determine the launch dates for each channel's Beta and Market Launch | All | C1/Client | 5
R06 | Project SoW: Draft Development | Develop the draft copy of SoW for review | All | C1 | 5
R07 | Project SoW: Sign-off | Client and C1 sign off on SoW | All | Client/C1 | 60
R08 | Banking Host & Data Seeding Discovery Session | Q & A for Pre-seeding Tests and Data Seeding | All | C1/Client | 1
R09 | Develop Project Plan with Schedule Estimates | Add estimates for duration and dates for all actvities | All | C1/Client | 5
R10 | Provide Credit Union branding and style guide by C1 | Provide all design documents | All | Client | 10
Training
T01 | Spark Learning | Complete Training on https://sparklearning.central1.com/ | All | Client | 10
T02 | Backbase | Complete Trainng on https://central1.learnupon.com/users/sign_in | All | Client | 5
T03 | Webinar | Complete viewing the Webinar (link) to be added | All | C1/Client | 1
Applepay Pre-Requisites
AP01 | Implement Strong PAC | Implement Strong PAC for Forge | Mobile | C1
AP02 | Implement 2SV | Implement 2SV (2 factor authentication) for Forge | Mobile | C1
AP03 | Implement Increased Auth (RSA) | Implement Increased Auth for Forge | Mobile | C1 | 0.2
AP04 | Implement Oauth | Implement Oauth for Forge | Mobile | C1 | 0.2 to 10
AP05 | Whitelist on C1's Firewall | Client to be whitelisted on C1's Firewall for access to Interac's Customer Service Portal | Mobile | C1 | 5
AP06 | Provide SOW and Signoff | Applepay specific SOW for Forge | Mobile | C1 | 10
AP07 | Provide Mobile Pay Addendum and Signoff | Applepay specific Mobile Pay Addendum for Forge | Mobile | C1 | 5
AP08 | FI onboarding Requirements with CCUA | FI to engage with CCUA; 2 tickets to be created to C1 (1 from CCUA, 1 from FI) | Mobile | Client/CCUA
Applepay Info Collection
AP09 | Check CCUA Ticket for Required Info | Launch schedule; FI BIN range | Mobile | C1 | 0.1
AP10 | Create Dev Ops Ticket for Key / Meta-Data | Provide Team ID, Adam ID, TeamID.Bundle ID, URL for app launch | Mobile | C1 | 0.1
AP11 | Notify CCUA Key Exchange in Progress | Email CCUA of key exchange is in progress | Mobile | C1 | 0.1
AP12 | Provide CCUA with Key / Meta-Data | Provide CCUA with the Team ID, Adam ID, TeamID.Bundle, and the URL for the Mobile application launch | Mobile | C1 | 0.1
AP13 | Interac Confirms Key Successfully Uploaded to TSP | Email Interac for confirmation they are in receipt of key and uploaded to their internal system TSP | Mobile | Interac | 2
AP14 | Apple confirms Entitlement Config is done | This step is a must, prior to building the app | Mobile | Apple | 10
AP15 | Update Dev Ops Ticket | Give go-ahead to Dev Ops to enable Applepay | Mobile | C1 | 0.1
Configuration & Testing
AP16 | Enable Applepay in Forge
AP17 | Add Teamsite Data to UXP SCC | Tenant Configuration Setup | Mobile | C1 | 0.1
AP18 | Setup CXP Pages for CU | CXP pages to be used for applepay | Mobile | C1 | 0.1
AP19 | Build FE App & BE Config for CU (BETA) |  | Mobile | C1 | 0.1
AP20 | Add Test Users | Add all test users to test flight app | Mobile | C1 | 0.1
AP21 | QA Test and Bug Fixes | Mobile / QA internal testing | Mobile | C1
AP22 | Cursory Test (Provision Card Test) | BA internal testing | Mobile | C1 | 0.2 to 5
AP23 | QA Approval | Joint approval from Mobile, QA, and BA | Mobile | C1
AP24 | Bug Fixes and Interac Shakedown | Interac to perform shakedown, C1/Interac/Apple to work on fixes | Mobile | C1/Interac/Apple
AP25 | FI UAT Test and Signoff by FI & CCUA | FI to perform E2E testing and signoff | Mobile | Client/CCUA | 10 to 15
AP26 | Update Dev Ops Ticket |  | Mobile | C1 | 0.1
Release and Launch
AP27 | Submit App for Apple Approval | Submit app to Apple Store for approval | Mobile | Apple | 4 to 5
AP28 | Update Dev Ops Ticket |  | Mobile | C1 | 0.1
AP29 | Send Advance Implementation Notice | Send email to FI of implementation notice | Mobile | C1 | 0.1
AP30 | Production Launch Day | Production day activities (refer to implementation process guide) | Mobile | C1 | 1 to 2
AP31 | Provide 5 Business Day Warranty | Warranty period | Mobile | C1 | 5
AP32 | Update Confluence page | Update confluence and add FI to list of CU's with applepay | Mobile | C1 | 0.1
AP33 | Billing | Billing process | Mobile | C1 | 0.1
PWS Planning
PWS01 | Public Site As-is Audit & Content Strategy | Review current MD site and assess pages/items to retain | PWS | Client | 10
PWS02 | Forge Theme Variables Template | Complete Theme Variable Sheet | PWS | Client | 5
PWS03 | Granting Access to Experience Manager | Ensure CU security officer has setup users for CxP | PWS | Client | 1
PWS04 | Experience Manager Portal Setup | CU Portal has been created in CxP | PWS | C1 | 5
PWS05 | Site Design and Branding | Complete all design and branding items | PWS | Client | 10
PWS06 | Site Imagery & Wireframes | Complete all site images and wireframes | PWS | Client | 10
PWS Build & Content Creation
PWS07 | Content Creation | Create content for CxP | PWS | Client | 15
PWS08 | PWS Build | Buile Pages and added content | PWS | Client | 45
PWS09 | Beta URL Creation | Purchase SSL Certs, create subdomain etc.; to be managed by domain owner C1 or CU | PWS | Dev-Ops (or Client) | 10
PWS10 | Beta Pages Publishing | Publish content and pages for Beta PWS | PWS | Client | 5
PWS11 | Provide CU with Test Guideline | Provide CU with Testing and Bug Reporting Documents | PWS | C1 | 1
PWS12 | Beta Launch | Share Beta URL with the Beta testers | PWS | C1/Client | 1
PWS13 | Beta Testing (include fixes based on feedback) | Test PWS Beta site, log issues and implement fixes | PWS | Client | 20
PWS14 | Complete MDi Lite Tasks | Refer to MDi Lite timeline sheet | PWS | C1
PWS15 | Launch Prep & Client Support Handoff Workshop | Refer PWS launch handbook | PWS | C1/Client | 1
PWS16 | Communication for launch | Internal and external comms managed by CU team regarding the PWS launch | PWS | Client | 1
PWS17 | Go/No Go Decision | Go/No-Go call with all stakeholders for PWS Market Launch; | PWS | C1 | 1
PWS18 | Public Site Launch | PWS Market Launch; Refer to PWS Launch Runbook | PWS | C1 | 1
PWS19 | Post-Launch Handoff | Post-Launch Handoff at end of warranty; refer to template email | PWS | C1 | 10
Online Banking
OLB01 | CU Engaged |  | OLB | C1 | 15
OLB02 | ISO Spec Complete | Provide CU ISO Spec | OLB | C1
OLB03 | Confirm Interac Profile |  | OLB | C1
OLB04 | OLB Assets | Provide CU templates for assets | OLB | C1
OLB05 | OLB Preview Doc | Provide CU with OLB Preview Document | OLB | C1
OLB06 | Feature Gap Analysis, Turn off Features | Complete Feature Gap Analysis | OLB | C1
OLB07 | Receive Assets and Test Accounts | Receive Assets and Test Accounts | OLB | C1 | 10
OLB08 | CU BH Changes | CU completest changes required for BH | OLB | Client | 120
OLB09 | Build BH Connection | Setup connectivity to BH | OLB | C1
OLB10 | Test BH Connection | Test connectivity to BH | OLB | C1/Client | 2
Additional Features go here
OLB11 | Import Last MPI Config to Forge |  | OLB | C1 | 0.5
OLB12 | ISO Testing in local Dev (Testing Login details against MD) | Tests to ensure ISO changes are complete | OLB | C1 | 0.1
OLB13 | Create Tenant in all Environments | Create CU as a tenant in all environments | OLB | C1 | 3
OLB14 | Create DB |  | OLB | C1
OLB15 | Tenant Config |  | OLB | C1
OLB16 | Configurations |  | OLB | C1 | 0.2
OLB17 | Conifig Oauth (white list) |  | OLB | C1
OLB18 | Create / Update Repo |  | OLB | C1
OLB19 | Seeding Config |  | OLB | C1
OLB20 | Backend Config E-transfer |  | OLB | C1
OLB21 | Config RDC |  | OLB | C1
OLB22 | Config Bill Pay |  | OLB | C1
OLB23 | Config A2A |  | OLB | C1
OLB24 | Config Auth |  | OLB | C1
OLB25 | MDI Integration |  | OLB | C1
OLB26 | Configure additional non-mobile features |  | OLB | C1
OLB27 | Deploy KDC/OAuth |  | OLB | C1
OLB28 | Smoke Test (BE API Tests for ISO) |  | OLB | C1 | 0.2
OLB29 | Bug Triage from API Testing |  | OLB | C1 | 0.2
OLB30 | Setup CxP Portal | Setup CxP Portal | OLB | C1 | 0.1
OLB31 | Add Online Banking Page | Develop Pages in OLB UAT Portal | OLB | C1 | 0.5
OLB32 | Supply Theming to Portal | Deploy Theming changes to OLB pages | OLB | C1 | 8
OLB33 | Internal QA in UAT | Test OLB UAT | OLB | C1 | 3
OLB34 | Bug Triage | Triage of reported issues from QA | OLB | C1 | 1
OLB35 | Bug Fixing |  | OLB | C1 | 15
OLB36 | QA Sign-off | QA signs off on UAT OLB Build | OLB | C1 | 1
OLB37 | Seeding Test in QA | Pre-seeding testing from BH QA env.; flat file required | OLB | C1/Client | 5
OLB38 | Seeding Test in PROD | Pre-seeding testing from BH PROD env.; flat file required | OLB | C1/Client | 5
OLB39 | OLB UAT Go/No-GO | GO/No-Go call with all stakeholders for OLB UAT | OLB | C1 | 1
OLB40 | Give to CU for UAT | Provide URL for OLB UAT to CU | OLB | C1 | 0.2
OLB41 | UAT Testing | CU testing of OLB in UAT | OLB | Client | 10
OLB42 | UAT Sign off | Client Signs off on all UAT reported bugs and timelines for fixes | OLB | Client | 10
OLB43 | Move Portal to Editorial | Copy pages from UAT to Editorial with edits based on UAT Testing | OLB | C1 | 5
OLB44 | Publish Pages | Publish all pages in Editorial | OLB | C1 | 0.2
OLB45 | Deploy all config from UAT to PROD |  | OLB | C1
OLB46 | UGX for PROD |  | OLB | C1 | 5
OLB47 | Seeding in PROD |  | OLB | C1
OLB48 | Beta F & F Launch | Share Beta URL with the Beta testers | OLB | C1/Client | 1
OLB49 | Beta Testing | Test OLB Beta site, log issues and implement fixes | OLB | C1 | 20
OLB50 | Bug Fixing | Resolve any pending bugs | OLB | C1 | 5
OLB51 | Data Seeding | Data seeding (should end 1 week before Market Launch) | OLB | C1 | TBD
OLB52 | Launch Prep & Client Support Handoff Workshop | OLB Market Launch; Refer to OLB Launch Runbook | OLB | C1 | 1
OLB53 | Go/No Go Decision | Go/No-Go call with all stakeholders for OLB Market Launch | OLB | C1/Client | 1
OLB54 | PROD Testing | Test OLB Beta site, log issues and implement fixes | OLB | C1 | 3
OLB55 | OLB Launch (steps listed in the launch runbook) | OLB Market Launch; Refer to OLB Launch Runbook | OLB | C1 | 1
OLB56 | Post-Launch Handoff | Post-Launch Handoff at end of warranty; refer to template email | OLB | C1 | 1
OLB57 | Communication for MDi Lite Decommissioning | Internal and external comms managed by CU team regarding changes to MDi Lite | OLB | Client | 1
OLB58 | Decommission MDi Lite |  | OLB | C1/Client
Mobile App
MA01 | JIRA Setup | Setup JIRA Ticket | Mobile | C1 | 0.1
MA02 | CU Engaged |  | Mobile | C1 | 15
MA03 | ISO Spec | Provide CU ISO Spec | Mobile | C1
MA04 | Config Interac Profile |  | Mobile | C1
MA05 | Mobile App Assets | Provide CU templates for assets | Mobile | C1
MA06 | Mobile App Tour Doc | Provide CU with OLB Preview Document | Mobile | C1
MA07 | Feature Gap Analysis | Complete Feature Gap Analysis | Mobile | C1
MA08 | Receive Assets and Test Accounts | Receive Assets and Test Accounts | Mobile | C1 | 15
MA09 | CU BH Changes | CU completest changes required for BH | Mobile | Client | 120
MA10 | Build BH Connection | Setup connectivity to BH | Mobile | C1 | 2
MA11 | Test BH Connection | Test connectivity to BH | Mobile | C1/Client | 2
MA12 | Import Last MPI Config to Forge |  | Mobile | C1 | 0.5
MA13 | ISO Testing in local Dev (Testing Login details against MD) | Tests to ensure ISO changes are complete | Mobile | C1 | 0.5
MA14 | Shape Setup |  | Mobile | C1 | 3
MA15 | Identify Core Build Tags for App |  | Mobile | C1 | 0.1
MA16 | Create Tenant in all environments | Create CU as a tenant in all environments | Mobile | C1 | 2
MA17 | Create DB |  | Mobile | C1
MA18 | Tenant Config |  | Mobile | C1
MA19 | Configurations |  | Mobile | C1 | 0.3
MA20 | Conifig Oauth |  | Mobile | C1
MA21 | Create / Update Repo |  | Mobile | C1
MA22 | Seeding Config |  | Mobile | C1
MA23 | Backend Config E-transfer |  | Mobile | C1
MA24 | Config RDC |  | Mobile | C1
MA25 | Config Bill Pay |  | Mobile | C1
MA26 | Config A2A |  | Mobile | C1
MA27 | Config Auth |  | Mobile | C1
MA28 | Deploy KDC/OAuth |  | Mobile | C1
MA29 | Smoke Test (BE API Tests for ISO) |  | Mobile | C1 | 0.3
MA30 | Bug Triage from API Testing |  | Mobile | C1 | 0.3
MA31 | Clone CxP Portal | Clone CxP Portal for Mobile | Mobile | C1 | 0.1
MA32 | Update CxP Portal |  | Mobile | C1 | 0.5
MA33 | Import Portal to every environment |  | Mobile | C1
MA34 | Update Custom Text |  | Mobile | C1
MA35 | Sync Certs |  | Mobile | C1 | 0.3
MA36 | Update iOS Certs |  | Mobile | C1
MA37 | AWS Notfication Setup |  | Mobile | C1 | 0.1
MA38 | Update Repo with Assets |  | Mobile | C1 | 0.2
MA39 | Apply Theming (Native) |  | Mobile | C1 | 5
MA40 | Apply Theming (Webviews and OAuth) |  | Mobile | C1 | 0.1
MA41 | Freeze Code Changes |  | Mobile | C1 | 0.1
MA42 | Build App | Build apps in Shared-Test or UAT? | Mobile | C1 | 0.1
MA43 | Internal Manual Testing | Manual testing of the app builds | Mobile | C1 | 1.5
MA44 | Bug Triage and Fixing | Debug and Triage of the Mobile App | Mobile | C1/Client | 15
MA45 | Create iOS and Android Projects (Test Flight and Google Play Beta) | Create project for iOS and Android for app stores | Mobile | C1 | 0.5
MA46 | QA Sign-off | QA teams signs off on testing | Mobile | C1 | 0.1
MA47 | Mobile UAT Go/No-GO | GO/No-Go call with all stakeholders for Mobile UAT | Mobile | C1 | 1
MA48 | Deploy Apps to CU for UAT | Deploy UAT mobile build for testing | Mobile | C1 | 0.2
MA49 | UAT Testing | CU testing of OLB in UAT | Mobile | Client | 10
MA50 | UAT Sign off | CU Signs off on all UAT reported bugs and timelines for fixes | Mobile | Client | 10
MA51 | Receive App Store / Play Store Contents | CU provides content for iOS and Android app store listing | Mobile | Client | 0.3
MA52 | Build App for PROD | Build Apps in PROD | Mobile | C1 | 0.1
MA53 | Prod App Release - Friends and Family or Beta | Deploy App to App stores for doing Beta Launch | Mobile | C1 | 0.1
MA54 | App Store Approvals |  | Mobile | C1/Client | 1
MA55 | Mobile App Beta Launch | Share Beta App with the Beta testers | Mobile | C1/Client | 1
MA56 | Beta Testing (include fixes based on feedback) | Integrate feedback from Beta testing | Mobile | C1/Client | 20
MA57 | Beta Feedback | Provide feedback and bug reports based on Beta testing | Mobile | Client | 5
MA58 | Go/No Go Decision | Go/No-Go call with all stakeholders for OLB Market Launch | Mobile | C1/Client | 1
MA59 | PROD Testing | Final checks of the PROD app before launch | Mobile | Client | 3
MA60 | Data Seeding |  | Mobile | C1 | TBD
MA61 | Launch Prep & Client Support Handoff Workshop |  | Mobile | C1 | 1
MA62 | Prod App Release - Market Launch |  | Mobile | C1 | 1
MA63 | Follow steps listed in the launch runbook |  | Mobile | C1 | 5
MA64 | Post-Launch Handoff |  | Mobile | C1 | 1
MA65 | Communication for Mobile App Decommissioning |  | Mobile | Client | 1
MA66 | Decommission MDi Mobile |  | Mobile | C1/Client | 1
Insert new rows ABOVE this one
2SV
Collabria
Note on F27: Best Case 0.2 day Worst case 2 weeks (bug triage and fixes)
Note on F47: Best Case is 0.2 day Worst Case with bug triage and fixes is 5 days (Interac 2 days, Apple 4 days)
Note on B56: Applepay release can only happen every 1st & 3rd Tues of each month