## Slide 1
Date: March 31, 2022
Digital Program Releases
Executive Summary
Digital Program

## Slide 2
VCOO Assumptions
Requirements gathering sessions are not required scope is established
No new data procurement is required; Beta will be built into the R1.1 version
The required APIs, which are currently employed in Beta, do not require development
VCOO instance of Spotlight needs to be incorporated into the current production Spotlight
There are 6 development Sprints
VCOO Beta will continue until formal business decision and readiness is confirmed
Notes: Action: Ahmed / confirm.

## Slide 3
2022
2022
Today
Apr
May
Jun
Jul
Aug
Sep
2022
Oct
5 days
0%
Aug 12 - Aug 18
Functional Testing
5 days
0%
Sep 19 - Sep 23
Performance Test
24 days
0%
Jul 20 - Aug 22
Viz Regression Testing
15 days
Apr 25 - May 13
Visualizer Upgrade to R1.1 (9.2.31)
0%
30 days
May 23 - Jul 1
VCOO Merge w/ R1.1
0%
10 days
Sep 5 - Sep 16
VCOO: Merge R1.1/Alerts/HF Regression
0%
5 days
0%
Oct 17 - Oct 21
Cotingency
10 days
Aug 22 - Sep 2
E2E Testing
0%
5 days
Sep 26 - Sep 30
Defect Fix & Retest
0%
4 days
Aug 16 - Aug 19
Functional Defect Re-testing
15 days
Aug 19 - Sep 8
Initial performance run
5 days
Oct 3 - Oct 7
Pen/BAT
10 days
Oct 3 - Oct 14
Pen Testing report
5 days
Oct 10 - Oct 14
Fixes and Retest (Perf, Pen, BAT)
2 days
Oct 17 - Oct 18
Run Book Dress Rehearsal
VCOO Go-Live (TBC)
Oct 24
R1.1 Go-Live
Jul 28
HF Build 1
Jul 1
HF Build 2
Jul 8
HF Build 3
Jul 15
Go No Go Decision
Oct 17
VCOO/Hotfix Build
Aug 2
VCOO/Hotfix Build
Aug 11
VCOO/Hotfix Build
Aug 18
VCOO Demo
Aug 9
VCOO/Hotfix Build (TBC)
Aug 25
VCOO Full Launch Proposed Plan
Temenos Confirmed
Temenos To Confirm
CWB Confirmed
CWB To Confirm
Notes: Add contingency 2 weeks
Shift r.1.1 to r1.2 after GL
Freeze period reduced to 1 week

## Slide 4
Upgrade & Merge Assumptions
Requirements gathering sessions are not required
An upgrade will not be required for the 20.07 streams

## Slide 5
2022
2022
Apr
May
Jun
Jul
Aug
Sep
2022
Today
Oct
Nov
Dec
30 days
0%
Aug 1 - Sep 9
Temenos: R1.1 to R1.2 Merge/Upgrade
12 days
0%
Jun 30 - Jul 15
R1.1 VCOO/HF
10 days
0%
Aug 1 - Aug 12
Regression for VCOO/HF
20 days
0%
Sep 12 - Oct 7
CWB Testing: R1.1 to R1.2 Merge/Upgrade
20 days
0%
Apr 18 - May 13
R1.1 Visualizer Upgrade
12 days
Jul 12 - Jul 27
Regression R1.1 Visualizer Upgrade
0%
10 days
May 16 - May 27
VCOO Merge with R1.1
0%
5 days
Jun 10 - Jun 16
Alerts Merge with R1.1
0%
20 days
Nov 14 - Dec 9
R1.1 Final Merge with R1.2
0%
R1.1/Alerts Go-Live
Jul 28
R1.1 Merge with R1.2 Start
Aug 1
R1.1 Fast Follower Go-Live (TBC)
Oct 31
R1.1 VCOO/HF Merge Go-Live
Aug 29
R1.1 to R1.2 Upgrade/Merge Complete
Sep 9
R1.1 Merged with Alerts
May 24
R1.1 Alerts Merged w/ VCOO/Hot Fix
Jul 15
Upgrade and Code Merge Proposed Plan
Temenos Confirmed
Temenos To Confirm
CWB Confirmed
CWB To Confirm