## Slide 1
Nov 28, 2022
VCOO/Hotfix 1 Readiness
Go/No-Go

## Slide 2
Agenda
Technical Readiness
Temenos
3rd Party
Mobile Apps
Business Readiness
Testing
Organizational Change Management
Support

## Slide 3
Technical Readiness
Temenos
VCOO/Infinity Prod Build*
T24 deployment planned
R1.1 Data Migration Readiness
Disaster Recovery for Prod
* Remaining required Critical and High defects.
CWB/3rd Party
Deployment plan/resources verified
Production env/connectivity verified
Production Deployment readiness:
  Celero (Doxim)
  C1
  OKTA
  Cloudflare
  Navaera*
  Twilio
  Mulesoft
  Helix
  BRIM
Mobile Apps
App submission artifacts (Description, Icons, and Videos)
App readiness and submission*
  Android
  Apple
Completed
Remediation
*Android and Apple submissions pending code finalization for binaries and submission
*Navaera will deploy on Dec 5 to Prod. Change is independent of Infinity.

## Slide 4
Business Readiness
Testing
Regression Testing#
Performance Testing completed+
Business/User Acceptance Testing^
Vulnerability Testing *
OCM
Communications, Internal & External
Support
BCSC – Branch support
Hypercare in place
Transition To Operations*
CWB/Temenos Support Model~
*Will be updated as required
~Support agreement awaiting finalization
Completed
Remediation
# Small Business and Combined user defects not included in this release.
+Outstanding performance defects TBD?
^ BAT test to be completed in VCOO/HF2 Go live. Shakedown test to be done for Hotfix 1 release.
* 2 Low defects to be addressed (60 – 90 day), and 3 Informational

## Slide 5
VCOO/Hotfix 1 - Outstanding Actions

## Slide 6
Stakeholder Approvals
Approved
      CWB/3rd Party
    Celero – Gerry W
    C1 – Gerry W
    OKTA – Tony F
    Cloudflare – Gerry W
    Helix – Gerry W
    Twilio – Gerry W
    Mulesoft – Alex/Andy
    BRIM – Gerry W
    Navaera – Gerry W
        Mobile Application Submission – Mark D
      Testing
    Functional Validation – Carmela
    End-to-End – Carmela
    Regression – Carmela
        Performance – Malik
        Penetration – Mike T
  People First – Trish/Stacy
    Training, Job Aides
    Communications
    HyperCare
      Temenos
        Infinity Prod Build complete
        Mobile Application Readiness
    Disaster Recovery for Prod
    T24 Deployment

## Slide 7
Go/No-Go Recommendation & Decision
Go – Subject to:
No-Go
  None
Decision (Azfar & Jeff)