## Data
Requirements Traceability
Project Name: |  | Digital Banking
Project Description:
Requirements | [5 empty] | Testing | [7 empty] | Defects
SOW ID | Requirements Description | Requirements Source | Requirement Type | Sprint # | User Story # | Test Description | Test Case | TEST | UAT | QA | PROD | PRE-PROD | NON-PROD | Defective | Defect ID | Defect Description | Req. Status
SOW10 | Authentication, Login Using Facial Recognition | SOW | Business |  | 10.1.1 |  | T0001 | Pass | [8 empty] | Complete
SOW108 | Login, Forgot Password | SOW | Business |  | 10.3.2 |  | T0003 | Fail | Pass | [5 empty] | D001 | Password length does not match | Partial Completion
SOW31 | Displays the registered phone number | SOW | Business |  | 12.2.5 |  | T0004 | Pass | [8 empty] | Complete
SOW112 | Load permissions->Dynamic Permissions and Entitlements | SOW | Non-Functional |  | 10.2.1 | [11 empty] | Not Started
|  |  | Functional | [13 empty] | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Status
Count of Req. Status | Requirement Type
Req. Status | (blank) | Business | Functional | Non-Functional
Not Started | 18 |  | 1 | 1
Partial Completion |  | 1
Complete |  | 2