Digital Transformation - Program Action and Issue Management Plan

Program Management Plan

## Purpose

The purpose of the Action and Issue Management Plan is to ensure that all issues are tracked and resolved, and all action items identified throughout the Program are performed in order to prevent delays to the Program.

## Scope and Assumptions

The scope entails actions and issues identified during the course of the Program that may affect the Program’ scope, budget and schedule.

## Overview

An action is defined as something that needs to be performed in order to maintain the Program’ scope, budget and/or schedule.

An issue is defined as something that is impacting or has the potential to impact the success of the Program – including the achievement of planned tasks and deliverables assigned in the schedule per the time, resources, and quality expected.

If an action is not performed by the targeted timeframe and starts to impact the achievement of tasks assigned in the schedule per the time, resources, and quality expected, the action will be changed to an issue and tracked accordingly.

Any actions and issues identified during the course of the Program that may affect its success are to be communicated to the Program Manager in a timely manner and added to the Program Issue/Action Log for tracking.

# Roles and Responsibilities

The following Key roles and responsibilities are defined in supporting the Action and Issue Management process.

| Role | Key Responsibilities |
| --- | --- |
| Program Manager | - Ensure the Action and Issue Management process is followed; - Ensure an Action/Issue Owner is assigned; and - Ensure actions and issues are resolved. |
| Program Owners | - Approve action/issue solutions |
| Action/Issue Owner | - Define solutions to address action items or issues; and - Responsible for resolution and implementation |
| Program Team Member | - Identify action items and/or issues as they arise; and - Participate as required in resolution of action items and issues. |

# Action and Issue Management Process

The Action and Issue Management process consists of six phases. These phases will cover the entire process of managing action items and issues throughout the Program. The following diagram outlines the high level process phases.

## Phase 1 - Identification

Action items and issues can be identified by any Program team member and must be reported to the Program Manager immediately. They can arise from a number of sources such as various Program meetings, during task activities, from a known or unknown risk that has occurred, etc.

The following tasks are performed during the Identification phase:

    - The Program Manager or Program Team Member will log the action items and issues in the Program Issue/Action log.

## Phase 2 - Analysis

The following tasks are performed during the Analysis phase:

    - The Program Manager will analyze the action or issue to determine the relevance of it to the Program;

    - The Program Manager will identify the date by which resolution is required to minimize impacts to the Program;

    - The Program Manager will assign an Action/Issue Owner and transfer the action/issue to the Action/Issue Owner;

- The Action/Issue Owner will work with the team members to identify a plan to address the action or issue. For complex actions or issues this may involve an Action/Issue Resolution Plan with possible options that can address the action or issue;

    - The Action/Issue Owner will document the plan to include a description of the tasks to be performed, the estimated dates, resources, any additional hardware/software, estimated costs, etc.;

    - The Action/Issue Owner will present the plan to the Program Manager;

    - The Program Manager (or delegate) will update the action/issue in the Program log accordingly.

## Phase 3 - Approval

The following tasks are performed during the Approval phase:

    - If the plan fits within the current scope, schedule and budget, then the Program Manager can approve the plan, if it does not then the Program Manager and Action/Issue Owner (if required) will review the plan with the Program Owner and the Program Owner will be required to approve the Action/Issue Resolution Plan;

    - The Program Manager will complete a Program Change Request if there are any changes to the scope, schedule or budget and have the Program Owner or appropriate signing authority, signoff the Program Change Request;

    - The Program Manager (or delegate) will update the action/issue in the Program log accordingly.

    - The Program Manager will inform the Action/Issue Owner of the approval.

## Phase 4 - Resolution

The following tasks are performed during the Resolution phase:

    - The Program Manager will secure resources as per the action plan;

    - The Program Manager will confirm dates with resources and Action/Issue Owner;

    - The  Action/Issue Owner will coordinate completion of activities per the action plan;

    - The  Action/Issue Owner will provide status updates to the Program Manager;

    - The Action/Issue Owner will notify the Program Manager when complete; and

    - The Program Manager (or delegate) will update the action/issue in the Program log accordingly.

## Phase 5 - Completion

The following tasks are performed during the Completion phase:

    - The Program Manager will validate that the resolution is complete;

    - The Program Manager will get agreement from the Program Owners (if required) to close actions or issues once they have been resolved; and

    - The Program Manager will update the Program Issue/Action log to a Status of Closed, the ‘Date Closed’, Progress Status of “Completed” and comment summary outlining why the action or issue is being closed.

## Phase 6 – Monitoring and Reporting

The following tasks are performed during the Monitoring and Reporting phase:

    - The Action/Issue Owner will provide status updates of activities during the Planning and Resolution phases;

    - The Program Manager will review all active/open actions and issues at team status meetings;

    - The Program Manager is responsible to track the status of all Program level issues and actions, including management of required escalations, extension of due dates, budget/schedule/quality impacts that require mitigation or re-planning, etc.; and

    - The Program Manager summarizes and reports on key Program actions and issues to the Program Owners, who will then present to the Executive Sponsors and Executive Steering Committee as needed.

The following outlines the tolerance levels to be used in tracing action and issue status, including status reporting:

Tolerance Scale for Action, Issue, and Spotlight Status Reporting