Digital Transformation Program

Program Change Control Plan

Contents

1.	Introduction	3

Purpose	3

Scope and Assumptions	3

Overview	3

2.	Plan Roles & Responsibilities	3

Individual Roles	4

Executive Sponsor(s)	4

Program Owners	4

Program Manager	4

Team, Board, Committee Roles	5

Program Change Control Board (if applicable)	5

Program Executive Steering Committee (if applicable)	5

Other Support	6

3.	Program Change Control Process	6

Program Change Request (PCR) Identification	6

PCR Assessment	6

PCR Review	7

PCR Approval	7

Individual PCR Approval or Rejection: No Impact	7

Individual PCR Approve or Reject – Cost Impact Outside of Budget	8

PCR Formal Sign-Off	8

PCR Implementation	8

4.	Program Change Control Escalation Process	8

5.	Program Change Control Process Monitoring	9

6.	Closure and sustainment	9

7.	Glossary	9

8.	Appendix A: PCR Template	9

# Introduction

## Purpose

The objective of the Program Change Control Plan is to provide the program with a systematic program change control approach, comprised of processes, procedures and templates, to manage requests for change to Program deliverables and baselines.

## Scope and Assumptions

The scope of this plan is to:

- Define, develop, and implement the Program Change Control Process.

- Define, develop, and implement the required templates and deliverables listed in Appendix A, which support the delivery of the Program Change Control Process.

## Overview

The purpose of the Program Change Control Plan is:

“Control of change means the assessment of the impact of potential changes, their importance, costs, and judgmental decisions by management on whether to include them or not in the Program. The purpose of the Program Change Control Plan is to set out the methods and procedures to handle all changes and impacts affecting the Program system implementation scope, which includes:

- Resources, costs, and timing.

- Scope, deliverables, product, and process quality.”

This plan will provide clarity on the roles, responsibilities, and processes required to support the delivery of this Program Change Control Plan.

This plan will standardize upon the terms and acronyms as follows: Program Change Request (PCR) and Program Change Control Board (PCCB).  These terms are synonymous with the following terms used in the Program Management Plan: Change Request (CR), CR, Program CR, and Change Control Board.  References to the roles and responsibilities defined in the Program Management Plan will use these standard terms.

# Plan Roles & Responsibilities

The following section outlines the key roles and responsibilities associated with this Program Change Control Plan.

## Individual Roles

### Executive Sponsor(s)

The following are the key change control responsibilities for the Executive Sponsor(s):

- Act as Chair of the Executive Steering Committee;

- Meet regularly with the Program Owner(s) to review and approve or reject PCRs;

- Approve individual PCRs within the approved authorized limit;

- Facilitate escalations of PCRs to the Executive Steering Committee where the Executive Sponsor(s)/Program Owner(s) do(es) not agree with the Program Change Control Board recommendations; and

- For any PCRs where the forecasted budget exceeds the approved Capital or NIE budget available, review and approve if the amount is within the Executive Sponsor(s)’s approval limit.

- For any PCRs where the forecasted budget exceeds the approved Capital or NIE budget available and the amount is above the Executive Sponsor(s)’s approval limit, the Executive Sponsor(s) reviews the Budget Adjustment Request with the CEO and provides back email or signature approval to the Program Manager.

### Program Owners

The following are the key change control responsibilities for the Program Owners:

- Act as Chair of the Program Change Control Board (PCCB);

- Meet regularly with the Executive Sponsors to provide Program updates including the review of PCRs and the Program Status Report. The Program Owners (or delegate) will record pertinent action items resulting from these meeting in ServiceNow PPM for the Program;

- With support from the Program Manager, provide the necessary details to complete status reporting related to PCRs to the Board of Directors, Executive Sponsor, and Program Executive Steering Committee;

- Approve individual PCRs within the approved authorized limit;

- Review and approve PCRs with no cost or impact to the approved schedule.  At the discretion of the Program Owner, PCRs with no cost or impact may be presented to the Program Change Control Board for its recommendation;

- For any PCRs where the forecasted budget exceeds the approved Capital or NIE budget available; review the Budget Adjustment Request with the Executive Sponsor; and

- Facilitate escalations to the Executive Sponsor.

### Program Manager

The following are the key change control responsibilities for the Program Manager:

- No authority to approve PCRs;

- Assigned full responsibility for facilitating or executing the Program Change Control Process to officially provide new Program requirements that impact time, cost, quality, resource, and/or scope;

- Assists with estimating and scheduling change against the existing baseline.

- Accepts, logs, and tracks PCRs;

- Responsible for coordinating Program Owners and/or Executive Steering Committee reviews and authorization of PCRs;

- Implement and manage the Program Change Control Process, including the implementation of controls to ensure the appropriate authority provides approval for all changes to agreed Program costs;

- Ensure the Program Change Control Process defined in this plan are being practiced and managed within the Program and specifically by the responsible team members identified.;

- Complete a Budget Adjustment Request, for any PCRs where the forecasted budget exceeds the approved Capital or NIE budget available and review with the Program Owner;

- Provide notification of any Budget Adjustment Requests to the Manager, PSC Governance; and

- Provide notification of any approved Budget Adjustment Requests to the Manager, PSC Governance and Finance.

## Team, Board, Committee Roles

### Program Change Control Board (if applicable)

The following are the key change control responsibilities of the Program Change Control Board:

- Review and recommend acceptance or rejection of PCRs for final approval by the Program Owners, Executive Sponsors, and/or Program Executive Steering Committee, ensuring the changes align with the business needs of CWB;

- Review, analyze, and accept or reject new PCRs where the effort to complete the impact assessment will exceed 5 days;

- Review of PCRs approved for evaluation to ensure appropriate actions have been taken; and

- Meet bi-weekly or more frequently to address PCRs that are critical or urgent.

### Program Executive Steering Committee (if applicable)

The following are the key change control responsibilities of the Program Executive Steering Committee:

- Establish Program authority levels, thresholds and limitations for changes in scope or deliverables;

- Review and approve or reject all PCRs:

  - That exceeds the authority levels of the Executive Sponsors;

  - Where no agreement could be reached by the Program Change Control Board;

  - Where the Executive Sponsors or Program Owners do not agree with the recommendations coming from the PCCB;

- Review the CRs in the Program Status Report to remain informed and to identify any emerging risks resulting from changes; and

- Meetings are bi-weekly or more frequently to address PCRs that are critical or urgent.

The members of the Program Executive Steering Committee are listed in the Terms of Reference of the Digital Transformation Program’s Executive Steering Committee.

## Other Support

The Digital Partners and other resources may be required to support the Program change control activity.

- A Digital Partner’s PCR may be used to identify the change and associated costs of the change.

- All Digital Partner’s PCR’s will follow the same process for review and approval as outlined below.

# Program Change Control Process

The following provides a high level over-view of the Program Change Control Process.   The detailed process is defined in the following sections.

Figure 3-1:   High Level Program Change Control Process

## Program Change Request (PCR) Identification

- If the Program Manager has been provided with information for a Program Change Request (PCR), the Program Manager will review and action the necessary Program Change Request Form.

- The Program Manager adds the item to ServiceNow PPM for the Program and informs the Program Team of the PCR investigation/assessment.

## PCR Assessment

- A PCR Impact Assessment is conducted by the Program Team to identify impacts and resources.

- If it is anticipated that the PCR Impact Assessment will take more than a day of effort to complete and there is a cost associated with this effort, a PCR Evaluation will be completed to provide an estimate of the number of hours or costs associated with the activities to create a PCR Impact Assessment that will require the approval of the Program Owners.

- Once the assessment has been completed, the PCR is distributed for review and discussion at the next Program Change Control Board meeting.

## PCR Review

- The PCCB reviews the PCR and provides recommendation. The Program Manager reviews the PCR and the PCCB’s recommendations with the Program Owner.

- If approved by the Program Owners, the PCR is then submitted for review and approval of the Executive Sponsors/Steering Committee. If the Executive Sponsors/Steering Committee agrees with the PCCB recommendation to move forward with the PCR, it will move forward to the PCR Approval process.

- If the Program Owners or Executive Sponsors do not agree with the PCCB recommendation, the PCR is then presented at the Program Steering Committee where a final decision is made.

- If the Program Executive Steering Committee agrees on the PCCB recommendation to move forward with the PCR, it will move forward to the PCR Approval process.

- The Program Manager captures the meeting minutes for the PCCB meeting.

- The Program Manager updates the PCR. ServiceNow PPM is also updated.

## PCR Approval

  - The Program Manager will coordinate with the Program Owners on the appropriate PCR Approval path, based upon the PCR total cost, and other considerations.

  - The Program Manager updates the appropriate sections of PCR. ServiceNow PPM is also updated.

### Individual PCR Approval or Rejection: No Impact

If the PCR has no cost impacts or changes that would result to the existing program baseline schedule or deliverables:

  - The Program Owners will review the completed PCR impact assessments and provide a decision to delay, accept or reject PCRs.

  - The Program Owners will communicate the decision to the PCCB.

    - If rejected, the PCR decision is recorded in the PCR and ServiceNow PPM.  All activities on the PCR will either cease at this point or further follow-up is needed.

    - If accepted, the PCR moves to PCR Formal Sign-Off and then PCR Implementation.

### Individual PCR Approve or Reject – Cost Impact Outside of Budget

If the forecasted budget exceeds the approved Capital or NIE budget available, the Budget Adjustment Request Process is followed to obtain approval for the budget adjustment.

## PCR Formal Sign-Off

- After the Program Change Control Process is complete, and the final decision on the PCR is made, the Program Manager will coordinate the delivery of a final copy to the Program Owners, and Executive Sponsors for formal (written or electronic) signatures to be captured in the PCR.  The scanned copy of the signed PCR will be stored in PDF format with the final electronic copy which will be stored in in MS Word format.  ServiceNow PPM will also be updated.

## PCR Implementation

- Approved PCRs are implemented when the Program Manager communicates the PCR approval and directs the Program team to move forward with the adjustments of the Program deliverables, documentation, schedules, and budget to the extent required and defined within the PCR.

- The Program Manager will track the tasks/deliverables of the PCR at the summary level to ensure visibility and alignment of the teams to deliver the change.

# Program Change Control Escalation Process

Issues with the Program Change Control Process or with the management of a specific PCR should be raised following the escalation path defined in Figure 4-1.  Once the issue is raised to a role, that role will own it until it is addressed or escalate it as required and will be tracked in the Program issue log.

Project Manager

Program Manager

Program Owners

Program Change Control Board (PCCB)

Executive Sponsors

Executive Steering Committee

Figure 4-1:   Program Change Control Escalation Process

# Program Change Control Process Monitoring

The Program Manager will summarize the weekly/monthly activity of PCR activities and ServiceNow PPM to identify trends and process improvement opportunities.

# Closure and sustainment

All documents and templates related to the Program Change Control Process are stored on the Program SharePoint site, following the practices established for the Program.  The templates will be updated as required throughout the Program.

They will be reviewed with, and handed over to the post-sustainment Operational Team Owners, as part of the Program’s transition to operations processes.

# Glossary

| Item | Description |
| --- | --- |
| Program Change Request (PCR) | A request made to the Program to change Program scope, schedule or budget |
| Program Change Control Board (PCCB)(if applicable) | A governance board that reviews and provides recommendations on PCRs |
| PCR Evaluation | A PCR Evaluation is an estimate of the number of hours or costs associated with the activities to create a PCR Impact Assessment |
| PCR Impact Assessment | A PCR Impact Assessment is an estimate of the deliverables, costs, resources, and schedule required to deliver the change as requested during the Program and to support it in Operations |

# Appendix A: PCR Template

The following is the link to the Program Change Request Form.

Program Change Request Form