Project or Project Phase Closure Report

Digital & Payments Program

April 10, 2025

General Information

| Project Name | Digital & Payments Program |
| --- | --- |
| Project Manager | Jaime Hart, Dino Noce, Fusi Olateru, Jacquie Davis |
| Project Owner | Jason Bond, Stacy Schmidt |
| Project Sponsor | Jeff Wright, Cory Gould |

Document Development History

Build Status:

| Version | Date | Author | Reason | Sections |
| --- | --- | --- | --- | --- |
| 1.0 | 10-04-2025 | Jaime Hart/ Jacquie | Initial Release | All |

Contents

Project Manager’s Report	4

Review of Project <or Project Phase> Objectives	5

Scope	5

Time	5

Cost	6

Financial Cost Benefit Analysis	6

Enabled or Realized Benefits	7

Lessons Learned	8

Issues That Occurred	8

What Worked Well	9

Transition Items	9

Sign-off	10

The purpose of the Project Closure Report is to review how the project performed against its objectives, schedule, cost, benefits realized, and lessons learned.

# Project Manager’s Report <Jaime/ Jacquie to complete or need direction>

Text…

**Blue text is included for illustrative purposes and must be removed before finalizing the document

Provide a summary of how the project performed and the deliverables it achieved.  For example:

The project achieved its objective of improving the end-user experience and expanding the functional capability and utility of the existing XX Portal application that has been established and incrementally evolved through earlier releases.  This release included refreshing the look and feel of the user interface and adding document management features among other functional enhancements to increase the utility of the system for XYZ industrial accounts and its Key Accounts team.

The implementation phase was completed with the following deliverables:

- XX Release 6.0 SIT Release

- XX Connects Release 6.

- User Acceptance Test Release

- XX Connects Release 6.0 Production Release

- XX Connects Release 6.0

- Implemented Production System

- End Project Report

This project (or this project phase) started on May 9, 2016 and finished on October 28, 2016, with the delivery of Post Go-Live Release 6.1 into production and the end project report by October 28; 4 weeks beyond its baseline end date.  The time and materials project was also completed at 32.5% over its baseline budget but within 3% of its approved budget (set out by change addendum 01).  The variance reasons were data quality improvement support that was added during the UAT phase and functional enhancements that were implemented during the UAT and post-go-live support phases.

In reviewing the project issues and receiving AB key stakeholder feedback, the lessons learned for future similar projects were:

- If a major scope change occurs, collaboratively issue an updated design specification.

- Develop a matrix of statuses and state change triggers in the requirements or design phase.

- Consider the segregation of SharePoint applications and define memory quotas for applications.

- Weekly sprints with sprint demos encouraged early client feedback and collaboration.

- Established, compressive .Net application code framework improved productivity.

- Jointly accessible incident log was critical to effective collaboration throughout the testing and PGLS phases.

Submitted by: 	<Project manager Name(s)>

Date Submitted:	<Date>

# Review of Project Objectives

## The primary objective of the Digital and Payments Program is to provide our clients with an enhanced digital banking experience. This includes the development of a digital onboarding platform (DCO), the modernization of digital self-servicing channels for personal and small business clients (cwb.digital), and the integration of a new platform with EFT functionality.

## Scope

| Deliverable | Outcome |
| --- | --- |
| DCO | - Released the new Business In-branch DCO channel - Journey Manager upgraded to v22.4.5 - Journey Workspaces upgraded to v22.04.2 - Journey Analytics upgraded to v24.04 - Completed Accessibility changes for Both Business Self serve and Personal Self serve - Completed development and SIT testing (without Infinity integration) of Motive Compatibility project (including Motive authenticated path and remaining accessibility items). - Completed the Journey Analytics project in May and Operational maintenance/hotfix releases completed in July, August and September. |
| CBX | NEXT MVP1.1 production deployment and pilot client migrations NEXT MVP1.1FF production deployment and pilot client readiness |
| PSH | Deployed Pilot release into production - Completed upgrades and production release changes for PSH versions 1.1, FF & 1.2.1 - Completed development for PSH Version 1.2.2 - Completed training and user onboarding |
| PPJV | Completed review of historical requirements and re packaged these within a new Migration SOW with PPJV - Piloted an update weekly data extract from PPJV as part of Migration planning activities |
| Infinity | Temenos has completed development, including Me-2-Me functionality and Motive - CWB is currently in Functional testing, expecting to enter End-to-End testing by Oct 8 - Temenos has completed the migration development and is currently testing the migration |

## Time

This project has different streams like Environment, DCO, VCOO and Infinity Upgrade.

| Critical Milestone | Original Delivery Date | Approved Delivery Date | New and Actual End Date |
| --- | --- | --- | --- |
| Personal DCO - Business Go Live Completed | 2023-01-30 | 2023-01-30 | 2023-01-30 |
| Journey Manager Upgrade 1 of 2 - Business Go Live Completed | 2023-06-01 | 2023-06-01 | 2023-06-01 |
| R1.1 Fast Follower - Business Go Live Completed | 2023-07-28 | 2023-07-28 | 2023-07-28 |
| R1.2 CBx Pilot Go Live | 2024-01-26 | 2024-01-26 | 2024-01-26 |
| R1.2 CBx Pilot - Business Go Live Completed | 2024-02-14 | 2024-02-14 | 2024-02-14 |
| Journey Manager Upgrade 2 of 2 | 2024-03-17 | 2024-03-17 | 2024-03-17 |
| VCOO Go-live | 2024-04-30 | 2024-04-30 | 2024-04-30 |
| Digital Banking - Business Go Live Completed | 2024-06-03 | 2024-06-03 | 2024-06-03 |
| DCO Motive Authenticated Project Go-Live | 2024-06-13 | 2024-06-13 | 2024-06-13 |
| Infinity Upgrade Go-live | 2024-06-30 | 2024-06-30 | 2024-06-30 |
| Accessibility Production Deploy | 2024-07-06 | 2024-07-06 | 2024-07-06 |
| Project Closure | 2024-10-31 | 2024-10-31 | 2024-10-31 |

## Cost <Confirm splits with Jacquie>

Text..

Provide a report of how the project budget was utilized to fund the project activities. For example:

The project was completed 32.5% over its baseline time and materials budget and within 3% of its approved time and materials budget:

| Budget Item | Budget | Approved Budget | Estimate at Completion | Variance at Completion |
| --- | --- | --- | --- | --- |
| Detailed Functional and Technical Design | $0 | $0 | $5,873 | -$5,873 |
| Build and Unit Testing | $260,300 | $260,317 | $276,488 | -$16,171 |
| System and Integration Testing | $168,000 | $168,000 | $113,907 | $54,093 |
| Business User Acceptance Testing | $50,300 | $201,063 | $242,596 | -$41,532 |
| Cutover | $35,700 | $7,789 | $41,137 | -$33,348 |
| Project Closure and Handover | $3,200 | $31,131 | $6,973 | $24,158 |
| Total | $517,500 | $668,300 | $690,286 | -$21,986 |

### Financial Cost Benefit Analysis

The following is a summary of the Project cost benefit analysis. Full details are available in the PMO Cost Benefit Analysis spreadsheet on the project SharePoint.

| Measure | Result | CAP/NIE | Comment |
| --- | --- | --- | --- |
| Implementation Cost | $68,267MM | $64,294MM/ $3,973MM |  |
| Annual On-going Cost Summary (5-year view) | $7,911MM |  | From FY25 CBA, is this correct – If we’re moving to NBC systems, will this be applicable? |
| Additional Revenue & Cost Savings (5-year view) | $0 |  | From FY25 CBA, is this correct |
| ROI | N/A |  |  |
| Payback Period | N/A |  |  |

## FY25 Budget Tracker and FY25 Cost Benefit Analysis

## Benefits Realization Plan

The project benefits have been defined and kept up to date in the Project’s High Level Benefits Realization Plan

EFT was part of the Digital Program until FY24 with benefits defined separately in the High Level Benefits Realization Plan

All the benefits have been tracked in the BRAID log with the latest status here

- Benefits Handover

All benefits, including the EFT benefits were tracked until FY25 Q1. Some of them have been cancelled in light of the acquisition. All benefit reporting have been stopped as of FY25 Q1. Following benefits have been realized.

| Benefit Description | Status | Agreed Benefit Realization Date |
| --- | --- | --- |
| More efficient In-Branch onboarding providing clients a better client experience. Improve the time for clients to onboard from more than 45 minutes to less than 10 minutes. Measure the current time it takes to open an account (see CAPE research) vs the time it takes after implementation of DCO. | Benefit fully achieved | July 31, 2024 |
| Clients will be able to open subsequent accounts in Personal and Small Business via online banking | Benefit fully achieved | July 31, 2024 |

- Benefits-Related Lessons Learned <Confirm with Jacquie – Meet with program team>

< Also, please comment on any lessons learned that have been captured from the team about things that we did well and things that we could have done better in terms of benefits identification, enablement, tracking and realization>

# Lessons Learned

## Issues That Occurred – Work with Jacquie to fill rest columns

The issues that were raised in the lessons learned workshop at the end of the project were:

| Description | Category | Lesson Learned (Recommended Action Plan) | Project Stage | Lesson Learned By |
| --- | --- | --- | --- | --- |
| Technical issues have delayed delivery of the CR to SIT | Technology |  |  |  |
| Code Drop for Approx 9 items/BRDs March 08 delayed. Intellect to provide ETA for Code drop #3 | Process |  |  |  |
| Working with Program Leadership to determine new budget ask. This will depend on pending schedule from Intellect | Process |  |  |  |
| Working with Temenos and Intellect to resolve ongoing issues. Working with internal resources to try and manage capacity and OT requirements. T24 defects related to API. | Process |  |  |  |
| Elaborate on delivery schedule, acquire clarity on approach to identify concerns early. Continue to seek alternatives and opportunities to de-risk cross dependencies. Timeline for CBX FF continues to be impacted due to delivery dates not being met by Intellect Working with vendors to find opportunities to streamline processes to avoid schedule delays Program does not recommend accelerating the migration during the summer months. | Process |  |  |  |
| MVP1.2.2 - Finastra URL for Intellect dev/testing not working. URL was provide to Intellect on July 02. It did not work when tested. Raised with Finestra multiple times and escalated on July 15. Received revised URL on July 23. Still does not work. Escalated on July 25 again. Impact: Intellect timeline to complete / finalize their code and testing continue to slip due to these delays impacting program timelines. Finastra URL (exposed externally) is a hard dependency for Intellect. Next Steps: Finastra to provide working URL urgently | Technology |  |  |  |
| Defect closure rate has been slow, impacting schedule. | Process |  |  |  |

## What Worked Well – Work with Jacquie

| Description | Category | Lesson Learned (Recommended Action Plan) | Project Stage | Lesson Learned By |
| --- | --- | --- | --- | --- |
| Weekly Build Sprints and Demos – kept the team productive by setting weekly development tasks, demonstrated progress, and elicited client feedback on UI and functions ahead of the formal SIT and UAT phases | Process | Weekly sprints with sprint demos during the Build stage will demonstrate progress, address design/build issues early and encourage early client feedback and collaboration. | Executing | Project Manager |
| Pace of Sprint Demo and UAT Issue Turnaround – There was a fast pace of delivery of sprint functionality during Build and requested enhancement during UAT and PPGLS. This (as well as the pace of build sprints) was enabled by the reuse of the .Net Code Frameworks that had been put in-place by AE Connect Release 5 project. | Technology | An established, compressive .Net application code framework will improve sprint and testing incident resolution productivity of system data and likely reduce development and testing effort. | Executing | BA |
| Title – brief description | Choose an item. | Description of Action plan – (how we will ensure this lesson is repeated) | Choose an item. | Name of person who identified Lesson |

# Transition Items

The following are outstanding items identified during the project (Change Request, Risk, Issue, Action, Dependency, Decision, Expense Item) that have been transitioned to the Sustainment Team for follow up and resolution:

| Outstanding Items | Description | Sustainment Owner |
| --- | --- | --- |
| Choose an item. | <enter description of outstanding item and action required> | <Sustainment Owner Name> |
| Choose an item. |  |  |
| Choose an item. |  |  |

# Sign-off

Authorization to Complete Project:

Sign-off (either digital approval, email or penned signature below) is required from the following people to confirm that the project is now complete:

|  |  |  | or |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| <name, title> Executive Sponsor |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
|  |  |  | or |  |  |  |
| <name, title> Project Owner |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
|  |  |  | or |  |  |  |
| <name, title> Benefit Owner |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
| <name, title> Finance Representative |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
| <name, title> AVP, PMO Practice |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |
|  |  |  | or |  |  |  |
| <name, title> Sr. Manager, Planning & Analysis |  | Date |  | Digital Approval (Double Click and select ‘checked’ under Default) |  | Date |