## Revision Control
Digital Banking Project - Identity & Access Management Use Cases
Revision Control Form
Last Updated: 2021-03-25 (Steve Kelcher)
Document Version | Revision Date | Change Summary | Updated by | Reviewed By |  | Approved By
1.0 | 2021-02-15 | 1) Initial copy created | Steve Kelcher | Reinhardt Tonn Dino Noce |  | n/a - draft
1.1 | 2021-03-25 | 1) Updated to reflect Reinhardt's architectural feedback 2) Added scope management columns (3 product releases) 3) Completed product releae scope priorities 4) 2021-03-16: Traceability updates by Reinhardt 5) Removed forgotten password use cases (PROF-11 & 12) from Release 1 scope. | Steve Kelcher Reinhardt Tonn | Facilitated Review Adam Skoreyko Reinhardt Tonn Dino Noce Stacy Schmidt Ian Hicks | Self Directed Review Gerry Weber Dilshad Bhatti Neil Cory Sunil Prasha Faizan Ahmed Jerry Naraine Lisa Rindero Charlotte Morgan Chix Dela Luna Chantel Butt Allan Rib | Stacy Schmidt (2021-03-08) Jason Bond (2021-03-25) Pending Approvals: Christina Mullin

## Definitions
Use Case & Requirement Priority Definitions
Last Updated: 2021-02-25 (Steve Kelcher)
Requirement Priorities
1 - Mandatory | - "Must have" functionality - Minimum functionality required for release to early adopters - Failure to implement these features results in an inadequate solution, even for MVP (pilot) releases. | Minimum Viable Product
2 - Recommended | - "Best Practice" functionality - Minimum functionality required for release to general public - Failure to implement these features results in a solution that does not meet commonly accepted quality standards, and may significantly degrade the product. | Minimum Marketable Product
3 - Desirable | - "Nice-to-have" functionality - Represent features that exceed most user expectations of the product. - Failure to implement these features will result in minor degredations to the overall product quality. | Enhanced Product
4 - Future Initiative | - "Out of Scope" functionality - Worth considering or possibly essential to the success of future product releases. | Not relevant to specified product release

## Use Cases
Digital Banking Project - Identity & Access Management Use Cases
[6 empty] | * See "Definitions" tab page for prioritization criteria and definitions. |  |  | Traceability
Case ID | Summary | Category | Description/Requirement | Actors | Status | Priority R1 Business Release (MVP "Pilot Group") | Priority R1 Personal Release (MVP "Pilot Group") | Priority Future Bus./Pers. Releases (MMP & beyond) | Architecture | DBX SOWs | DBX User Stories (and other specs) | DCO Journey Flow (and other specs) | Okta Documentation (Arch. SDD) | T24 IRDs | Migration Strategy | Notes
AUTH-01 | Login to digital banking | 1 - Authentication | Digital banking users must be able to log into their digital banking platform using credentials stored in the Identity & Access Management system. | Digital banking user (all types) | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution confirmed | SOW 0 SOW 42 | 1.1.1 - Under review 1.1.6 - Approved | n/a | [TBD] | n/a | n/a
AUTH-02 | First login for migrated personal banking account owners | 1 - Authentication | Migrated personal account owners should be able to log into the Infinity personal banking platform the first time using the PAN & PAC combination they currently use to log into their Central1 online banking platform. | Personal banking user | Approved | Not Applicable | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.8 | n/a | n/a | n/a | [TBD] | [TBD] | Solution confirmed
AUTH-03 | First login for migrated business banking card holders | 1 - Authentication | Migrated business banking card holders should be able to log into the Infinity business banking platform the first time using the PAN & PAC combination they currently use to log into their Central1 online banking platform. | Business banking card holder | Approved | 1 - Mandatory (Must Have) | Not Applicable | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.8 | n/a | n/a | n/a | [TBD] | [TBD] | Solution in progress | Temenos working on technical solution design
AUTH-04 | First login for migrated business banking delegates | 1 - Authentication | Migrated business banking delegates should be able to log into the Infinity platform the first time using the delegate credentials they normally use to log into their Central1 online banking platform. | Business banking delegate | Approved | 2 - Recommended (Best Practice) | Not Applicable | 2 - Recommended (Best Practice) | Solution confirmed 3.5.3.8 Implementaiton Gap: Approval for Central-1 development required. Not likely to meet MVP deadline. | n/a | n/a | n/a | [TBD] | n/a | Solution in progress | Waiting for C1 estimates RISK: Central-1 has indicated the delegate API would be at risk for the May timeline. Propose for MVP that we migrate small businesses without delegates or that we manually create and invite delegates via spotlight. [2021-03-03]: Architectural solution confirmed. C1 completed estimates for delegate authentication hook.
AUTH-05 | First login MFA Enrollment | 1 - Authentication | All users should be able to enroll for one or more MFA factors during (or before) their first login to the digital banking platform | Digital banking user (all types) | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution Confirmed 3.5.3.9 | n/a | n/a | n/a | [TBD] | n/a | n/a | Specific solution still under consideration (options being compared). Dependencies on DCO and Okta capabilities apply.
AUTH-06 | Consolidated business accounts | 1 - Authentication | Business banking card holders should have a way to consolidate one or more business PANs under a single digital banking user interface. This would allow a user to view accounts from multiple businesses within a single digital banking session. | Business banking card holder | Approved | 4 - Future Initiative (out of scope) | Not Applicable | 2 - Recommended (Best Practice) | Solution in progress 3.5.3.8 | Unclear - possibly SOW 285 | Unclear - Possibly S15, Story 2 | n/a | n/a | [TBD] | Solution in progress | Architecture Feedback. The consolidation model in Infinity is company based, whereas it was user based with C1. There is a considerable difference here that is causing challenges with respect to migration. Path forward: Architecture has requested the capture of actual scenarios CWB needs to support, based on the data we have from C1 and T24. The scenarios are being captured by Steve and presented Feb 19th. Temenos will then review and confirm how their model will support each of these use cases. Architecture is supporting the discussion. Risk: there are some use cases that may not be well supported in this model and the business will need to make some choices on how to proceed.
AUTH-07 | Consolidated personal accounts | 1 - Authentication | Business banking card holders should have a way to consolidate a single personal PAN under a single digital banking user interface. This would allow the user to view their personal accounts in the same digital banking session as their business accounts. | Business banking card holder | Approved | 1 - Mandatory (Must Have) | Not Applicable | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.9 | Unclear - possibly SOW 285 | Unclear - Possibly S15, Story 2 | n/a | [TBD] | [TBD] | Solution confirmed | As of Mar 3, there are only 273 C1 users who have consolidated personal accounts but no other business accounts. GAP: this can only be done in spotlight.
LEG-01 | Legacy platform access restriction | 2 - Authentication (Legacy) | Migrated users must be prevented from logging into their legacy Central1 banking platforms. Legacy system access for such users must be disabled. | Migrated user | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution proposed 3.5.3.6 Implementation Gap: Approval for Central-1 development required. PCR being reviewed March 16th. | n/a | n/a | n/a | n/a | [TBD] | Solution confirmed | Waiting for C1 estimates RISK: estimate not yet received from C1, but they have indicated the effort is lower than the delegate API noted above.
LEG-02 | Legacy platform redirection | 2 - Authentication (Legacy) | Migrated users who attempt to log into their legacy Central1 banking platforms should be redirected to a suitable page allowing them to log in successfully to an appropriate Infinity banking channel. | Migrated user | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution proposed 3.5.3.6 PCR being reviewed March 16th. | Missing | Missing | n/a | [TBD] | [TBD] | Solution confirmed | Waiting for C1 estimates. Approved process flow currently outstanding (Steve).
LEG-03 | Legacy e-transfer deposit redirection | 2 - Authentication (Legacy) | Digital baking users who attempt to log in for the purpose of depositing an Interac e-transfer payment, should be redirected to the appropriate digital banking platform depending on whether or not they have been migrated to Infinity. | Digital banking user (all types) | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution proposed Implementation Gap: Infinity dev work required, Interac configuration, Central-1 estimate/development required. Use cases documented solution discussions to start with Temenos. Needs to be scheduled. | Missing | Missing | n/a | [TBD] | [TBD] | Solution confirmed | TODO: CWB is looking at this internally to resolve challenge with Central-1
ONB-01 | Personal banking user name selection | 3 - Onboarding | Personal banking applicants (primary and co-applicants) should be able to specify an authentication user name other than their PAN. For example an e-mail address or nickname of their choosing. | Personal banking user | Approved | Not Applicable | 2 - Recommended (Best Practice) | 2 - Recommended (Best Practice) | Solution confirmed 3.5.3.4 | n/a | n/a | [TBD] | [TBD] | n/a | n/a
ONB-02 | Business banking user name selection | 3 - Onboarding | The primary applicant on a business banking application should be able to specify an authentication user name other than their PAN. For example an e-mail address or nickname of their choosing. Note: the primary applicant should not be able to choose user names for the other authorized signers or delegates on their application. | Business banking card holder | Approved | 2 - Recommended (Best Practice) | Not Applicable | 2 - Recommended (Best Practice) | Solution proposed 3.5.3.4 | n/a | n/a | [TBD] | [TBD] | n/a | n/a
ONB-03 | Onboarding new-to-bank personal banking relationship | 3 - Onboarding | A new-to-bank applicant wishes to start a personal banking relationship with CWB or Motive Financial. | New-to-bank applicant | Approved | Not Applicable | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.1 | Missing | Missing - auto enrollment | Missing - Spec updates required | [TBD] | [TBD] | n/a
ONB-04 | Onboarding new-to-bank business banking relationship | 3 - Onboarding | A new-to-bank applicant wishes to start a business banking relationship with CWB. | New-to-bank applicant | Approved | 1 - Mandatory (Must Have) | Not Applicable | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.2 | Missing | Missing - Add Virtual Company - Associate PAN - Associate signer - Associate delegate - Set entitlements | Missing - Spec updates required | [TBD] | [TBD] | n/a
ONB-05 | Onboarding new personal banking product(s) for existing client - authenticated entry point | 3 - Onboarding | A) A current personal banking client wishes to add a new product to their existing PAN. B) The client initiates this request from an authenticated digital banking (Infinity) session. | Personal banking user | Approved | Not Applicable | 2 - Recommended (Best Practice) | 2 - Recommended (Best Practice) | Blocked 3.5.3.5 | Unclear - possibly SOW 136 | Unclear - Possibly S15, Story 1 | Missing - Spec updates required | n/a | [TBD] | n/a | Process mapping & journey flows not complete Architecture Feedback: DCO team must coordinate discussions on process flow and BA must document accordingly. General architecture pattern of integrating with Okta should be applied. We will weigh in on additional details once the flow and additional requirement details have been identified. Kendyl has planned an initial session on Feb 19th.
ONB-06 | Onboarding new personal banking product(s) for existing client - public entry point | 3 - Onboarding | A) A current personal banking client wishes to add a new product to their existing PAN. B) The client initiates this request from a public link (unauthenticated) on the CWB or Motive website. | Personal banking user | Approved | 4 - Future Initiative (out of scope) | 2 - Recommended (Best Practice) | 2 - Recommended (Best Practice) | Blocked 3.5.3.5 | n/a | n/a | Missing - Spec updates required | n/a | [TBD] | n/a | Process mapping & journey flows not complete Architecture Feedback: DCO team must coordinate discussions on process flow and BA must document accordingly. General architecture pattern of integrating with Okta should be applied. We will weigh in on additional details once the flow and additional requirement details have been identified. Kendyl has planned an initial session on Feb 19th.
ONB-07 | Onboarding new business banking product(s) for existing client - authenticated entry point | 3 - Onboarding | A) A current business banking client wishes to add a new product to their existing PAN. B) The client initiates this request from an authenticated digital banking (Infinity) session. | Business banking card holder | Approved | 4 - Future Initiative (out of scope) | Not Applicable | 2 - Recommended (Best Practice) | Blocked 3.5.3.5 | Unclear - possibly SOW 136 | Unclear - Possibly S15, Story 1 | Missing - Spec updates required | n/a | [TBD] | n/a | Process mapping & journey flows not complete Architecture Feedback: DCO team must coordinate discussions on process flow and BA must document accordingly. General architecture pattern of integrating with Okta should be applied. We will weigh in on additional details once the flow and additional requirement details have been identified. Kendyl has planned an initial session on Feb 19th.
ONB-08 | Onboarding new business banking product(s) for existing client - public entry point | 3 - Onboarding | A) A current business banking client wishes to add a new product to their existing PAN. B) The client initiates this request from a public link (unauthenticated) on the CWB or Motive website. | Business banking card holder | Approved | 4 - Future Initiative (out of scope) | Not Applicable | 2 - Recommended (Best Practice) | Blocked 3.5.3.5 | [TBD] - possibly n/a | [TBD] - possibly n/a | Missing - Spec updates required | n/a | [TBD] | n/a | Process mapping & journey flows not complete Architecture Feedback: DCO team must coordinate discussions on process flow and BA must document accordingly. General architecture pattern of integrating with Okta should be applied. We will weigh in on additional details once the flow and additional requirement details have been identified. Kendyl has planned an initial session on Feb 19th.
ONB-09 | Onboarding new business banking relationship for existing client - authenticated entry point | 3 - Onboarding | A) A current personal or business banking client wishes to start a new business banking relationship (new business CIF) with CWB. B) The client initiates this request from an authenticated digital banking (Infinity) session. | Personal banking user | Approved | 4 - Future Initiative (out of scope) | 4 - Future Initiative (out of scope) | 3 - Desirable (Nice To Have) | Blocked 3.5.3.5 | Missing | Missing - UI controls - Add Virtual Company - Associate PAN - Associate signer - Associate delegate - Set entitlements | Missing - Spec updates required | [TBD] | [TBD] | n/a | Process mapping & journey flows not complete Architecture Feedback: DCO team must coordinate discussions on process flow and BA must document accordingly. General architecture pattern of integrating with Okta should be applied. We will weigh in on additional details once the flow and additional requirement details have been identified. Kendyl has planned an initial session on Feb 19th.
ONB-10 | Onboarding new business banking relationship for existing client - public entry point | 3 - Onboarding | A) A current personal or business banking client wishes to start a new business banking relationship (new business CIF) with CWB. B) The client initiates this request from a public link (unauthenticated) on the CWB or Motive website. | Digital banking user (all types) | Approved | 4 - Future Initiative (out of scope) | 4 - Future Initiative (out of scope) | 3 - Desirable (Nice To Have) | Blocked 3.5.3.5 | Missing | Missing - Add Virtual Company - Associate PAN - Associate signer - Associate delegate - Set entitlements | Missing - Spec updates required | [TBD] | [TBD] | n/a | Process mapping & journey flows not complete Architecture Feedback: DCO team must coordinate discussions on process flow and BA must document accordingly. General architecture pattern of integrating with Okta should be applied. We will weigh in on additional details once the flow and additional requirement details have been identified. Kendyl has planned an initial session on Feb 19th.
ONB-11 | New client entitlements | 3 - Onboarding | Business banking card holders should be granted sufficient entitlements during the onboarding process, so that they may perform basic digital banking tasks, including further adjustment of entitlements within their organization. | Business banking card holder | Approved | 1 - Mandatory (Must Have) | Not Applicable | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.6 3.5.3.7 | Missing | Missing - Set entitlements | Missing - Spec updates required | n/a | [TBD] | n/a | Detailed design TBD (Temenos - Kony & Avoka teams) March 29 - Temenos working on mapping into Infinity Entitlements
ONB-12 | Manual provisioning support | 3 - Onboarding | Staff must have a way to manually provision digital banking user in the event that digital onboarding fails. This includes objects in T24, Okta, and Infinity. | Staff | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Business Process Required. Adam, Efosa, OCM | [TBD] | [TBD] - Spotlight config | Missing - Workspaces updates | [TBD] - Admin interface config | [TBD] - Possibly n/a | n/a | Detailed requirements needed to proceed with architectural solution. Architecture Feedback: manual business process steps need to be documented utilizing the T24, Okta and Spotlight to determine if any improvements are required to the process supported by these tools. Risk: this process will initially be more manually intensive given the virtual company structure of Infinity and IAM (Okta) in the architecture.
PROF-01 | Add new delegate user (AKA: Business user) | 4 - Profile Upkeep | Business banking users with suitable privileges should be able to create new delegate users associated with their organization. | Business banking card holder | Approved | 2 - Recommended (Best Practice) | Not Applicable | 1 - Mandatory (Must Have) | Missing | Unclear - possibly SOW 238 - possibly SOW 266 | Unclear - Possibly S11, Story 9 - Possibly S12, Story 12 - Possibly S13, Story 3 | n/a | [TBD] | n/a | n/a | Architecture needs more discussion about requirements
PROF-02 | Remove delegate user (AKA: Business user) | 4 - Profile Upkeep | Business banking users with suitable privileges should be able to remove delegate user accounts from their organization. | Business banking card holder | Approved | 2 - Recommended (Best Practice) | Not Applicable | 1 - Mandatory (Must Have) | Missing | Unclear - possibly SOW 238 | Unclear - Possibly S12, Story 12 | n/a | [TBD] | n/a | n/a | Architecture needs more discussion about requirements
PROF-03 | Update delegate user (AKA: Business user) | 4 - Profile Upkeep | Business banking users with suitable privileges should be able to update existing delegate user accounts. Example: changing a last name or contact information. | Business banking card holder | Approved | 2 - Recommended (Best Practice) | Not Applicable | 1 - Mandatory (Must Have) | Missing | Unclear - possibly SOW 238 - possibly SOW 268 | Unclear - Possibly S11, Story 10 - Possibly S12, Story 12 | n/a | [TBD] | n/a | n/a | Architecture needs more discussion about requirements
PROF-04 | Suspend delegate user (AKA: Business user) | 4 - Profile Upkeep | Business banking users with suitable privileges should be able to suspend or temporarily deactivate a delegate user account within their organization. | Business banking card holder | Approved | 2 - Recommended (Best Practice) | Not Applicable | 1 - Mandatory (Must Have) | Missing | Unclear - possibly SOW 238 | Unclear - Possibly S12, Story 12 | n/a | [TBD] | n/a | n/a | Architecture needs more discussion about requirements
PROF-05 | Contact information updates | 4 - Profile Upkeep | All users should have access to a mechanism within their digital banking platform, that allows them to update their personal contact information. At a minimum, this information includes e-mail address and phone number. | Digital banking user (all types) | Approved | 2 - Recommended (Best Practice) | 2 - Recommended (Best Practice) | 1 - Mandatory (Must Have) | Blocked | Missing | Missing | n/a | [TBD] | [TBD] | n/a | Detailed (field-level) requirements needed for architectural solution. Architecture Feedback: Business review required of email and phone number updates in Infinity and their impact to downstream systems. E.g. should the mobile phone number update also update the Okta SMS Factor? Path forward: Assign a BA to resolve these basic questions. BA should involve business, architecture, Okta lead, T24 lead, Infinity lead. This should really not take more than 1 hour to resolve.
PROF-06 | First login contact information update | 4 - Profile Upkeep | All digital banking users should be given an opportunity to review and update their personal contact information during their first login. At a minimum, this information includes e-mail address and phone number. | Digital banking user (all types) | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution Proposed 3.5.3.10 | [TBD] - Possibly n/a | [TBD] - Possibly n/a | n/a | [TBD] | [TBD] | Solution in progress | Architecture Feedback: Architecture has proposed the capture of several data elements at time of login to update data that is important but likely not accurate in our current systems. Path forward: Assign a BA to discuss the flow and user implications. BA should involve business, user experience, architecture, Okta lead, T24 lead, Infinity lead. Subsequent to this discussion, we can likely hand this over to Temenos for detailed design (UI experience, business rules, etc.). Ensure that Infinity is handling this use case during first login of migrated users. They may have to set a status flag during the load process.
PROF-07 | User name updates | 4 - Profile Upkeep | Digital banking users should be able to update their authentication user name to something other than their PAN. For example an e-mail address or nickname of their choosing. | Digital banking user (all types) | Approved | 4 - Future Initiative (out of scope) | 4 - Future Initiative (out of scope) | 2 - Recommended (Best Practice) | Not started | [TBD] - Possibly n/a | [TBD] - Possibly n/a | n/a | [TBD] | n/a | n/a | Out of scope for R1 Requirements analysis required before finalizing architectural solution. Architecture Feedback: Architecture has asked that a formal documentation of requirements, use cases and process flows be created for all IAM topics. This has never been done with the assumption that Okta had the flows CWB required. Okta's flows have been shown to be inflexible and not of the enterprise calibre we believe is necessary; however, we do not have the business input on what the flows should support to properly evaluate this. Assign a BA (preferably Steve) to work through these details.
PROF-08 | Password changes | 4 - Profile Upkeep | All users should have access to a mechanism within their digital banking platform, for changing their password. | Digital banking user (all types) | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution confirmed | SOW 204 | 14.5.1 - Approved 14.5.1 - Approved | n/a | [TBD] | n/a | n/a
PROF-09 | First login password change | 4 - Profile Upkeep | All digital banking users should have the opportunity to update their password during first login. This would be part of setting up their global identity. | Digital banking user (all types) | Declined/cancelled | Not Applicable | Not Applicable | Not Applicable | n/a | n/a | n/a | n/a | n/a | n/a | n/a | No longer required.
PROF-10 | Password strength enforcement | 4 - Profile Upkeep | All digital banking users must be subject to policy-based password strength enforcement while changing or resetting passwords. Strength enforcement is not required at any other time, such as during authentication. | Digital banking user (all types) | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.1 | n/a | n/a | [TBD] - Depending on integration, may or may not be required. | [TBD] | n/a | n/a
PROF-11 | Forgotten password | 4 - Profile Upkeep | During login, all digital banking users should have access to a self-serve mechanism allowing them to reset a forgotten password. | Digital banking user (all types) | Approved | 4 - Future Initiative (out of scope) | 4 - Future Initiative (out of scope) | 1 - Mandatory (Must Have) | Blocked | SOW 4 SOW 5 SOW 6 SOW 7 SOW 9 SOW 10 SOW 11 SOW 12 SOW 14 SOW 15 | 1.1.2 - Under review 1.1.7 - Under review | n/a | [TBD] | n/a | n/a | Out of scope for R1 Requirements analysis required before finalizing architectural solution. Architecture Feedback: Architecture has asked that a formal documentation of requirements, use cases and process flows be created for all IAM topics. This has never been done with the assumption that Okta had the flows CWB required. Okta's flows have been shown to be inflexible and not of the enterprise calibre we believe is necessary; however, we do not have the business input on what the flows should support to properly evaluate this. Assign a BA (preferably Steve) to work through these details.
PROF-12 | Forgotten password identity verification | 4 - Profile Upkeep | While resetting a forgotten password via self-serve functionality, all digital banking users should be challenged to prove their identity. | Digital banking user (all types) | Approved | 4 - Future Initiative (out of scope) | 4 - Future Initiative (out of scope) | 1 - Mandatory (Must Have) | Blocked | n/a | n/a | n/a | [TBD] | n/a | n/a | Out of scope for R1 Requirements analysis required before finalizing architectural solution. Architecture Feedback: Architecture has asked that a formal documentation of requirements, use cases and process flows be created for all IAM topics. This has never been done with the assumption that Okta had the flows CWB required. Okta's flows have been shown to be inflexible and not of the enterprise calibre we believe is necessary; however, we do not have the business input on what the flows should support to properly evaluate this. Assign a BA (preferably Steve) to work through these details.
PROF-13 | MFA preference changes | 4 - Profile Upkeep | All users should have access to a mechanism within their digital banking platform, for changing their MFA preferences. This should include factor selection and configuration. | Digital banking user (all types) | Approved | 2 - Recommended (Best Practice) | 2 - Recommended (Best Practice) | 1 - Mandatory (Must Have) | Blocked | [TBD] - Possibly n/a | [TBD] - Possibly n/a | n/a | [TBD] | n/a | n/a | Out of scope for R1 Requirements analysis required before finalizing architectural solution. Architecture Feedback: Architecture has asked that a formal documentation of requirements, use cases and process flows be created for all IAM topics. This has never been done with the assumption that Okta had the flows CWB required. Okta's flows have been shown to be inflexible and not of the enterprise calibre we believe is necessary; however, we do not have the business input on what the flows should support to properly evaluate this. Assign a BA (preferably Steve) to work through these details.
PROF-14 | PAN replacement | 4 - Profile Upkeep | Staff must be able to replace a current PAN with a new one, and have this change propagate to all required systems. | Staff | Approved | 4 - Future Initiative (out of scope) | 4 - Future Initiative (out of scope) | 1 - Mandatory (Must Have) | Solution in progress | [TBD] - Possibly n/a | [TBD] - Possibly n/a | n/a | [TBD] | [TBD] | n/a | Assumed out of scope for R1. Manual process to be defined. Architecture Feedback: it is assumed a manual approach will be identified for MVP to keep PAN updates in sync between systems. Going forward, we are working on a solution on how changes in T24 (such as the PAN) should be replicated to other systems (such as Okta). George is looking at a T24 replication pattern.
PROF-15 | PAN termination & re-issue | 4 - Profile Upkeep | Staff must be able to terminate a current PAN, and at a later time, re-issue a replacement PAN to the same user. This change must be propagated to all required systems. | Staff | Approved | 4 - Future Initiative (out of scope) | 4 - Future Initiative (out of scope) | 1 - Mandatory (Must Have) | Solution in progress | [TBD] - Possibly n/a | [TBD] - Possibly n/a | n/a | [TBD] | [TBD] | n/a | Assumed out of scope for R1. Manual process to be defined. Architecture Feedback: it is assumed a manual approach will be identified for MVP to keep PAN updates in sync between systems. Going forward, we are working on a solution on how changes in T24 (such as the PAN) should be replicated to other systems (such as Okta). George is looking at a T24 replication pattern.
PROF-16 | Profile information propagation | 4 - Profile Upkeep | Changes made to a user's profile information in one system must be propagated to all other required systems. Example: contact information updated in the digital banking platform, must be propagated to the IAM and core banking systems as required. Example: Staff changes a client's last name in T24. | Staff | Approved | 2 - Recommended (Best Practice) | 2 - Recommended (Best Practice) | 1 - Mandatory (Must Have) | Blocked | Missing - Possibly n/a | Missing - Possibly n/a | [TBD] | [TBD] | [TBD] | n/a | Detailed requirements needed Architecture Feedback: we must also understand if this is bi-directional (i.e. updates in T24 to relevant information such as phone #, email, etc. are pushed to other systems as well)? George is looking at a T24 replication pattern.
POL-01 | Password strength policy | 5 - Policy | Staff must be able to define and modify a password strength policy to reduce the use of weak password. | Staff | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.2 | n/a | n/a | n/a | [TBD] | n/a | n/a
POL-02 | Password expiry policy | 5 - Policy | Staff must be able to define and modify a password expiry policy such that users must change their password after a defined period of time. | Staff | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.2 | n/a | n/a | n/a | [TBD] | n/a | n/a | Confirmation of requirement required from business Architecture Feedback: supported via Okta. No further input required.
POL-03 | MFA factor policy | 5 - Policy | Staff must be able to define and modify a policy that defines the set of acceptable MFA factors available to digital banking users. | Staff | Approved | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.2 | n/a | n/a | n/a | [TBD] | n/a | Solution confirmed | Need to determine how to migrate users so that they are prompted for MFA enrollment on first login. Tony indicated that Okta will detect the missing factors during first login of migrated users, and prompt for enrollment.
ENT-01 | Entitlements - new accounts | 6 - Entitlements | Business banking users must be subject to entitlements and approvals that define who has the authority to add new accounts/products. | Business banking card holder | Approved | 1 - Mandatory (Must Have) | Not Applicable | 1 - Mandatory (Must Have) | Blocked | Missing | Missing | [TBD] | n/a | [TBD] | Blocked | Direct entry point to DCO require architectural consideration. Detailed business requirements/roles needed Architectural Feedback: discussions on onboarding are ongoing, but we have not yet discussed the authenticated use cases and how entitlements will play in to this. This will very likely require DCO to inquire of Infinity what the user's entitlements are to determine if they can proceed and add accounts on behalf of an existing business or user. Meetings coordinated by Kendyl starting Feb 19th.
ENT-02 | Entitlements - transactions | 6 - Entitlements | Business banking users must be subject to entitlements and approvals that define who has the authority to execute transactions. | Business banking card holder | Approved | 1 - Mandatory (Must Have) | Not Applicable | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.6 | Missing | Missing | [TBD] | n/a | [TBD] | Blocked | Detailed business requirements/roles needed
ENT-03 | Entitlements - user admin | 6 - Entitlements | Business banking users must be subject to entitlements and approvals that define who has the authority to administer users within their organization. | Business banking card holder | Approved | 1 - Mandatory (Must Have) | Not Applicable | 1 - Mandatory (Must Have) | Solution confirmed 3.5.3.6 | Missing | Missing | [TBD] | n/a | [TBD] | Blocked | Detailed business requirements/roles needed

## List Values
Review Status | Priority
New consideration | 1 - Mandatory (Must Have)
Proposed (New) | 2 - Recommended (Best Practice)
Revised | 3 - Desirable (Nice To Have)
Approved | 4 - Future Initiative (out of scope)
Declined/cancelled | 5 - To be determined
Fulfilled | Not Applicable