## Sprint Status Dashboard
Sprint# | 1900-01-13
Count of User Story #
Status | Total
Decision Updated | 1900-01-02
In Review | 1900-01-02
Approved | 1900-01-25
UI Pending | 1900-01-01
Grand Total | 1900-02-02

## DBX Sprint
SOW291, | Sprint# | Sprint Start Date | Sprint End Date | User Story Approval Due Date | Module | Feature | Functionality | SOW Description | User Story # | Status | Decision Date if the Status is "Decision Updated" | Decision Details if the Status is "Decision Updated" | Decision Made by if the Status is "Decision Updated" | Additonal Notes | Story Approval Date
SOW170 | TBD |  |  |  | Transfers | Fund Transfers | Transfer to own account in other financial institutions (Me2Me) | Add a new account in another domestic bank/CU as an external account (recipient) to the profile, by providing account information. Users can transfer funds to the external account once it has been verified and activated. |  | Decision Updated | 2020-12-18 | 12/18/2020 CM: Defer Me2Me from R1 to a post R1 release. This needs to be there with Motive as it is a retail function. Temenos and CWB agreed both recommended deferring M2M, and collectively indicated it would put R1 at risk in the workshop this morning. | Christina Mullin | This needs to be there with Motive as it is a retail function.
SOW190 | TBD |  |  |  | Cheque Management | Stop Cheque Payment | Stop Cheque payment | The Infinity Stop Cheque and Stop Payment function includes a field for the Date of Request Field. The intent of this field is to display the date the stop request was made. This date is captured and sent to T24. However when a user is review the request history, the Date Requested field is not returned from T24. CWB does require this field (should) and a decision is required on how to solution this field. The four options discussed are as follows: • Change the API to return the Date of Request • Suppress the field • Display the date based on what Infinity captures when (needs to be validated if this is technically possible). This would be a temporary solution. • Leave it blank |  | Decision Updated |  | The request create date is required. Suppresssing and leaving it blank are not options as date is on the screen and part of the user story. Next step is to ask Temenos what would suffice as a solution. |  | Neil (1/15/20) set email to Grant to request solution scope)
SOW283 | 11 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit Provincial Business Tax (separate forms from CRA) | 11.1.1 | Approved
SOW283 | 11 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit Provincial Business Tax (separate forms from CRA) | 11.1.2 | Approved |  |  |  |  | Jan 18-22
SOW283 | 11 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit Provincial Business Tax (separate forms from CRA) | 11.1.3 | Approved
SOW283 | 11 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit Provincial Business Tax (separate forms from CRA) | 11.1.4 | Approved
SOW283 | 11 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit Provincial Business Tax (separate forms from CRA) | 11.1.5 | Approved |  |  |  |  | 2021-01-26
SOW283 | 11 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit Provincial Business Tax (separate forms from CRA) | 11.1.6 | Approved |  |  |  |  | 2021-01-26
SOW70 | 11 |  |  |  | Payments & Withdrawals | CRA Fund Transfer | View CRA Payment History | Ability to view payment history | 11.2.1 | Approved
SOW70 | 11 |  |  |  | Payments & Withdrawals | CRA Fund Transfer | View CRA Payment History | Ability to view payment history | 11.2.2 | Approved
SOW70 | 11 |  |  |  | Payments & Withdrawals | CRA Fund Transfer | View CRA Payment History | Ability to view payment history | 11.2.3 | Approved
SOW71 | 11 |  |  |  | Payments & Withdrawals | CRA Fund Transfer | View CRA Payment History | Ability to view payment history | 11.2.4 | Approved
SOW72 | 11 |  |  |  | Payments & Withdrawals | CRA Fund Transfer | View CRA Payment History | Ability to view payment history | 11.2.5 | Approved
SOW73 | 11 |  |  |  | Payments & Withdrawals | CRA Fund Transfer | View CRA Payment History | Ability to view payment history | 11.2.6 | Approved
SOW83 | 11 |  |  |  | Accounts | Transactions | Pagination | Increase pagination beyond 10 transactions at a time. The requirement is to allow User to see 50 per page. Parameter of the pagination has to be passed to MS, need a cursor value back for next and previous transaction pages. | 11.3.1 | In Review
SOW282 | 11 |  |  |  | Transfers | External Accounts | Manage External Bank accounts | Remove external accounts added for transfers | 1899-12-31 | In Review
SOW282 | 11 |  |  |  | Transfers | External Accounts | Manage External Bank accounts | Remove external accounts added for transfers | 1900-01-01 | Draft
SOW60 | 12 |  |  |  | Bill Payment | Bill Pay | Transaction / Payment Receipts | Ability to view list of bill payments, with the option to manage each transaction ( i.e. print and download each receipt). The list can contain the beneficiary name, transaction description, type, from account, transaction ID, date, status, amount | 12.1.1 | In Review
SOW60 | 12 |  |  |  | Bill Payment | Bill Pay | Transaction / Payment Receipts | Ability to view list of bill payments, with the option to manage each transaction ( i.e. print and download each receipt). The list can contain the beneficiary name, transaction description, type, from account, transaction ID, date, status, amount | 12.1.2 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.1 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.2 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.3 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.4 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.5 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.6 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.7 | UI Pending
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.8 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.9 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.10 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.11 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.12 | Draft | 2020-12-22 | Revoke PAP will not be in R1 | Include in Scope to manage multiple statuses for PAP. | removed b/c Stop Cheque is not in r1 1/14/21- Notified Temenos, stories moved to In Draft Status in Confluence
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.13 | Approved | 2020-12-22 | Revoke PAP will not be in R1 | Include in Scope to manage multiple statuses for PAP. | removed b/c Stop Cheque is not in r1 1/14/21- Notified Temenos, stories moved to In Draft Status in Confluence | 2021-01-25
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.14 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.15 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.16 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.17 | Approved
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.18 | Approved |  |  |  |  | 2021-01-25
SOW97 | 13 |  |  |  | User Interface | Menu | Navigation and Configuration | Deliver a configurable menu in Release 1 (not a customization that would impact future upgrades). They require two sections for money movement at the top hierarchy of the menu structure: Transfers – includes only internal A2A and external A2A transfers) Payments – includes all other payment type CRA (Tax Payments) Bill Pay EFT / ACH eTransfers (P2P) – This mean splitting the transfers module into two and adding restrictions Wires (Domestic and International) CWB requests Product team take this item Note - 9/18 - EFT is no longer in scope for Release 1 and is in the backlog | 13.2.1 | In Review
SOW97 | 13 |  |  |  | User Interface | Menu | Navigation and Configuration | Deliver a configurable menu in Release 1 (not a customization that would impact future upgrades). They require two sections for money movement at the top hierarchy of the menu structure: Transfers – includes only internal A2A and external A2A transfers) Payments – includes all other payment type CRA (Tax Payments) Bill Pay EFT / ACH eTransfers (P2P) – This mean splitting the transfers module into two and adding restrictions Wires (Domestic and International) CWB requests Product team take this item Note - 9/18 - EFT is no longer in scope for Release 1 and is in the backlog | 13.2.2 | Approved
SOW34, SOW35 | 13 |  |  |  | Foreign Exchange | Rate Display | FX Rate Display | Display info on buying or selling US cash, cheques or traveler's cheques exchange rates. (C1 Returns the exchange rates from the institution) FX calculator to assist users while converting foreign currencies to CAD or vice versa - User inputs a value, currency to and from and can generate a quote for the exhange rate. | 13.4.1 | Approved
SOW34, SOW35 | 13 |  |  |  | Foreign Exchange | Rate Display | FX Rate Display | Display info on buying or selling US cash, cheques or traveler's cheques exchange rates. (C1 Returns the exchange rates from the institution) FX calculator to assist users while converting foreign currencies to CAD or vice versa - User inputs a value, currency to and from and can generate a quote for the exhange rate. | 13.4.2 | Approved
SOW34, SOW35 | 13 |  |  |  | Foreign Exchange | Rate Display | FX Rate Display | Display info on buying or selling US cash, cheques or traveler's cheques exchange rates. (C1 Returns the exchange rates from the institution) FX calculator to assist users while converting foreign currencies to CAD or vice versa - User inputs a value, currency to and from and can generate a quote for the exhange rate. | 13.4.3 | Approved
SOW34, SOW35 | 13 |  |  |  | Foreign Exchange | Rate Display | FX Rate Display | Display info on buying or selling US cash, cheques or traveler's cheques exchange rates. (C1 Returns the exchange rates from the institution) FX calculator to assist users while converting foreign currencies to CAD or vice versa - User inputs a value, currency to and from and can generate a quote for the exhange rate. | 13.4.4 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.1 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.2 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.3 | Approved
SOW301 | 13 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Delete CRA Business Account Number | Ability to delete CRA Business Account Number registered to file | 13.6.1 | Approved
SOW301 | 13 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Delete CRA Business Account Number | Ability to delete CRA Business Account Number registered to file | 13.6.2 | Approved
SOW301 | 13 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Delete CRA Business Account Number | Ability to delete CRA Business Account Number registered to file | 13.6.3 | Approved
SOW169 | 11 |  |  |  | Transfers | Fund Transfers | Beneficiary management | View the recipients added to the profile so that the user can initiate transfers to a recipient, edit a recipient’s details, or delete the recipient the user no longer wishes to transfer money to and view the transfer history for a recipient. | 11.6.1 | UI Pending |  |  |  | Neil 1/15/21) Pending UI Approval
SOW169 | 11 |  |  |  | Transfers | Fund Transfers | Beneficiary management | View the recipients added to the profile so that the user can initiate transfers to a recipient, edit a recipient’s details, or delete the recipient the user no longer wishes to transfer money to and view the transfer history for a recipient. | 11.6.2 | Approved
SOW169 | 11 |  |  |  | Transfers | Fund Transfers | Beneficiary management | View the recipients added to the profile so that the user can initiate transfers to a recipient, edit a recipient’s details, or delete the recipient the user no longer wishes to transfer money to and view the transfer history for a recipient. | 11.6.3 | UI Pending
SOW 138 | 10 |  |  |  | Accounts | Transactions | Transaction Search | Transaction Search Current Search Capabilities are documented in the linked documents. Here is a summary: Show most recent 50 transactions (50 is default) User needs to see 50 transactions per page. By Date Range: From Date, to Date (calendar Selector) (five years is max) By Month for the last 12 months. (Drop Down Menu) Advanced Search Options: All Statement Items (default) Deposits only Withdrawals Cheques Bill Payments Search by Descriptor Search by Cheque Number Search by Amount Search by Confirmation Number The User can select the display format . These include: On Screen with details (Date, Description, Credits, Debits, Balance)* this is the default On Screen without details (Date, Limited Description, Credits, Debits, Balance) | 11.4.1 | Approved
SOW 138 | 10 |  |  |  | Accounts | Transactions | Transaction Search | Transaction Search Current Search Capabilities are documented in the linked documents. Here is a summary: Show most recent 50 transactions (50 is default) User needs to see 50 transactions per page. By Date Range: From Date, to Date (calendar Selector) (five years is max) By Month for the last 12 months. (Drop Down Menu) Advanced Search Options: All Statement Items (default) Deposits only Withdrawals Cheques Bill Payments Search by Descriptor Search by Cheque Number Search by Amount Search by Confirmation Number The User can select the display format . These include: On Screen with details (Date, Description, Credits, Debits, Balance)* this is the default On Screen without details (Date, Limited Description, Credits, Debits, Balance) | 11.4.2 | Approved
SOW 138 | 11 |  |  |  | Accounts | Transactions | Transaction Search | Transaction Search Current Search Capabilities are documented in the linked documents. Here is a summary: Show most recent 50 transactions (50 is default) User needs to see 50 transactions per page. By Date Range: From Date, to Date (calendar Selector) (five years is max) By Month for the last 12 months. (Drop Down Menu) Advanced Search Options: All Statement Items (default) Deposits only Withdrawals Cheques Bill Payments Search by Descriptor Search by Cheque Number Search by Amount Search by Confirmation Number The User can select the display format . These include: On Screen with details (Date, Description, Credits, Debits, Balance)* this is the default On Screen without details (Date, Limited Description, Credits, Debits, Balance) | 11.4.3 | Approved
SOW 138 | 11 |  |  |  | Accounts | Transactions | Transaction Search | Transaction Search Current Search Capabilities are documented in the linked documents. Here is a summary: Show most recent 50 transactions (50 is default) User needs to see 50 transactions per page. By Date Range: From Date, to Date (calendar Selector) (five years is max) By Month for the last 12 months. (Drop Down Menu) Advanced Search Options: All Statement Items (default) Deposits only Withdrawals Cheques Bill Payments Search by Descriptor Search by Cheque Number Search by Amount Search by Confirmation Number The User can select the display format . These include: On Screen with details (Date, Description, Credits, Debits, Balance)* this is the default On Screen without details (Date, Limited Description, Credits, Debits, Balance) | 11.4.4 | UI Pending
SOW3 | 14 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.1 | Approved |  |  |  |  | 2021-01-25
SOW3 | 14 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.2 | Approved |  |  |  |  | 2021-01-26
SOW3 | 14 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.3 | UI Pending
SOW3 | 14 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.4 | UI Pending
SOW3 | 14 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.5 | Approved |  |  |  |  | 2021-01-27
SOW3 | 14 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.6 | Approved |  |  |  |  | 2021-01-26
SOW3 | 14 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.7 | In Review |  |  |  |  | 2021-01-27
SOW3 | 14 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.8 | Approved |  |  |  |  | 2021-01-27
SOW4 | 15 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.9 | Approved |  |  |  |  | 2021-01-27
SOW5 | 16 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.10 | In Review
SOW6 | 17 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.11 | In Review
SOW7 | 18 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.12 | In Review
SOW8 | 19 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.13 | In Review
SOW9 | 20 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.14 | Approved |  |  |  |  | 2021-01-27
SOW10 | 21 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.15 | Approved |  |  |  |  | 2021-01-27
SOW11 | 22 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.16 | Approved |  |  |  |  | 2021-01-27
SOW12 | 23 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.17 | In Review
SOW13 | 24 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.18 | In Review
SOW14 | 25 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.19 | In Review
SOW15 | 26 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.20 | In Review
SOW16 | 27 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | 14.1.21 | Draft
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.4 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.5 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.6 | Approved
SOW 138 | 10 |  |  |  | Accounts | Transactions | Transaction Search | Transaction Search Current Search Capabilities are documented in the linked documents. Here is a summary: Show most recent 50 transactions (50 is default) User needs to see 50 transactions per page. By Date Range: From Date, to Date (calendar Selector) (five years is max) By Month for the last 12 months. (Drop Down Menu) Advanced Search Options: All Statement Items (default) Deposits only Withdrawals Cheques Bill Payments Search by Descriptor Search by Cheque Number Search by Amount Search by Confirmation Number The User can select the display format . These include: On Screen with details (Date, Description, Credits, Debits, Balance)* this is the default On Screen without details (Date, Limited Description, Credits, Debits, Balance) | 11.4.3
SOW198 | 2 |  |  |  | Customer Service | Contact Us | Click to call or text-message | Ability to call, email the bank. | 2.2.7 | Approved
SOW198 | 2 |  |  |  | Customer Service | Contact Us | Click to call or text-message | Ability to call, email the bank. | 2.2.8 | Approved
SOW68 | 13 |  |  |  | Transfers | Fund Transfers | Cross Currency Transfer | Ability to make cross-currency transfers between Canadian and U.S. dollar accounts | 13.1.1 | Approved |  |  |  |  | 2021-01-22
SOW68 | 13 |  |  |  | Transfers | Fund Transfers | Cross Currency Transfer | Ability to make cross-currency transfers between Canadian and U.S. dollar accounts | 13.1.2 | Approved |  |  |  |  | 2021-01-22
SOW68 | 13 |  |  |  | Transfers | Fund Transfers | Cross Currency Transfer | Ability to make cross-currency transfers between Canadian and U.S. dollar accounts | 13.1.3 | Approved |  |  |  |  | 2021-01-22
SOW68 | 13 |  |  |  | Transfers | Fund Transfers | Cross Currency Transfer | Ability to make cross-currency transfers between Canadian and U.S. dollar accounts | 13.1.4 | Approved |  |  |  |  | 2021-01-25
SOW7 | TBD |  |  |  | Payments & Withdrawals | CRA Fund Transfer | CRA Fund Transfer | Ability to perform multiple transfers to and from different accounts at the same time (similar to bulk transfer - paying one tax payment from multiple accounts or multiple tax payments at the same time). | TBD | Decision Updated | 2021-01-18 | Remove this from scope from R1. Let's keep on the list for post R1 and revisit priority later. | Christina Mullin | This is not standard functionality today (for both CWB and Infinity), so it would go against the direction of the project in taking out of the box where applicable. There is limited perceived value from the client perspective given the overall complexity of each tax form making it difficult from a UX viewpoint to offer a bill payment interaction that could encompass multiple tax forms within one experience. Potential reconciliation issues were raised for the back office staff if a single payment was made from multiple accounts given the nature of how T24 process and records these transactions. T24 transact can only process a single payment at one time, which would then require a mechanism by which Infinity/Mule would store the multiple payments in sequential order to be processed by T24 transact. This level of functionality would require development and would introduce additional risk into the payment process. Given the above points and the overall sensitive nature of the CRA payments overall, we are recommending to exclude SOW7 from delivery for the R1 release and potentially entirely from the development schedule.
SOW68 | 13 |  |  |  | Transfers | Fund Transfers | Cross Currency Transfer | Ability to make cross-currency transfers between Canadian and U.S. dollar accounts | 13.1.5 | Approved |  |  |  |  | 2021-02-01
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.7 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.8 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.9 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.10 | Approved
SOW290, SOW291, SOW292, SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | See Delivery Plan | 15.1.11 | Approved
SOW142, SOW155, SOW15 | 14 |  |  |  | Bill Payment | Bill Pay Enrollment | Activate Bill Payment for a user | E-Bills | TBD | Decision Updated | 2021-01-21 | E-Bill functionality not available for CWB. | Christina Mullin
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.19 | Approved |  |  |  |  | 2021-01-25
SOW1000 | 12 |  |  |  | Cheque Management | Stop Payment | Stop payment | Stop Payment for Pre-Authorized Payment | 12.3.20 | Approved
SOW88 | 13 |  |  |  | Payments & Withdrawals | Pay Business Taxes | CRA "Vendor" list for Small Business Banking | Enhance vendor list or create new Vendor list in Spotlight to allow input of Canadian Revenue Agency (CRA) payees. This is specific to Canada. Today, the vendor list that exists in Spotlight is used to Bill Pay vendors, e.g. Gov. of Alberta, etc. Similarly, there are CRA vendors for paying country-wide and provincial payees. This would function like a bill pay vendor list, but needs a focus for CRA vendors. Requirements include everything from the existing vendor list. This is required if we are to move away from storing these in Central 1. | 13.5.1 | Approved |  |  |  |  | 2021-01-25
SOW283 | 11 |  |  |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit Provincial Business Tax (separate forms from CRA) | 11.1.7 | Approved |  |  |  |  | 2021-01-26
SOW158 SOW146 | 14 |  |  |  | Bill Payment Payments & Withdrawals | Bill Pay | Pay multiple bills together Pay a registered biller | Payment Amount | 14.3.1 | Decision Updated | 2021-02-09 | Last Payment field removed for R1 Must be added back post R1. | Christina Mullin | Story Approved with AC of Last Payment field removed | 2021-02-11
SOW158 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay multiple bills together |  | 14.3.2 | Approved |  |  |  |  | 2021-02-08
SOW152 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Confirmation of Payment details | 14.3.3 | Approved |  |  |  |  | 2021-02-08
SOW152 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Confirmation of Payment details | 14.3.4 | Approved |  |  |  |  | 2021-03-07
SOW162 SOW144 | 14 |  |  |  | Payments & Withdrawals Bill Payment | Bill Pay | Manage billers (add, update, delete) | View a list of registered bill payees, view history of bills paid to a company, update the payee details or delete the payee account. Search for a previously added bill payee from a list of all bill payees for easy access Search A biller - Biller details page will be appeared in the same screen. Browse for payees by browsing from pre-defined payee type categories such as Insurance, Property, Schools and Utilities. | 14.3.5 | In Review
SOW162 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Manage billers (add, update, delete) | View a list of registered bill payees, view history of bills paid to a company, update the payee details or delete the payee account. Search for a previously added bill payee from a list of all bill payees for easy access | 14.3.6 | In Review
SOW162 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Manage billers (add, update, delete) | View a list of registered bill payees, view history of bills paid to a company, update the payee details or delete the payee account. Search for a previously added bill payee from a list of all bill payees for easy access | 14.3.7 | Approved |  |  |  |  | 2021-03-07
SOW65 |  |  |  |  | Transfers | e-Transfer | E-Transfer Security Question | 1. The ability to set up and store the security question and answer per recipient (still editable but via edit recipient details api); and 2. The ability to change the security question and answer ad hoc (i.e. whenever a new payment is made). Depending on the how the Interec API works, it may or may not overwrite the Security question and answer already in place for that recipient. | TBD | Decision Updated | 2021-02-03 | Currently our system only allows for Option 1, the foregoing thought that only Option 2 was needed in the new platform, but the decision is now both Options 1 and 2 for Infinity. | Christina Mullin | As Per Email from Gerry W dated Feb 03, 2021
SOW309 SOW31 | 10 |  |  |  | Business Banking Dashboard | Email Registered phone number | Email Registered phone number | Displays the registered email Displays the registered phone number | 10.0.5 | Approved |  |  |  | Pre-Approved story required further clarification regarding phone number format and validation rules | 2021-02-05
SOW309 SOW31 | 10 |  |  |  | Business Banking Dashboard | Email Registered phone number | Email Registered phone number | Displays the registered email Displays the registered phone number | 1900-01-09 01:26 | Approved |  |  |  | Pre-Approved story required further clarification regarding phone number format and validation rules | 2021-02-05
SOW162 | 14 |  |  |  | Payments & Withdrawals | Bill Pay |  |  | 14.3.8 | Approved |  |  |  |  | 2021-02-18
SOW15 SOW16 SOW143 SOW146 SOW147 SOW148 SOW149 SOW150 SOW151 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Pay a bill immediatley, or schedule a payment | 14.3.9 | Approved
SOW152 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Confirmation of Payment details | 14.3.10 | Approved
SOW152 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Acknowledgement of my completed bill payment or recurring payment | 14.3.11 | Approved |  |  |  |  | 2021-03-08
SOW160 SOW16 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Schedule a bill pay Update or Cancel scheduled bill payments | Assign a future date for bill payment instead of paying immediately. Possible to set up recurring payments as well In case of a scheduled future-dated bill payment, ability to modify the details or cancel the payment. | 14.3.12 | Approved |  |  |  |  | 2021-03-08
SOW160 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Update or Cancel scheduled bill payments | In case of a scheduled future-dated bill payment, ability to modify the details or cancel the payment. | 14.3.13 | Approved |  |  |  |  | 2021-03-07
SOW161 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | View history of bill payments | View and search from a list of the recent bill payment and scheduled payments, sorted by date (most recent on top). | 14.3.14 | Approved |  |  |  |  | 2021-02-19
SOW160 SOW161 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Mobile: In case of a scheduled future-dated bill payment, ability to modify the details or cancel the payment. View and search from a list of the recent bill payment and scheduled payments, sorted by date (most recent on top). | 14.3.15 | Approved |  |  |  |  | 2021-02-11
SOW160 SOW161 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Mobile: In case of a scheduled future-dated bill payment, ability to modify the details or cancel the payment. View and search from a list of the recent bill payment and scheduled payments, sorted by date (most recent on top). | 14.3.16 | Approved |  |  |  |  | 03-052021
SOW160 SOW161 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Mobile: In case of a scheduled future-dated bill payment, ability to modify the details or cancel the payment. View and search from a list of the recent bill payment and scheduled payments, sorted by date (most recent on top). | 14.3.17 | Approved |  |  |  |  | 2021-03-05
SOW15 SOW16 SOW143 SOW146 SOW147 SOW148 SOW149 SOW150 SOW151 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Update or Cancel scheduled bill payments View history of bill payments | Mobile Banking: SOW 15-End Date SOW16-Schedule a Bill Pay SOW143-Initiate a new bill payment with option to select recurring payment SOW146-Payment Amount SOW147-Frequency selection SOW148-Duration selection SOW149-Start Date SOW150-Send Date SOW151-Recurrence number | 14.3.18 | Approved |  |  |  |  | 2021-03-04
SOW15 SOW16 SOW143 SOW146 SOW147 SOW148 SOW149 SOW150 SOW151 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Update or Cancel scheduled bill payments View history of bill payments | Mobile Banking: SOW 15-End Date SOW16-Schedule a Bill Pay SOW143-Initiate a new bill payment with option to select recurring payment SOW146-Payment Amount SOW147-Frequency selection SOW148-Duration selection SOW149-Start Date SOW150-Send Date SOW151-Recurrence number | 14.3.19 | Approved |  |  |  |  | 2021-03-04
SOW162 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Manage billers (add, update, delete) | View a list of registered bill payees, view history of bills paid to a company, update the payee details or delete the payee account. Search for a previously added bill payee from a list of all bill payees for easy access | 14.3.20 | Approved |  |  |  |  | 2021-03-05
SOW162 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Manage billers (add, update, delete) | View a list of registered bill payees, view history of bills paid to a company, update the payee details or delete the payee account. Search for a previously added bill payee from a list of all bill payees for easy access | 14.3.21 | Approved |  |  |  |  | 2021-03-05
SOW161 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | View and search from a list of the recent bill payment and scheduled payments, sorted by date (most recent on top) | 14.3.22 | Approved
SOW142 SOW162 SOW143 SOW158 SOW16 | 14 |  |  |  | Payments & Withdrawals | Bill Pay | Virtual Company Functionality | Add Payee, make a payment, delete payee, schedule a payment | 14.3.x | Decision Updated | 2021-02-26 | At R1 Infinity will support funcitonality for a combined profile of one retail and one busienss CIF. The virtual company functionality to support CWB's multi-CIF business customers is not avilable ib the 2020.07 release | Christina Mullin
SOW204 | 14 |  |  |  | Profile Management | Login Credentials | Update password | Modify the username or password by providing the 6-digit secure code sent to the registered mobile number / email. | 14.5.1 | Approved |  |  |  |  | 2021-02-26
SOW204 | 14 |  |  |  | Profile Management | Login Credentials | Update password | Modify the username or password by providing the 6-digit secure code sent to the registered mobile number / email. | 14.5.2 | Approved |  |  |  |  | 2021-02-26
SOW260 | 13 |  |  |  | Administration | Application Content Management | Manage Customer Care Information | Manage Customer Care Information (phone numbers and email ids) - Generic and service level | 13.6.1 | Approved |  |  |  |  | 2021-02-22
[9 empty] | 13.6.2 | Approved
SOW260 | 44209 |  |  |  | Administration | Application Content Management | Manage Customer Care Information | Manage Customer Care Information (phone numbers and email ids) - Generic and service level | 13.6.2 | Approved |  |  |  |  | 2021-02-22
Multiple | TBD |  |  |  | Multiple | Multiple | Multiple | Multiple SOWs | TBD | In Review |  | Christina and Jason to review and approve IAM Use Case scope decisions. Traceability matrix sent on Mar 9, 2021. (Decision requested by: Steve K.) |  | We need this ASAP, as it informs our R1 development priorities. | n/a
SOW141 | 11 |  |  |  | Accounts | Accounts | Statements | View and Download Statements | N/A | Decision Updated | 2021-03-12 | Download statement chnages required in Infinty to align with Doxim. Doxim statements are consolidated at CIF level. Infinity functionlity is at account level. Re-design of Infinity view statement screen, add View Statements link to hamburger menu under "Accounts" | Gerry Weber
SOW168 | 15 | Transfers | e-Transfer |  | Transfers | e-Transfer | Ability to add interac e-transfer recipient by importing existing mobile contact through mobile banking app |  | N/A | Decision Updated | 2021-03-10 | Not in OOTB, Backlog for post R1. Email 03/11/2021 from Lauren: I reviewed this requirement with Christina and Stacy yesterday and they confirmed this is not required for R1. This decision is also documented as #3 in yesterday’s daily leadership update (Sprint 15A - SOW168 – Christina and Stacy confirmed mobile contact import to populate Bill Pay and e-transfer recipients not needed for R1. Item backlogged for future release prioritization). | Christina Mullin
SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.12 | Approved |  |  |  |  | 2021-03-11
SOW291 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.13 | Approved |  |  |  |  | 2021-03-11
SOW290 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.14 | Approved |  |  |  |  | 2021-03-11
SOW290 SOW292 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.15 | Approved |  |  |  |  | 2021-03-11
SOW290 SOW292 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.16 | Approved |  |  |  |  | 2021-03-11
SOW291 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.17 | Approved |  |  |  |  | 2021-03-11
SOW290 SOW291 SOW292 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.18 | Approved |  |  |  |  | 2021-03-11
SOW291 SOW292 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.19 | In Review
SOW292 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.20 | In Review
SOW292 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.21 | Approved |  |  |  |  | 2021-03-11
SOW292 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.22 | In Review
SOW292 SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.23 | In Review
SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.24 | In Review
SOW291 SOW290 SOW325 | 15 | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.25 | In Review
SOW290 SOW325 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.26 | Approved |  |  |  |  | 2021-03-12
SOW290 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.27 | In Review
SOW291 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.28 | In Review
SOW290 SOW291 SOW292 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.29 | In Review
SOW290 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.30 | Approved |  |  |  |  | 2021-03-15
SOW290 | 15 |  |  |  | Approvals and Request | Transactions | Recall Transactions Expired Transactions List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user |  | 15.1.31 | In Review
SOW188 | 16 |  |  |  | Cheque Management | Remote Deposit Capture | View pending and recent deposits | Suppress feature for R1 - View a list of recent Cheque deposits, sorted by date (most recent on top). Pending will not be displayed; only past | 16.9.1 | Decision Updated | 2021-03-26 | The view pending and recent cheque deposit funcitonality will be suppressed from RDC. The C1 doesn’t have APIs to provide the history of remote deposit requests.
SOW189 | 16 |  |  |  | Cheque Management | Remote Deposit Capture | View Cheque images | Suppress feature for R1 - For specific transactions, view the back / front Cheque images. Only on-us Cheques will display and will come from DOXIM; is dependent upon integration with MS and Doxim. | 16.9.1 | Decision Updated | 2021-03-27 | The view pending and recent cheque deposit funcitonality will be suppressed from RDC. The C1 doesn’t have APIs to provide the history of remote deposit requests.
SOW291 | 15 |  |  |  | Approvals and Request | Transactions | List of Approved, Rejected, Pending approval by Business user Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | This story identities the rules for how long these items should remain visible in the Transaction Manager “Requested” list. These items are to be purge from this viewed after 35 days and archived information for 7 years. | 15.2.17 | Decision Updated | 2021-04-12 | Request to Spit SoW- Move the purge and and archive funtctionlaity to a different SoW. | 2021-04-12 |  | 2021-03-15
SOW 235 | 16 |  |  |  | Business Administration | Employee Management | Create a Company | Fetching Accounts while adding a Company | 16.9.4 | Decision Updated | 2021-04-12 | Request to Spit SoW - Temenos needs to figure out how to represent a "no limit" value in Spotlight. The current state would show a max limit of $999,999,999.00. How ever customer would see this limit in the user admin tool in Infinity. This is not a desired UX. | 2021-04-12
SOW38 | 19 |  |  |  | Marketing | Advertisements | Accounts list Advertisements | In-feed banner advertisements on the Accounts List screen | 19.3.1 - 19.3.3 | Decision Updated | 2021-05-12 | We have a decision from Christina on the Combined profile to go with the OOTB functionality i.e. the default should be the combined view with the business "ad" then clients seeing the retail ad when they switch. The issue we raised on displaying both retail and business ads on the Combined profile dashboard can be tracked and fixed post R1.1. | Christina Mullin | [Monday 7:58 p.m.] Efosa Okonkwo ( initial business request for decision from Christina) Hi Christina Mullin, We went through the AD campaigns user stories today on in-feed banner ads on the dashboards( SOW38). The banners that will be displayed to different clients type depends on whether it is a retail or business client and the ad created in Spotlight. A Retail or Business client will see targeted ads for retail or business respectively. A client with linked retail and business profiles will be able to switch the dashboard view between Retail, Business or Combined based on preference, with the Combined view being the default view. For the combined profile, we have learnt that in the Retail view, the client will see only retail accounts and the ads for retail, in Business view see only the business accounts and ads for business but when in the Combined view only able to see the business ads. This is the OOTB behavior and Temenos has mentioned that Infinity is not able to display retail and business ads for a Combined view. Our concern is that clients who are always on the Combined view will not see the retail opportunities that may be available to them through ads. We have asked the Temenos team on the call to check with their Dev team on what can be done to display the ad banners for retail and business in a Combined view. Here are the options we discussed for a Combined profile: Option 1: Default the client to the Retail View upon log in so that they can see any retail campaigns before switching to the Combined view. This does not provide the best user experience Option 2: Default the client to the Combined view where they are only able to see the business ads except they make a switch to Retail view. This is the OOTB behavior. Option 3: Default the client to the Combined view and allow the campaigns for retail and business to be displayed. This option provides a better experience for the client. This will require that in Spotlight, ads are created with the combined retail and business profile as the target audience. During the review we observed there are 3 categories for Customer type in Spotlight for ad campaign – Retail, Business and Retail & Business and we would want to see how this is relayed in Infinity front end. The Temenos team on the call did not know the impact of selecting the Retail & Business category and so we are expecting them to dig further into this. This option may require a CR depending on what they come back with. Although we await feedback from Temenos on how to improve the client experience with combined view in relation to the ad banners or what the limitations are to achieving it, we would want to know if you are okay with going with the OOTB behavior for R1 ( Option 2) if they do not come back with an affirmative response. We can then add a request for enhancement to our backlog for enhancement. (1 liked)
SOW97 | 19 |  |  |  | User Interface | Menu - Header and Hamburger | Navigation | CWB is requesting that we deliver a configurable menu in Release 1 (not a customization that would impact future upgrades) CWB is communicating this request as a ‘Canadianization’ item. They do not want this to be a standard services customization request due to the impacts in future upgrades. They want this as part of base product. Their main concern pertains to how the payments and transfers options are nested / organized. They will need to change the structure. They require two sections for money movement at the top hierarchy of the menu structure: Transfers – includes only internal A2A and external A2A transfers) Payments – includes all other payment type CRA (Tax Payments) Bill Pay EFT / ACH eTransfers (P2P) – This mean splitting the transfers module into two and adding restrictions Wires (Domestic and International) | 19.2.2-19.2.6 | Decision Updated | 2021-05-12 | Decisions from Christina - I think we need to defer to the next release. When communicating back, please advise that this is needed for our 1.2 release as we will have more menu items and the list will grow. Thanks! | Christina Mullin | [9:39 a.m.] Nolan Smits Hi Christina & Sandra, Temenos is providing an estimate of "8 man days" or "64 hours" of work to update the mobile menu to include titles for the sections. I would like to note that the estimate based on my experience is unreasonably high, I asked the reason for the high estimate of effort but the response was not satisfactory. Would you like to move ahead with this change? ​[10:39 a.m.] Christina Mullin Hi Nolan - thanks for bring this forward. It's good we have the estimate and I agree it's high, but believe it does include testing and related work. As we are hitting some short timelines to get R1 out the door ;et ​[10:41 a.m.] Christina Mullin *con't - I think we need to defer to the next release. When communicating back, please advise that this is needed for our 1.2 release as we will have more menu items and the list will grow. Thanks! (1 liked)​[11:12 a.m.] Nolan Smits Christina, sounds good (yes) I'll forward the request. ​[11:12 a.m.] Nolan Smits They confirmed that the thicker/darker separation lines will be included between the sections. (1 liked)​[11:13 a.m.] Christina Mullin Thanks Nolan Smits that's better than what it is now! (smile)
SOW266 | 19 |  |  |  | Business Entitlements | User Management | Create User | Creates a Business Banking User in DBX System | 16.21.1 | Decision Updated | 2021-05-13 | Infinity limitation regarding one business signer and multiple companies. If one Business Signer is related to two or more companies, the Business Signer can only be associated with one Virtual Company in Spotlight. | Stacy | [stacey] To confirm, this is/will be addressed in a newer version correct? [Bhavesh] Yes, Infinity R21.04 which is based on the Contract based model doesn’t have this limitation. [Stacey] My understanding is that we agreed to defer this (link to multiple companies) to R1.2. Can you confirm that is your understanding as well so we’re aligned? [Bhavesh] Yes
Note on I116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update will function as a cancel and reset with new parameters
Note on I133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PDF format
Note on I155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Come back to this feature for Commercial Banking Release.

## PM Dashboard (hidden)
OOTB without customization | #REF! |  | Functionality items per sprint
OOTB with customization | #REF! |  | Sprint 8 | 0
New Feature | #REF! |  | Sprint 9 | 0
Other | #REF! |  | Sprint 10 | 0
TOTAL | #REF! |  | Sprint 11 | 0
|  |  | Sprint 12 | 0
|  |  | Sprint 13 | 0
|  |  | Sprint 14 | 0
|  |  | Sprint 15 | 0
|  |  | TOTAL | 0
| OOTB without customization | OOTB with customization | New Feature | TOTAL
Sprint 8 | #REF! | #REF! | #REF! | #REF!
Sprint 9 | #REF! | #REF! | #REF! | #REF!
Sprint 10 | #REF! | #REF! | #REF! | #REF!
Sprint 11 | #REF! | #REF! | #REF! | #REF!
Sprint 12 | #REF! | #REF! | #REF! | #REF!
Sprint 13 | #REF! | #REF! | #REF! | #REF!
Sprint 14 | #REF! | #REF! | #REF! | #REF!
Sprint 15 | #REF! | #REF! | #REF! | #REF!
TOTAL | #REF! | #REF! | #REF! | #REF!
T24 Data mapping |  |  |  |  | Technical Design |  |  |  |  | Services/RAML Definition |  |  |  |  | UI/UX |  |  |  |  | User Story |  |  |  |  | CWB Story Approval |  |  |  |  | Mulesoft and third-party
Completed | Overdue | Due Tomorrow | Due 2-5 days from today | Due 6-10 days from today | Completed | Overdue | Due Tomorrow | Due 2-5 days from today | Due 6-10 days from today | Completed | Overdue | Due Tomorrow | Due 2-5 days from today | Due 6-10 days from today | Completed | Overdue | Due Tomorrow | Due 2-5 days from today | Due 6-10 days from today | Completed | Overdue | Due Tomorrow | Due 2-5 days from today | Due 6-10 days from today | Completed | Overdue | Due Tomorrow | Due 2-5 days from today | Due 6-10 days from today | Completed | Overdue | Due Tomorrow | Due 2-5 days from today | Due 6-10 days from today

## Formatted (hidden)
SOW# | JIRA EPIC IDs | Jira EPIC ID Owner | CWB Comments | Questions | Module | Feature | Functionality | Description | 3rd Party Dependency Due Date | Requirements Workshop Date | T24 Data mapping Owner | T24 Data mapping status | Technical Design Due Date | Technical Design Owner | Technical Design Status | Services Definition Due Date | Services DefinitionOwner | Services Definition Status | UI/UX Due Date | UI/UX Owner | UI/UX Screens Readines Status | User Story Due Date | User Story Owner | User Story Readiness Status | CWB Story Approver | CWB Story Readiness Meeting Approval Date | T24 Data mapping Due Date | Dev Status | Transact WS Due Date | Mule Delivery Due Date | Mule Delivery Owner | Service Details (refer services sheet for details) | Mule Readiness Status | Dev Layer | Prioritization_1119 | Original Sprint | Sprint as of Aug | Target Sprint# | Sprint Start Date | Sprint End Date | CWB Bus Acceptance of Dev Delivery Date | Dev Type | Scrum Teams | Efforts | Comments from L3 Transact Team | Sprint Readiness Analysis/Comments
SOW0 | 97, 101, 102, 105 | Sagar | GTG | Okta Dependency | Authentication | Login | Login using Username and Password | Securely sign in with username and password, with an option to securely store and remember the username. | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Bhavesh | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 1 | 1900-01-14 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW1 |  | Sagar | GTG | Okta Dependency | Authentication | Login | Login using Fingerprint | Biometric authentication for iOS and Android devices by using the native fingerprint authentication capability. OKTA integration required as the device tokens need to be stored at OKTA. | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 04 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 1 | 1900-01-04 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW10 |  | Sagar | GTG | Okta Dependency | Authentication | Login | Login using Facial recognition | OKTA integration required as the device tokens need to be stored at OKTA. | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 04 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 1 | 1900-01-04 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW108 | 98, 103 | Sagar | Need further discussion | Okta Dependency | Authentication | Login | Forgot Password | User can choose Security code | OKTA | Completed 11/23/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 2 | 1900-01-03 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW109 | 98, 103 | Sagar | Need further discussion | Okta Dependency | Authentication | Login | Forgot Password | Enter security Code | OKTA | Completed 11/23/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 2 | 1900-01-03 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW110 | 98, 103 | Sagar | Need further discussion | Okta Dependency | Authentication | Login | Forgot Password | Send OTP for second factor authentication | OKTA | Completed 11/23/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 2 | 1900-01-03 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW111 | 98, 103 | Sagar | GTG | Okta Dependency | Authentication | Login | Forgot Password | Create a new password by entering new password, retype password | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 2 | 1900-01-03 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW101 | 98, 103 | Sagar | GTG | Okta Dependency | Authentication | Login | Forgot Username | User to enter the Date of birth | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 1 | 1900-01-03 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW102 | 98, 103 | Sagar | GTG | Okta Dependency | Authentication | Login | Forgot Username | User will be shown with the options to choose from login with user name / reset the password | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 1 | 1900-01-03 |  | f
SOW103 | 98, 103 | Sagar | GTG | Okta Dependency | Authentication | Login | Forgot Username | User will be asked to enter Security code to be registered. | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 2 | 1900-01-03 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW104 | 98, 103 | Sagar | GTG | Okta Dependency | Authentication | Login | Forgot Username | Enter Security code screen | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 2 | 1900-01-03 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW106 | 98, 103 | Sagar | GTG | Okta Dependency | Authentication | Login | Forgot Username | Send OTP for second factor authentication | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | In progress | Complete | Christa | Complete | Complete | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-23 | OOTB | Team 2 | 1900-01-03 |  | Need clarity on requirement / acceptance criteria from Okta/Bhavesh
SOW190 |  | Sagar | GTG | Stop PAP (Pre-Authorized Payment) is Custom development as part of newly created SOW 999 | Check Management | Stop Check Payment | Stop check payment | Stop Check Payment, View list of requests, and delete stop check payment request | T24 | Completed 11/21/2020 | Naj | In Progress | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | Complete | NA | NA | NA | 2020-11-23 | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG | createStopPayment deleteStopPayment getStopCheckPaymentRequestTransactions | Complete | L3 | OOTB without Customization | Sprint 03 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-02 | OOTB | Team 1 | 1900-01-14 | Currently under clarificaion from CWB under offshore development with L3 transact teams | Most of the development is completed for this feature. Pending Services development for Active and Completed Status fields from Lisa and RingFence
SOW207 |  | Sagar | GTG |  | Personalization | User Preferences | Set default accounts | Ability for a user to set a default account for various transactions such as Bill Pay and Remote Check Deposits (for ease of use). | NA | Completed 11/21/2020 | Jude | In Progress | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | Complete | NA | NA | NA | 2020-11-23 | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG | GetAccountDetails | Complete | L3 | OOTB without Customization | Sprint 03 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-02 | OOTB | Team 1 | 1900-01-04 | Infinity service required. Not with Transact. Clarification raised with CAMB team for exisiting service availability. | Ready for development, no acceptance criteria required. OOTB implementation
SOW212 |  | Sagar | GTG |  | Personalization | User Preferences | Reorder accounts |  | NA | Completed 11/21/2020 | NA | NA | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | Complete | NA | NA | NA | 2020-11-23 | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG | NA | Complete | L3 | OOTB without Customization | Sprint 03 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-02 | OOTB | Team 2 | 1900-01-09 | Not a Tranasact Requirement. To be addressed in Infinity service | Ready for development, no acceptance criteria required. OOTB implementation
SOW241 |  | Sagar | GTG |  | Administration | Customer Service | Update customer details and preferences | Details of customers/members can be viewed and, in some cases, updated | T24 | Completed 11/21/2020 | Naj | In Progress | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | Complete | NA | NA | NA | 2020-11-23 | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG | UpdateCustomerDetails | Complete | L3 | OOTB without Customization | Sprint 04 | Sprint 10 | Sprint 01 | #REF! | #REF! | 2020-12-02 | OOTB | Team 2 | 1900-01-05 |  | Partial Development can be done for updating DBX DB but we need Okta Service API to update details in Okta if required. Do we need to update User Name as well?
SOW17 |  | Sagar | GTG |  | Transfers | Fund Transfers | Set up a transfer to own account | Transfer funds between accounts within the same bank, by providing the From and To accounts, amount, transfer date, and optional and notes. | T24 | Completed 11/21/2020 | Naj | In Progress | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | Complete | NA | NA | NA | 2020-11-23 | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG | CreateInternalTransfer UpdateInternalTransfer DeleteInternalTransfer GetInternalTransfers | Complete | L3 | OOTB without Customization | Sprint 05 | Sprint 04 | Sprint 01 | #REF! | #REF! | 2020-12-02 | OOTB | Team 2 | 1900-01-11 |  | Have Approved Stories. Development is in progress on Sprint 0
SOW130 |  | Sagar | GTG |  | Accounts | Accounts | Account Details | Additional information on all account types - users can select an account from the dashboard and view details of the accounts including quick links. User can toggle between accounts on this page. | T24 | Completed 11/21/2020 | Naj | In Progress | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | Complete | NA | NA | NA | 2020-11-23 | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG | GetAccounts | Complete | L3 | OOTB without Customization | Sprint 09 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-02 | OOTB | Team 1 | 1900-01-03 |  | Have Approved Stories. Some are blocked due to Combined Banking
SOW131 |  | Sagar | GTG |  | Accounts | Accounts | Account Details - Settings | Account Nicknames - support of account nicknaming - which occurs on the | T24 | Completed 11/21/2020 | Naj | In Progress | 2020-12-01 | Jack V | In progress | 2020-08-31 | Bhavesh | Complete | NA | NA | NA | 2020-11-23 | Sagar | Complete | Azfar & Jeff | Approved 11/21 | 2020-12-02 | To Do | 2020-12-07 | 2020-12-11 | BIG | UpdateAccountDetails | Complete | L3 | OOTB without Customization | Sprint 09 | Sprint 03 | Sprint 01 | #REF! | #REF! | 2020-12-02 | OOTB | Team 1 | 1900-01-03 |  | Service required but need to do dev with Stubs
SOW65 |  |  | Temenos to present User stories |  | Transfers | Interac Funds Transfer | Transfer via interac | Ability to perform interac transfers - send (part of base), receive (new), request (new), auto deposit (new), view history (part of base), search (base) | NA | L2 Story Review Already Scheduled | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-04 | Bhavesh | To Do | 2020-12-04 | Adam | To Do | 2020-12-04 | Grant | In progress | Christina & Jason | 2020-12-04 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L2 | New Feature | Sprint 10 | Sprint 09 | Sprint 02 | #REF! | #REF! | 2021-01-06 | New Feature | Team 3 | 1900-05-29
SOW121 |  | Sagar | GTG | Okta Dependency | Authentication | Device Registration | Device Registration | After successful first-time login, if a user’s device is not registered, enter a one-time-password and register the device in the bank ’s server. Applies only to the native phone and tablet applications. 4.1 will support Web. | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | 2020-11-21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-02
SOW122 |  | Sagar | GTG | Okta Dependency | Authentication | Device Registration | Device Registration | Device Registration Message | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | 2020-11-21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-02
SOW123 |  | Sagar | GTG | Okta Dependency | Authentication | Device Registration | Device Registration | Enter security Code | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | 2020-11-21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-02
SOW124 |  | Sagar | GTG | Okta Dependency | Authentication | Device Registration | Choose Default Login Method | Choose Default Login Method (user name/Pwd, Touch ID, Pin & face ID) - part of the device registration flow at login | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | 2020-11-21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-02
SOW125 |  | Sagar | GTG | Okta Dependency | Authentication | Device Registration | Device Registration | Touch ID Image | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | 2020-11-21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-02
SOW126 |  | Sagar | GTG | Okta Dependency | Authentication | Default Sign In | Touch ID | Touch ID Setting / Success Pop up | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | 2020-11-21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-03
SOW127 |  | Sagar | GTG | Okta Dependency | Authentication | Device Registration | Device Registration | Face ID | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | 2020-11-21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-03
SOW128 |  | Sagar | GTG | Okta Dependency | Authentication | Default Sign In | Face ID | Face ID Settings | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | 2020-11-21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-03
SOW206 |  | Sagar | GTG |  | Personalization | Default Sign In | Turn on or off Touch ID | Ability for a user to turn on/off the Touch ID feature (for security purposes). Applies only to native phone applications. | NA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 03 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-04
SOW208 |  | Sagar | GTG |  | Personalization | Default Sign In | Set default login method | Define the default login method - fingerprint, facial identification etc. in SETTINGS | NA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 03 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-04
SOW213 |  | Sagar | GTG |  | Personalization | Default Sign In | Turn on or off Facial recognition |  | NA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 03 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-05
SOW204 |  | Sagar | GTG | Okta Dependency | Profile Management | Login Credentials | Update password | Modify the username or password by providing the 6-digit secure code sent to the registered mobile number / email. | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | Christa | Complete | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 10 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-07
SOW205 |  | Sagar | GTG | Okta Dependency | Profile Management | Login Credentials | Update username | Modify the username or password by providing the 6-digit secure code sent to the registered mobile number / email. | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | Christa | Complete | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 10 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-04
SOW242 |  | Sagar | GTG |  | Administration | Customer Service | Update customer details and preferences | profile information such as name, home branch, risk/fraud status, mobile/online banking enrollment status, etc. | OKTA? | Completed 11/21/2020 | Shrikanth | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 10 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-05
SOW243 |  | Sagar | GTG |  | Administration | Customer Service | Update customer details and preferences | Contact information and preferences | OKTA? | Completed 11/21/2020 | Shrikanth | NA | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 10 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-05
SOW173 |  | Sagar | GTG |  | Transfers | Fund Transfers | Schedule a one-time transfer | Ability to transfer to a own account or beneficiary account one - time that has been added as a recipient / external account. | T24 | Completed 11/21/2020 | Naj | To Do | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG | CreateInternalTransfer UpdateInternalTransfer DeleteInternalTransfer GetInternalTransfers | To Do | L3 | OOTB without Customization | Sprint 06 | Sprint 06 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-09
SOW174 |  | Sagar | GTG |  | Transfers | Fund Transfers | Setup recurring transfers | Ability to optionally set up a recurring transfer (daily, weekly, or monthly) within a date range or specify the number of times. | T24 | Completed 11/21/2020 | Naj | To Do | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG | CreateInternalTransfer UpdateInternalTransfer DeleteInternalTransfer GetInternalTransfers | To Do | L3 | OOTB without Customization | Sprint 06 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-14
SOW281 |  | Rodrigo | Temenos to present User stories and workflows |  | Transfers | External Accounts | Add Accounts from External Banks | Add accounts from external financial institutions for external transfers only | T24 Flinks | Week of 12/7/2020 | Naj | To Do | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | Rodrigo | NA | 2020-12-11 | Rodrigo Ferreira | In progress | Christina & Jason | 2020-12-14 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG | GetExternalAccounts CreateExternalTransfer | To Do | L3 | OOTB with Customization | Sprint 08 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 1 | 1900-01-14
SOW36 |  | Sagar | GTG |  | Marketing | Advertisements | Pre-login Advertisements | Pre-login banner advertisements or offers on the login screen |  | Completed 11/21/2020 | NA | To Do | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 07 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-04
SOW37 |  | Sagar | GTG |  | Marketing | Advertisements | Post-login Full-screen Advertisements | Full screen advertisements immediately after login |  | Completed 11/21/2020 | NA | To Do | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 07 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-07
SOW38 |  | Sagar | GTG |  | Marketing | Advertisements | Accounts list Advertisements | In-feed banner advertisements on the Accounts List screen |  | Completed 11/21/2020 | NA | To Do | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 07 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-04
SOW287 |  | Sagar | GTG |  | Accounts | Accounts | Remove Consolidated Accounts | Ability to edit/remove consolidated accounts - this is hide / show accounts (favoriting) | Need more clarity on requirement | Completed 11/21/2020 | NA | To Do | 2020-12-02 | Jack | In Progress | 2020-12-02 | Bhavesh | In Progress | 2020-12-04 | NA | NA | 2020-12-11 | Sagar | In progress | Azfar & Jeff | Approved 11/21 | 2020-12-11 | To Do | 2020-12-11 | 2020-12-18 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 04 | Sprint 02 | #REF! | #REF! | 2021-01-06 | OOTB | Team 2 | 1900-01-03
SOW112 | 101, 105 | Sagar | GTG | Okta Dependency | Authentication | Login | Load permissions->Dynamic Permissions and Entitlements | Fetch the list of permissions and entitlements for the logged-in customer. These permissions define the behavior and availability of features for a specific customer. AI3 - Entitlements to control data sharing access permissions and viewing of data results on a per client and user level CF5 - Access will be entitlement driven at the client and user level | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-04 | Jack V | In progress | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | Drafted | 2020-12-10 | Sagar | In Progress | Azfar & Jeff | Approved 11/22 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 01 | Sprint 11 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-09
SOW261 |  | Sagar | GTG |  | Administration | Transaction and Audit Logs | Transactional Logs | View the logs of all the transactions initiated with the OLB and mobile app channels and filter the results CF5 - Access will be entitlement driven at the client and user level |  | Completed 11/21/2020 | NA | NA | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 12 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 1 | 1900-01-09
SOW262 |  | Sagar | GTG |  | Administration | Transaction and Audit Logs | Admin console Audit Logs | View the logs of all the actions performed by employees within the Administration console |  | Completed 11/21/2020 | NA | NA | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 12 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 1 | 1900-01-04
SOW263 |  | Sagar | GTG |  | Administration | Transaction and Audit Logs | Customer Activity Logs | View the activities of a customer/member on the OLB and mobile app channels, along with the changes made by employees to a customer's profile |  | Completed 11/21/2020 | NA | NA | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 12 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 1 | 1900-01-04
SOW309 |  | Sagar | Need further discussion | with Product | Business Banking Dashboard | Email | Email | Displays the registered email |  | Week of 12/7/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Christina & Jason | 2020-12-28 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 11 | Sprint 10 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 1 | 1900-01-01
SOW31 |  | Sagar | Need further discussion | with Product | Business Banking Dashboard | Registered phone number | Registered phone number | Displays the registered phone number |  | Week of 12/7/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Christina & Jason | 2020-12-28 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 11 | Sprint 10 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 1 | 1900-01-01
SOW78 |  | Sagar | GTG |  | User Interface | Date format | Set date formats | Set Date Format to below Time Stamp Date Format should be MMM DD, YYYY The MMM should be alpha characters and display the abbreviation for the month, and there should be a comma after the two-digit numerical date The year should be the numerical 4 year format Time zone should be MDT |  | Completed 11/21/2020 | NA | NA | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 12 | Sprint 12 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-19
SOW197 |  |  | Temenos to present User stories and workflows | Requirement for Combined User | Customer Service | Contact Us | View customer care contact information | View contact numbers and email ids for customer care. |  | Week of 12/7/2020 | Naj | To Do | 2020-12-04 | Jack V | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | Christa | Complete | 2020-12-10 | Rodrigo Ferreira | To Do | Christina & Jason | 2020-12-28 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 02 | Sprint 02 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-01
SOW132 |  | Sagar | Need Services discussion |  | Accounts | Accounts | Accounts | Quick Balance - Show a quick snapshot of account balances to a user even without logging into the application. Information displayed on this screen is encrypted and displays real-time balance of user accounts. This service can be enabled by customers who require it . |  | Week of 12/7/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-11-27 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Christina & Jason | 2020-12-28 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 04 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 1 | 1900-01-09
SOW210 |  |  | GTG | Similar to SOW 132 | Personalization | User Preferences | Turn on or off Quick Balance | Settings for Quick Balance - Show a quick snapshot of account balances to a user even without logging into the application. Information displayed on this screen is encrypted and displays real-time balance of user accounts. This service can be enabled by customers who require it . |  | Completed 11/21/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | Christa |  | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 03 | Sprint 04 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-04
SOW244 |  | Sagar | GTG |  | Administration | Customer Service | Update customer details and preferences | Product/Accounts owned | More clarity needed | Completed 11/21/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2021-01-04 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 10 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-05
SOW245 |  | Sagar | GTG |  | Administration | Customer Service | Update customer details and preferences | Activity History | More clarity needed | Completed 11/21/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2021-01-04 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 11 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-05
SOW246 |  | Sagar | GTG |  | Administration | Customer Service | Update customer details and preferences | Requests/Messages |  | Completed 11/21/2020 | NA | To Do | 2020-12-04 | Jack | To Do | 2021-01-04 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 11 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-05
SOW248 |  | Sagar | GTG |  | Administration | Customer Service | Update customer details and preferences | Groups and Entitlements |  | Completed 11/21/2020 | NA | To Do | 2020-12-04 | Jack | To Do | 2021-01-04 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 11 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-05
SOW170 |  | Sagar | GTG |  | Transfers | Fund Transfers | Transfer to own account in other financial institutions | Add a new account in another domestic bank/CU as an external account (recipient) to the profile, by providing account information. Users can transfer funds to the external account once it has been verified and activated. |  | Completed 11/21/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG | CreateExternalTransfer UpdateExternalTransfer DeleteExternalTransfer GetExternalTransfers | To Do | L3 | OOTB without Customization | Sprint 05 | Sprint 05 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-07 | This is referreing to Me2ME transfer
SOW171 |  | Sagar | GTG |  | Transfers | Fund Transfers | Transfer to another person's account in same financial institution | Add other members of the same bank as recipients by providing their Account Number, Account Type (Checking/Savings), Account Holder's Name/Beneficiaries Name, and Nickname details. |  | Completed 11/21/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG | CreateExternalTransfer UpdateExternalTransfer DeleteExternalTransfer GetExternalTransfers | To Do | L3 | OOTB without Customization | Sprint 05 | Sprint 05 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-14 | To double check if the same set of API are used for Domestic as well
SOW172 |  | Sagar | GTG |  | Transfers | Fund Transfers | Transfer to another person's account in other financial institution | Add members of other banks as recipients by providing their Account Number, Bank Name, Account Type (Checking/Savings), Account Holder's Name /Beneficiary's Name, and Nickname details. |  | Completed 11/21/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG | CreateExternalTransfer UpdateExternalTransfer DeleteExternalTransfer GetExternalTransfers | To Do | L3 | OOTB without Customization | Sprint 05 | Sprint 05 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-14 | To double check if the same set of API are used for Domestic as well
SOW282 |  |  | Temenos to present User stories and workflows |  | Transfers | External Accounts | Manage External Bank accounts | Update nickname and remove external accounts added for transfers |  | Week of 12/7/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Rodrigo Ferreira | To Do | Christina & Jason | 2020-12-28 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 07 | Sprint 05 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-11
SOW251 |  |  | Requirements with Temenos |  | Accounts | Account Dashboard | Dashboard | The default landing screen for the application; shows accounts list, a summary of messages and notifications received. Applies to Retail, SBB and Combined Dashboard. This does not include the CODAT integration |  | Week of 12/7/2020 | Naj | To Do | 2020-12-04 | Jack | To Do | 2020-12-07 | Bhavesh | To Do | 2020-12-10 | Christa | Complete | 2020-12-10 | Rodrigo Ferreira | To Do | Christina & Jason | 2020-12-28 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 09 | Sprint 03 | Sprint 03 | #REF! | #REF! | 2021-01-20 | OOTB | Team 2 | 1900-01-09
SOW138 |  |  | Temenos to present User stories and workflows |  | Accounts | Transactions | Transaction Search | Transaction Search Current Search Capabilities are documented in the linked documents. Here is a summary: Show most recent transactions in the following increments 5,10, 15, 50, or 100 in the last 15 days (50 is default) User needs to see 50 transactions per page. By Date Range: From Date, to Date (calendar Selector) (five years is max) By Month for the last 12 months. (Drop Down Menu) Advanced Search Options: All Statement Items (default) Deposits only Withdrawals Cheques Bill Payments Search by Descriptor Search by Cheque Number Search by Amount Search by Confirmation Number The User can select the display format . These include: On Screen with details (Date, Description, Credits, Debits, Balance)* this is the default On Screen without details (Date, Limited Description, Credits, Debits, Balance) |  | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack | To Do | 2020-12-10 | Bhavesh | To Do | 2020-12-10 | 2020-12-08 | 2020-12-09 | 2020-12-10 | Rodrigo Ferreira | To Do | Christina & Jason | 2020-12-09 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L3 | New Feature | Sprint 09 | Sprint 06 | Sprint 03 | #REF! | #REF! | 2021-01-20 | New Feature | Team 4 | 1900-02-08
SOW326 |  |  | Temenos to present User stories |  | Payments & Withdrawals | CRA Fund Transfer | CRA and Provincial Tax Form UI | Develop UI for all CRA and Provincial Tax Forms | NA | L2 Story Review Already Scheduled | Naj | To Do | 2020-12-10 | Jack | To Do | 2020-12-10 | Bhavesh | To Do | 2020-12-10 | 2020-12-08 | 2020-12-09 | 2020-12-10 | Grant | To Do | Christina & Jason | 2020-12-09 | 2020-12-17 | To Do | 2020-12-17 | 2020-12-31 | BIG |  | To Do | L2 | New Feature |  | Sprint 05 | Sprint 03 | #REF! | #REF! | 2021-01-20 | New Feature | Team 4 | 1900-05-09
SOW259 |  | Sagar | GTG |  | Administration | Application Content Management | Manage Service Outage Messages | Manage service outage messages that get displayed to the customers - this would be the outage message that the bank sets in Spotlight and outage messages for when different MS API's fail |  | Completed 11/21/2020 | NA | NA | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | Complete | Christa | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 1 | 1900-01-09
SOW268 |  | Sagar | GTG |  | Business Entitlements | User Management | Manage User | Allows Administrators manage Users | To be clarified with CWB. To organise a session | Week of 12/7/2020 | NA | NA | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | Complete | Christa | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-09
SOW269 |  | Sagar | GTG |  | Business Entitlements | User Management | View All Users | Allows Administrators to view list of Users | To be clarified with CWB. To organise a session | Week of 12/7/2020 | NA | NA | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | Complete | Christa | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-07
SOW27 |  | Sagar | GTG |  | Business Entitlements | User Management | User Management - Activate / Deactivate | Confirmation screen on activating/deactivating a User | To be clarified with CWB. To organise a session | Week of 12/7/2020 | NA | NA | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | Complete | Christa | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-05
SOW271 |  | Sagar | GTG |  | Business Entitlements | User Management | Bill Pay Transaction Approval | Invoking integration service after approval process of Bill Pay Transactions | To be clarified with CWB. To organise a session | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | Complete | Christa | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-05
SOW272 |  | Sagar | GTG |  | Business Entitlements | User Management | Transfer transactions Approval | Invoking integration service after approval process of Transfer Transactions | To be clarified with CWB. To organise a session | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | Complete | Christa | Complete | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-05
SOW266 |  | Sagar | GTG |  | Business Entitlements | User Management | Create User | Allows Administration to create a Business Banking User in DBX System | To be clarified with CWB. To organise a session | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 12 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 1 | 1900-01-04
SOW267 |  | Sagar | GTG |  | Business Entitlements | User Management | Customize Email Template for User Creation | Brand & Content update for user creation email that is sent to users when they are created by the account signer | To be clarified with CWB. To organise a session | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 12 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 1 | 1900-01-09
SOW9 |  | Sagar | GTG |  | Business Entitlements | User Management | Manage User Permissions | Micro-Feature Level Entitlement in DBX Within features there are several micro-features (or functions) that are available. For example, in Bill Pay a user who has access to that module can: Add Payee Delete Payee Create Transaction Edit & Cancel Transaction View History (all) Etc. CWB is looking for an entitlement that allows the client to assign a feature and then sub/micro features as they may want a user to be able to transact a bill payment but not modify the payees list or see the entire history. AI3 - Entitlements to control data sharing access permissions and viewing of data results on a per client and user level CF5 - Access will be entitlement driven at the client and user level | To be clarified with CWB. To organise a session | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 013 | Sprint 11 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-03
SOW91 |  | Sagar | GTG |  | Business Entitlements | User Management | Manage User Permissions | Feature Level Entitlements in DBX CWB needs the ability to allow clients to set feature level permissions. In the SBB demo app it appears the top level is the Role, then the admin can select the accounts and limits for transaction types. If the account has the entitlements to Bill Pay and Wires, the delegate user (if they have the Create Role) can create transactions for both features. The gap is that the client needs to be able to select ‘For this account, the user can make Bill Pay transactions but not Wire transactions’ AI3 - Entitlements to control data sharing access permissions and viewing of data results on a per client and user level CF5 - Access will be entitlement driven at the client and user level | To be clarified with CWB. To organise a session | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 013 | Sprint 11 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-07
SOW93 |  | Sagar | GTG |  | Business Entitlements | User Management | Manage User Permissions | Templatizing user roles in DBX CWB currently has the ability for Commercial clients to templatize user roles For example, they can set up a user role as Create, with X account access and X transaction limits. Then they can ‘Save as Template’ and assign the template to future users CWB will have to have this for Commercial and the expectation is that it can be rolled back to the SBB platform once implemented. | To be clarified with CWB. To organise a session | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 07 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-11
SOW24 |  |  | Temenos to present User stories and workflows |  | Administration | Customer Management | Manage customer groups | These groups define the set of customers/members that the financial institution may want to categorize on various criteria. Every service assigned to a group is an entitlement for the end user. Users may also have some additional entitlements assigned to them outside of the groups. |  | Week of 12/14 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | Christa | To Do | 2020-12-10 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-11 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 03 | Sprint 11 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-11
SOW240 |  |  | Temenos to present User stories and workflows | Linked to SOW 250 | Administration | Customer Management | Search and view customer details | Front desk employees or member care may be required to view certain details of customers/members from time to time to provide assistance. Member care employees can search for a customer, view details of the customer, lock / unlock the customer, as well as turn on or off specific services for a customer |  | Week of 12/14 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | Christa | To Do | 2020-12-10 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-11 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 03 | Sprint 11 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-11
SOW283 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit Provincial Business Tax (separate forms from CRA) | NA | L2 Story Review Already Scheduled | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-12-10 | Bhavesh | To Do | 2020-12-10 | Adam | To Do | 2020-12-10 | Grant | To Do | Christina & Jason | 2020-12-11 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L2 | New Feature | Sprint 06 | Sprint 11 | Sprint 04 | #REF! | #REF! | 2021-02-02 | New Feature | Team 4 | 0
SOW70 |  |  | Temenos to present User stories |  | Payments & Withdrawals | CRA Fund Transfer | View CRA Payment History | Ability to view payment history | NA | L2 Story Review Already Scheduled | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-12-10 | Bhavesh | To Do | 2020-12-10 | Adam | To Do | 2020-12-10 | Grant | To Do | Christina & Jason | 2020-12-11 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L2 | New Feature | Sprint 06 | Sprint 11 | Sprint 04 | #REF! | #REF! | 2021-02-02 | New Feature | Team 4 | 1900-01-19
SOW286 |  | Sagar | GTG |  | Business Entitlements | User Management | Manage Delegate Access to Consolidated Accounts | Ability to grant access to delegates to access consolidated accounts, define permissions for each account | To be clarified with CWB. To organise a session | Week of 12/7/2020 | Naj | To Do | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-14
SOW296 | 101, 105 | Sagar | GTG | Okta Dependency | Authentication | Login | Load permissions | Fetch the list of permissions and entitlements for the logged-in customer. These permissions define the behavior and availability of features for a specific customer | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 11 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-03
SOW83 |  |  | Temenos to present User stories and workflows |  | Accounts | Transactions | Pagination | Increase pagination beyond 10 transactions at a time. The requirement is to allow User to see 50 per page. Parameter of the pagination has to be passed to MS, need a cursor value back for next and previous transaction pages. |  | Week of 12/7/2020 | Naj |  | 2020-12-10 | Jack V | To Do | 2020-12-10 | Bhavesh | To Do | 2020-12-10 | Christa | To Do | 2020-12-10 | Rodrigo Ferreira | To Do | Christina & Jason | 2020-12-11 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | New Feature | Sprint 08 | Sprint 06 | Sprint 04 | #REF! | #REF! | 2021-02-02 | New Feature | Team 3 | 1900-04-29
SOW285 |  | Sagar | GTG |  | Accounts | Accounts | Consolidate Accounts: account signer | Ability to allow account signer to consolidate personal and Business accounts - this is part of the flexible dashboard and is done in Spotlight to consolidate |  | Completed 11/21/2020 | NA | NA | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 2 | 1900-01-07 | Dependent on Sprint 01 getAccountList
SOW140 |  | Sagar | Need further discussion |  | Accounts | Accounts | Statements - Settings | Activate Paperless Statements |  | Week of 12/7/2020 | Naj |  | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Christina & Jason | 2021-01-11 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 09 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 1 | 1900-01-01
SOW141 |  | Sagar | GTG |  | Accounts | Accounts | Statements | View and Download Statements |  | Completed 11/21/2020 | NA | NA | 2020-12-10 | Jack V | To Do | 2020-08-31 | Bhavesh | To Do | 2020-12-10 | NA | NA | 2020-12-10 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2020-12-17 | To Do | 2020-12-31 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 09 | Sprint 08 | Sprint 04 | #REF! | #REF! | 2021-02-02 | OOTB | Team 1 | 1900-01-05
SOW216 |  | Sagar | GTG |  | Notifications | Alert Settings | Manage payment and transfer alerts | To include Push, SMS, Secure Message Center and Email Alerts AP5 - Users can select preferred channels for Insight delivery via profile preferences. Insight content will be generated based on the channel (secure v. non secure) | This will be looked on case by case basis with the current alerts Setup | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-07
SOW265 |  | Sagar | Need further development |  | Administration | Master Data Management | Manage Alert Configuration | Activate / deactivate alerts (account alerts, security, promotional alerts, etc), as well as define the alert message content within Spotlight |  | Week of 12/14 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | Complete | 2020-12-28 | Sagar | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-11
SOW308 |  |  | GTG | Okta Dependency | Profile Management | Contact Address | Contact Address | Displays the registered contact address | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | Christa |  | 2020-12-28 | Rodrigo Ferreira | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 11 | Sprint 10 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-04
SOW235 |  | Sagar | Need further discussion on Group ID , Company mapping |  | Administration | Employee Management | Create a Company | Fetching Accounts while adding a Company |  | Week of 12/14 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 12 | Sprint 11 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-03
SOW136 |  | Sagar | GTG |  | Accounts | Accounts | New Account Opening - Current Customer | New deposit account opening application - Pre-Login was de-scoped, post login will be an authenticated redirect to the DCO application or re-use the services that have been built for DCO. | API Delivered | Completed 11/21/2020 | Naj | Completed | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG | addProduct | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1899-12-31 | Delviered as part DCO on boarding Digital program
SOW236 |  | Sagar | GTG |  | Administration | Employee Management | Manage employee roles | Define various roles for internal users in Administration Console. Each employee can be assigned to one role. | To chcked transact dependency | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 02 | Sprint 11 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-03
SOW237 |  | Sagar | GTG |  | Administration | Employee Management | Manage employee permissions | Multiple permissions can be assigned to a role. All permissions assigned to a role apply to users in that role, but additional permissions can be assigned to a specific user. | To chcked transact dependency | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 03 | Sprint 11 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-05
SOW34 |  |  | Temenos to present User stories and workflows (Need to be reviewed) |  | Foreign Exchange | Rate Display | FX Rate Display | Display info on buying or selling US cash, cheques or traveler's cheques exchange rates. (C1 Returns the exchange rates from the institution) | NA | L2 Story Review Already Scheduled Week of 11/30/2020 | 2020-12-18 | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | Adam |  | 2020-12-28 | Santiago | In Progress CWB to reply to Santiago's email - Sunil and Charlotte | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L2 | New Feature | Sprint 03 | Sprint 07 | Sprint 05 | #REF! | #REF! | 2021-02-17 | New Feature | Team 4 | 1900-01-09
SOW35 |  |  | Temenos to present User stories and workflows (Need to be reviewed) |  | Foreign Exchange | Calculator | FX Calculator | FX calculator to assist users while converting foreign currencies to CAD or vice versa - User inputs a value, currency to and from and can generate a quote for the exhange rage. | NA | L2 Story Review Already Scheduled Week of 11/30/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | Adam |  | 2020-12-28 | Santiago | In Progress CWB to reply to Santiago's email - Sunil and Charlotte | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L2 | New Feature | Sprint 03 | Sprint 07 | Sprint 05 | #REF! | #REF! | 2021-02-17 | New Feature | Team 4 | 1900-01-14
SOW60 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Transaction / Payment Receipts | Ability to view list of bill payments, with the option to manage each transaction ( i.e. print and download each receipt). The list can contain the beneficiary name, transaction description, type, from account, transaction ID, date, status, amount | NA | Week of 12/14/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | Adam |  | 2020-12-28 | Santiago | In Progress CWB to reply to Santiago's email - Sunil and Charlotte | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L2 | New Feature | Sprint 013 | Sprint 07 | Sprint 05 | #REF! | #REF! | 2021-02-17 | New Feature | Team 3 | 1900-02-08
SOW238 |  | Sagar | GTG |  | Administration | Employee Management | Manage employees’ user accounts | Specific users (e.g. administrators) can create, update, delete, suspend (temporary), deactivate (permanent) employee accounts for admin console. An email is sent to the new user when his/her profile is created. | To chcked transact dependency | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 11 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-09
SOW239 |  |  | Temenos to present User stories and workflows | Available OOTB | Administration | Employee Management | Employee login | Employees can sign in by entering a username and password combination. The application also helps the employees to reset their password pre- and post-login. Will require an integration to OKTA |  | Week of 12/14 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | Christa | To Do | 2020-12-28 | Rodrigo Ferreira | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 04 | Sprint 11 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-07
SOW247 |  | Sagar | GTG |  | Administration | Customer Service | Update customer details and preferences for alerts | Notifications/Offers available; Alert settings within Spotlight AP5 - Users can select preferred channels for Insight delivery via profile preferences. Insight content will be generated based on the channel (secure v. non secure) |  | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 04 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-05
SOW201 |  | Sagar | GTG | Okta Dependency | Profile Management | Communication Details | Manage address, phone, email details | Ability for users to view/update their profile – includes contact information (email ID, phone number, address). | OKTA | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | Christa | To Do | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 06 | Sprint 10 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-05
SOW302 |  |  | Remove this line item as only Business taxes are considered. Personal taxes are part of OOTB Bill Pay |  | Bill Payment | Pay Personal Taxes | Remit Tax via Bill Pay Module for Personal Taxes | Ability to remit Provincial personal taxes (separate biller in the list for bill payments - 3-4 payees/vendors for Personal). CRA "Vendor" list for Personal Tax Payments (included in payee list for personal tax payments). This will not be a different flow than the Bill Pay feature - will be part of the payee list that is returned. Form data is the same | NA | L2 Story Review Already Scheduled | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | Adam | To Do | 2020-12-28 | Grant | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L2 | New Feature | Sprint 06 | Sprint 07 | Sprint 05 | #REF! | #REF! | 2021-02-17 | New Feature | Team 4 | 0
SOW215 |  | Sagar | Need further development |  | Notifications | Alert Settings | Manage account specific alerts | To include Push, SMS, Secure Message Center and Email Alerts AP5 - Users can select preferred channels for Insight delivery via profile preferences. Insight content will be generated based on the channel (secure v. non secure) |  | Week of 12/21/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 07 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-05
SOW25 |  | Sagar | GTG |  | Administration | Customer Service | Message templates | Create and update message templates that can be used while communicating with customers via messages |  | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 07 | Sprint 12 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-03
SOW274 |  | Sagar | GTG - Tiered approvals are available |  | Business Entitlements | Approvals & Requests | Approve General Transaction | Administrator or Authorizer approves a Transfer | T24 | Completed 11/21/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 07 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-07 | To find existiing or new API to be developed
SOW284 |  | Sagar | Need to check the Transact/Infinity mapping |  | Accounts | Accounts | Consolidate Accounts: user | Ability to consolidate multiple accounts - this is to show all of the accounts the user has with CWB on one dashboard and is driven by the Core system. Infinity to display list of accounts as received by T24; this is part of base and the API's will have to be developed to go through Mulesoft to obtain the list of accounts related to the users CIF. |  | Week of 12/7/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 07 | Sprint 10 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-11
SOW278 |  | Sagar | GTG |  | Business Entitlements | Approvals & Requests | Reject transactions | Reject different transaction types | T24 | Completed 11/21/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-07 | To find existiing or new API to be developed
SOW279 |  | Sagar | GTG |  | Business Entitlements | Approvals & Requests | Requests | Displays list of transactions initiated by User. Transaction Types are General Transactions | T24 | Completed 11/21/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 08 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-07 | To find existiing or new API to be developed
SOW192 |  | Sagar | Need further development |  | Notifications | Push Notifications | Receive push notifications | Receive push notifications, powered by the underlying Kony Digital Banking platform |  | Week of 12/21/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 09 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 1 | 1900-01-03
SOW217 |  | Sagar | Need further development |  | Notifications | Alert Settings | Manage security alerts | To include Push, SMS, Secure Message Center and Email Alerts AP5 - Users can select preferred channels for Insight delivery via profile preferences. Insight content will be generated based on the channel (secure v. non secure) |  | Week of 12/21/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 09 | Sprint 09 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-05
SOW252 |  | Sagar | GTG |  | Administration | Reports | User login reports | Standard reports around customer log in attempts will be available out of the box, with the option to generate custom reports in real time |  | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 09 | Sprint 10 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-09
SOW253 |  | Sagar | GTG |  | Administration | Reports | Transaction reports | Standard reports around banking transactions will be available out of the box, with the option to generate custom reports in real time | To be checked with Sudha on the current integration | Completed 11/21/2020 | NA | NA | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 09 | Sprint 10 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2 | 1900-01-11
SOW264 |  | Sagar | GTG |  | Administration | Master Data Management | Manage Services and Limits | Control various aspects of services e.g. transaction limits, fees/charges, availability schedule. Limits may be applicable for all customers/members or only to a certain group; administrators can view and update these limits. Back-end only | To be checked with Sudha on the current integration | Completed 11/21/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | NA | NA | 2020-12-28 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | OOTB without Customization |  | Sprint 11 | Sprint 05 | #REF! | #REF! | 2021-02-17 | OOTB | Team 2
SOW TBD |  | Grant | Temenos to present User stories and workflows |  | Check Management | Stop Check Payment | Stop check payment | Stop Check Payment for Pre-Authorized Payment |  | Week of 12/21/2020 | Naj | To Do | 2020-12-28 | Jack V | To Do | 2020-12-28 | Bhavesh | To Do | 2020-12-28 | Adam | To Do | 2020-12-28 | Rodrigo Ferreira | To Do | Christina & Jason | 2020-12-30 | 2021-12-28 | To Do | 2021-01-04 | 2021-01-15 | BIG |  | To Do | L3 | New Feature | Sprint 03 | Sprint 05 | Sprint 05 | #REF! | #REF! | 2021-02-17 | New Feature | Team 4 | 1900-01-09
SOW260 |  | Sagar | GTG - Prelogin | Post login needs to have Business and Retail specific Customer Care info displayed based on Customer Profile | Administration | Application Content Management | Manage Customer Care Information | Manage Customer Care Information (phone numbers and email ids) - Generic and service level |  | Completed 11/21/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | Complete | NA | Complete | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 10 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-03
SOW84 |  | Sagar | GTG |  | Administration | Audit Trail | Audit Trail of Business User Activity | Displays list of all events initiated by a business users, event type, time etc. CF6 - Enable user activity tracking and analysis for all cash flow features and provide automate data extracts to enable billing AP7 - Enable user activity tracking and analysis for Insights and provide automated data extracts to facilitate biling (as needd) |  | Completed 11/21/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L2 | OOTB without Customization | Sprint 10 | Sprint 12 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-04
SOW289 |  | Sagar | GTG |  | Administration | System Logs | System Login | Captures the system log in, log out and related information at the bank admin level |  | Completed 11/21/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 11 | Sprint 12 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 2 | 1900-01-04
SOW315 |  | Sagar | GTG |  | Accounts | Transactions | View Check Images | View the back/front check images of specific transactions On-us cheques only | Gerry W - 12/4/2020 | Week of 12/14/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 11 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-04
SOW88 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Pay Business Taxes | CRA "Vendor" list for Small Business Banking | Enhance vendor list or create new Vendor list in Spotlight to allow input of Canadian Revenue Agency (CRA) payees. This is specific to Canada. Today, the vendor list that exists in Spotlight is used to Bill Pay vendors, e.g. AT&T, Netflix, PayPal, etc. Similarly, there are CRA vendors for paying country-wide and provincial payees. This would function like a bill pay vendor list, but needs a focus for CRA vendors. Requirements include everything from the existing vendor list. This is required if we are to move away from storing these in Central 1. | NA | L2 Story Review Already Scheduled | Naj |  | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | Adam | To Do | 2021-01-08 | Grant | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L2 | New Feature | Sprint 12 | Sprint 08 | Sprint 06 | #REF! | #REF! | 2021-03-03 | New Feature | Team 4 | 1900-01-09
SOW198 |  |  | GTG |  | Customer Service | Contact Us | Click to call or text-message | Ability to call, email the bank. |  | Completed 11/21/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | Christa | To Do | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 02 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 2 | 1900-01-02
SOW21 |  | Sagar | Need further discussion |  | Personalization | User Preferences | Security settings | Reset the list of security questions, as well as the secure access code delivery option |  | Week of 12/28/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Christina & Jason | 2021-01-25 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 03 | Sprint 10 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-07
SOW188 |  | Sagar | GTG |  | Check Management | Remote Deposit Capture | View pending and recent deposits | View a list of recent check deposits, sorted by date (most recent on top). Pending will not be displayed; only past | Gerry W - 12/4/2020 Kofax | Week of 12/14/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 03 | Sprint 05 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-03
SOW189 |  | Sagar | GTG |  | Check Management | Remote Deposit Capture | View check images | For specific transactions, view the back / front check images. Only on-us checks will display and will come from DOXIM; is dependent upon integration with MS and Doxim. | Gerry W - 12/4/2020 DOXIM | Week of 12/14/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 03 | Sprint 05 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-03
SOW169 |  |  | Temenos to present User stories and workflows |  | Transfers | Fund Transfers | Beneficiary management | View the recipients added to the profile so that the user can initiate transfers to a recipient, edit a recipient’s details, or delete the recipient the user no longer wishes to transfer money to and view the transfer history for a recipient. |  | Week of 12/7/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | Christa | To Do | 2021-01-08 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-25 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 2 | 1900-01-11
SOW299 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Pay Business Taxes | Add CRA Business Account Number | Ability to add CRA Business Account Number registered to file taxes | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | Adam | To Do | 2021-01-08 | Grant | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L2 | New Feature | Sprint 06 | Sprint 08 | Sprint 06 | #REF! | #REF! | 2021-03-03 | New Feature | Team 4 | 1900-02-18
SOW301 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Pay Business Taxes | Delete CRA Business Account Number | Ability to delete CRA Business Account Number registered to file | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | Adam | To Do | 2021-01-08 | Grant | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L2 | New Feature | Sprint 06 | Sprint 08 | Sprint 06 | #REF! | #REF! | 2021-03-03 | New Feature | Team 4 | 1900-01-29
SOW163 |  |  | Temenos to present User stories and workflows |  | Transfers | e-Transfer | Activate / Register for e-Transfer | Activate e-Transfer payment services, so that the user can send and receive money via email ID or mobile number. By default, the email ID and phone number registered with the bank should be displayed for confirmation to use for P2P payments, but the user should be able to edit them. In case the user has multiple eligible accounts, s/he should be able to select a specific account for this service. |  | Week of 11/30/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 06 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-04
SOW164 |  |  | Temenos to present User stories and workflows |  | Transfers | e-Transfer | Send money | Send money via e-Transfer transfers to a person the user may or may not have added as a recipient. The user should be able to set up a recurring e-Transfer transfer for any of the previously added recipients. |  | Week of 11/30/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 06 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-07
SOW165 |  |  | Temenos to present User stories and workflows |  | Transfers | e-Transfer | Schedule P2P transfer for future date | Assign a future date for e-Transfer payment instead of paying immediately. Possible to set up recurring payments as well. |  | Week of 11/30/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 06 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-11
SOW166 |  |  | Temenos to present User stories and workflows |  | Transfers | e-Transfer | Update or cancel scheduled e-Transfers | In case of a scheduled future-dated e-Transfer transfer, ability to modify the details or cancel the e-Transfer transfer. |  | Week of 11/30/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 06 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-07
SOW167 |  |  | Temenos to present User stories and workflows |  | Transfers | e-Transfer | View history of e-transfers | View and search from a list of recent e-Transfer transfers and scheduled transfers, sorted by date (most recent on top). |  | Week of 11/30/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 06 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-05
SOW176 |  | Sagar | GTG |  | Transfers | Fund Transfers | Update or cancel scheduled transfers | In case of a scheduled future-dated transfer, ability to modify the details, or cancel the transfer. |  | Completed 11/21/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 06 | Sprint 04 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 2 | 1900-01-07 | Exisiting APIs to be reused from the previous SPRINTS Transfer STANDING.ORDER
SOW249 |  | Sagar | GTG |  | Administration | Customer Service | Messages and requests | Member care employees can view all messages sent by the end user using the secure messaging feature of the mobile/online banking application and respond to these messages, initiate new messages, view, search, filter as well as route messages to specific employees |  | Completed 11/21/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 07 | Sprint 12 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-07
SOW250 |  | Sagar | GTG |  | Administration | Customer Service | Remote screen impersonation | Impersonation tool for the customer service representative. The tool allows a member care employee to sign in as a member in view-only mode to help the member with troubleshooting. All actions will be logged for auditing purposes. CSR assist option will be available only for those customer profiles who have provided their consent for the same. |  | Completed 11/21/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 07 | Sprint 12 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-11
SOW254 |  | Sagar | GTG |  | Administration | Reports | Secure message reports | Standard reports around messaging will be available out of the box, with the option to generate custom reports in real time |  | Completed 11/21/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 07 | Sprint 12 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 2 | 1900-01-03
SOW168 |  |  | Temenos to present User stories and workflows |  | Transfers | e-Transfer | Manage e-Transfer recipient | View a list of registered e-Transfer recipients, create a new e-Transfer recipient either manually or by importing from the device contacts list, modify/delete a recipient's details if desired, send/request money to/from a selected recipient, and view the e-Transfer transfer history associated with a selected recipient. |  | Week of 11/30/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 07 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-14
SOW68 |  |  | Temenos to present User stories |  | Transfers | Fund Transfers | Cross Currency Transfer | Ability to make cross-currency transfers between Canadian and U.S. dollar accounts | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | Adam | To Do | 2021-01-08 | Santiago | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L2 | New Feature | Sprint 09 | Sprint 11 | Sprint 06 | #REF! | #REF! | 2021-03-03 | New Feature | Team 4 | 1900-01-02
SOW137 |  | Sagar | GTG |  | Accounts | Transactions | Transactions | Recent and Pending Transactions in base - only posted transactions are supported via the CWB core - not pending transactions will be displayed |  | Completed 11/21/2020 | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG | GetAccountTransactions | To Do | L3 | OOTB without Customization | Sprint 09 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-14
SOW14 |  | Sagar | GTG |  | Accounts | Transactions | Print Transactions | Print transactions |  | Completed 11/21/2020 | NA | NA | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | NA | NA | 2021-01-08 | Sagar | To Do | Azfar & Jeff | Approved 11/21 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 09 | Sprint 06 | Sprint 06 | #REF! | #REF! | 2021-03-03 | OOTB | Team 1 | 1900-01-09
SOW44 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Pay Business Taxes | Search for a CRA Biller | Ability for client to search for a biller that is not a saved bill payee - specific to CRA Vendor | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | Adam | To Do | 2021-01-08 | Grant | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L2 | New Feature |  | Sprint 08 | Sprint 06 | #REF! | #REF! | 2021-03-03 | New Feature | Team 3 | 1900-01-19
SOW97 |  |  | Temenos to present User Stories and workflows |  | User Interface | Menu | Navigation and Configuration | Deliver a configurable menu in Release 1 (not a customization that would impact future upgrades). They require two sections for money movement at the top hierarchy of the menu structure: Transfers – includes only internal A2A and external A2A transfers) Payments – includes all other payment type CRA (Tax Payments) Bill Pay EFT / ACH eTransfers (P2P) – This mean splitting the transfers module into two and adding restrictions Wires (Domestic and International) CWB requests Product team take this item Note - 9/18 - EFT is no longer in scope for Release 1 and is in the backlog | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-01-08 | Jack V | To Do | 2021-01-08 | Bhavesh | To Do | 2021-01-08 | Adam | To Do | 2021-01-08 | Santiago | To Do | Christina & Jason | 2021-01-08 | 2021-01-15 | To Do | 2021-01-29 | 2021-02-12 | BIG |  | To Do | L2 | New Feature |  | Sprint 08 | Sprint 06 | #REF! | #REF! | 2021-03-03 | New Feature | Team 3 | 1900-01-19
SOW66 |  |  | Temenos to present User stories |  | Transfers | Interac Funds Transfer | Validate interac transfer | Ability to validate the beneficiary details for interac (base doesn't validate, enter only). | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Adam | To Do | 2021-01-15 | Grant | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L2 | New Feature | Sprint 11 | Sprint 09 | Sprint 07 | #REF! | #REF! | 2021-03-17 | New Feature | Team 3 | 1900-05-29
SOW89 |  |  | Temenos to present User stories |  | Payments & Withdrawals | CRA Fund Transfer | CRA Direct Deposit | The ability to set up direct deposit to recieve funds from CRA. This applies to Personal and SBB | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Adam | To Do | 2021-01-15 | Grant | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L2 | New Feature | Sprint 013 | Sprint 11 | Sprint 07 | #REF! | #REF! | 2021-03-17 | New Feature | Team 4 | 1900-01-14
SOW311 |  | Sagar | Needs further discussion on 3rd party |  | Check Management | Remote Deposit Capture | Deposit a check | Choose an account into which you deposit a check, specify the amount, add a note, take pictures of the check (front and back images), and initiate a remote deposit. | Gerry W - 12/4/2020 Kofax | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | NA | NA | 2021-01-15 | Sagar | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB without Customization | Sprint 03 | Sprint 05 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-04
SOW323 |  |  | CWB: Dependent on the identified Vendor by Dec 4th |  | Check Management | Remote Deposit Capture | Check capture & compression /resizing of check and validations using third parties | Check capture & compression /resizing of check and validations using third parties | Gerry W - 12/4/2020 Kofax | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 03 | Sprint 05 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-08
SOW162 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Manage billers (add, update, delete) | View a list of registered bill payees, view history of bills paid to a company, update the payee details or delete the payee account. Search for a previously added bill payee from a list of all bill payees for easy access |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 04 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-23
SOW142 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay Enrollment | Activate Bill Payment for a user | Option for user to accept the T&C and activate Bill Pay service for his profile. |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 03 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-11
SOW143 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | Initiate a new bill payment to a payee added to the profile by providing the From account, payee nickname, amount, transfer date, and optional recurrence details and notes. |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-09
SOW144 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | Search A biller - Biller details page will be appeared in the same screen. Browse for payees by browsing from pre-defined payee type categories such as Insurance, Property, Schools and Utilities. |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-04
SOW145 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | Biller details Page |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-01
SOW146 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | Payment Amount |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1899-12-31
SOW147 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | Frequency Selection page |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1899-12-31
SOW148 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | Duration selection |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-01
SOW149 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | Start Date |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1899-12-31
SOW15 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | End Date |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-01
SOW150 |  |  | Temenos to present User stories and workflows |  | Bill Payment | Bill Pay | Pay a registered biller | Send Date |  | Week of 12/14/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-01
SOW151 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Recurrence # page |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-01
SOW152 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Confirmation of Payment details |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1899-12-31
SOW153 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Mobile Number Capture screen for Phone recharge |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1899-12-31
SOW154 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Relation Number capture screen |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-01
SOW155 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Pay a registered biller | Policy Number capture screen for Insurance Payments |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-01
SOW158 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Pay multiple bills together |  |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-09
SOW16 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Schedule a bill pay | Assign a future date for bill payment instead of paying immediately. Possible to set up recurring payments as well |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-03
SOW160 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | Update or Cancel scheduled bill payments | In case of a scheduled future-dated bill payment, ability to modify the details or cancel the payment. |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 05 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-07
SOW3 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Pay Business Taxes | Remit Tax | Ability to remit CRA Business Tax (sepearate forms from Provincial Business Tax) | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Adam | To Do | 2021-01-15 | Grant | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-02-19 | BIG |  | To Do | L2 | New Feature | Sprint 06 | Sprint 10 | Sprint 07 | #REF! | #REF! | 2021-03-17 | New Feature | Team 4 | 0
SOW161 |  |  | Temenos to present User stories and workflows |  | Payments & Withdrawals | Bill Pay | View history of bill payments | View and search from a list of the recent bill payment and scheduled payments, sorted by date (most recent on top). |  | Week of 12/28/2020 | Naj | To Do | 2021-01-15 | Jack V | To Do | 2021-01-15 | Bhavesh | To Do | 2021-01-15 | Christa | To Do | 2021-01-15 | Rodrigo Ferreira | To Do | Christina & Jason | 2021-01-18 | 2021-01-22 | To Do | 2021-02-05 | 2021-01-29 | BIG |  | To Do | L3 | OOTB with Customization | Sprint 06 | Sprint 07 | Sprint 07 | #REF! | #REF! | 2021-03-17 | OOTB | Team 1 | 1900-01-09
SOW61 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Transaction receipts | Tax Payments Transactions - Receipts and History | Ability to view list of tax payments, with the option to manage each transaction ( i.e. print and download each receipt). The list can contain the beneficiary name, transaction description, type, from account, transaction ID, date, status, amount | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Grant | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | 2021-02-15 | L2 | New Feature | Sprint 11 | Sprint 10 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 3 | 1900-02-08
SOW7 |  |  | Temenos to present User stories |  | Payments & Withdrawals | CRA Fund Transfer | CRA Fund Transfer | Ability to perform multiple transfers to and from different accounts at the same time (similar to bulk transfer - paying one tax payment from multiple accounts or multiple tax payments at the same time). | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Grant | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | 2021-02-15 | L2 | New Feature | Sprint 04 | Sprint 10 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 4 | 1900-02-08
SOW69 |  |  | Temenos to present User stories |  | Payments & Withdrawals | CRA Fund Transfer | CRA Fund Transfer | Ability to file or remit, initiate immediate transfer, scheduled, recurring, transfers, delete scheduled transfers and view/modify | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Grant | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | 2021-02-15 | L2 | New Feature | Sprint 06 | Sprint 10 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 4 | 1900-01-19
SOW30 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Pay Business Taxes | View Payment | Ability to view payment | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Grant | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | 2021-02-15 | L2 | New Feature | Sprint 07 | Sprint 10 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 4 | 1900-02-18
SOW300 |  |  | Temenos to present User stories |  | Payments & Withdrawals | Pay Business Taxes | File Taxes and Filing History | Ability to view filing history and File business taxes | NA | L2 Story Review Already Scheduled | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Grant | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | 2021-02-15 | L2 | New Feature | Sprint 07 | Sprint 10 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 4 | 1900-02-18
SOW290 |  |  | Temenos to present User stories | Recall is for pending approvals; not required for Post approvals | Approvals and Request | Transactions | Recall Transactions | Small Business Pre approved User Transactions: Able to recall transaction that have been rejected by the initiating signer or for which the requester wants to discontinue processing (post approval) | NA | Week of 12/21/2020 | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Santiago | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | To Do | L2 | New Feature | Sprint 08 | Sprint 11 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 3 | 1900-01-09
SOW291 |  |  | Temenos to present User stories |  | Approvals and Request | Transactions | Expired Transactions | Small Business Pre approved User Transactions. List of transaction that have expired For scheduled payments, if the date of the first payment / cutoff times is surpassed the payment moves into the expired listing. Requirement is to have one place for the client to manage all of their payments for SBB; should be able to one aggregated payment listing with all payment statuses and payment types. Would include EFT (ACH), eTransfers, Bill Pay, Transfers, Wires in one list. Be able to filter the list, expand the list details, download the list (filtered / not filtered). Will be critical for Corporate. At minimum for release 1, having a listing of all the payments in one listing with all payment statuses with filtering ability. EFT is OK for post release 1, but def needed for Corporate. Note - 9/18 - EFT is no longer in scope for Release 1 and is in the backlog | NA | Week of 12/21/2020 | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Santiago | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | 2021-02-15 | L2 | New Feature | Sprint 09 | Sprint 11 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 3 | 1900-02-18
SOW292 |  |  | Temenos to present User stories |  | Approvals and Request | Transactions | List of Approved, Rejected, Pending approval by Business user | A list of approved, Rejected, Pending approval by Business user. Requirement is to have one place for the client to manage all of their payments for SBB; should be able to one aggregated payment listing with all payment statuses and payment types. Would include EFT (ACH), eTransfers, Bill Pay, Transfers, Wires in one list. Be able to filter the list, expand the list details, download the list (filtered / not filtered). Will be critical for Corporate. At minimum for release 1, having a listing of all the payments in one listing with all payment statuses with filtering ability. EFT is OK for post release 1, but def needed for Corporate. Note - 9/18 - EFT is no longer in scope for Release 1 and is in the backlog | NA | Week of 12/21/2020 | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Santiago | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | 2021-02-15 | L2 | New Feature | Sprint 09 | Sprint 11 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 3 | 1900-02-18
SOW325 | Approvals and Request |  | Temenos to present User stories |  | Approvals and Request | Transactions | Include Expired and Recalled into the list of Approved, Rejected, and Pending approval by Business user | SPLIT FROM SOW292 Small Business Users: Adding listing A list of approved, Rejected, Recalled, Pending approval or Expired by Business user. Requirement is to have one place for the client to manage all of their payments for SBB; should be able to one aggregated payment listing with all payment statuses and payment types. Would include EFT (ACH), eTransfers, Bill Pay, Transfers, Wires in one list. Be able to filter the list, expand the list details, download the list (filtered / not filtered). Will be critical for Corporate. At minimum for release 1, having a listing of all the payments in one listing with all payment statuses with filtering ability. EFT is OK for post release 1, but def needed for Corporate. Note - 9/18 - EFT is no longer in scope for Release 1 and is in the backlog | NA | Week of 12/21/2020 | Naj | To Do | 2021-02-05 | Jack V | To Do | 2021-02-05 | Bhavesh | To Do | 2021-02-05 | Adam | To Do | 2021-02-05 | Santiago | To Do | Christina & Jason | 2021-02-08 | 2021-02-12 | To Do | 2021-02-26 | 2021-03-12 | BIG |  | To Do | L2 | New Feature |  | Sprint 07 | Sprint 08 | #REF! | #REF! | 2021-03-21 | New Feature | Team 3 | 1900-04-09
SOW258 |  |  | Complete |  | Administration | Application Content Management | Manage Terms and Conditions content | Create and manage the terms and conditions content that gets displayed to the customers |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | NA | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 10 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 1 | 1900-01-03
SOW193 |  |  | Complete |  | Customer Service | Secure Messaging | Send new message | Send and receive messages to and from the bank/CU, as a secure channel of communication with the bank. Messages sent to and received from the Bank/CU will support text, images, URLs and allow capability for sending and receiving files as attachments securely. |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 2 | 1900-01-04
SOW194 |  |  | Complete |  | Customer Service | Secure Messaging | Reply to a message | Reply to messages to and from the bank/CU, as a secure channel of communication with the bank. Messages sent to and received from the Bank/CU will support text, images, URLs and allow capability for sending and receiving files as attachments securely. |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 2 | 1900-01-04
SOW195 |  |  | Complete |  | Customer Service | Secure Messaging | View list of inbound and sent messages | View list of messages sent and received group by subject as threads. |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 2 | 1900-01-11
SOW196 |  |  | Complete |  | Customer Service | Secure Messaging | View list of deleted messages | View list of deleted messages. |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 2 | 1900-01-05
SOW199 |  |  | Complete |  | Customer Service | Self Help | FAQ | Contextual Frequently Asked Questions - this will be a linkout to a CWB web browser page |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 2 | 1899-12-31
SOW2 |  |  | Complete |  | Customer Service | Self Help | Help | This will be a linkout to a CWB web browser page |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 2 | 1899-12-31
SOW224 |  |  | Complete |  | Terms & Conditions | Terms & Conditions | Terms and Conditions | This includes the ability to view terms and conditions to use the banking application, view privacy policy of the bank. |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 2 | 1900-01-05
SOW129 |  |  | Complete |  | Accounts | Accounts | Accounts | Accounts List |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Bhavesh | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 1 | 1900-01-03
SOW200 |  |  | Complete |  | Customer Service | Customer Feedback | Provide feedback (Ratings, Comments, Feature Requests) | Request for a feature/service from the bank as a part of the feedback.: FEEDBACK LINK IN-APP; Feedback link post logout is not required |  |  | Complete |  |  |  |  | Complete | Bhavesh |  | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason |  | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 02 |  | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 1 | 1900-01-07
SOW191 |  |  | Complete |  | Notifications | Notification Center | Notification Center | View a list of all the notifications the bank has sent; the user can also delete notifications that has already been read. |  |  | Complete |  |  |  |  | Complete | Bhavesh |  | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason |  | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 09 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 1 | 1900-01-07
SOW218 |  |  | Complete |  | Locations | Locations | Find the nearest ATM or branch | Find the nearest ATM/branch based on your device current location or search by using postal code, city, or state details. - this will be a linkout to Sitecore UI and display in an iFrame |  |  | Complete |  |  |  |  | Complete | Bhavesh |  | Complete | Complete | Complete | Complete | Complete | Complete | Christina & Jason |  | Complete | Complete |  | Complete | Complete | Complete | Complete | L3 | Dev Completed | Sprint 09 | Sprint 02 | SPRINT 99 - DONE | #N/A | #N/A | To Do | OOTB | Team 1 | 1900-01-02
SOW257 |  | Sagar | Not Required |  | Administration | Application Content Management | View Credentials Policies | View the credential policy definitions |  | Post R1 | Naj | Post R1 | Post R1 | Post R1 | Post R0 | Post R1 | Bhavesh |  | Post R1 | NA | Post R1 | Post R1 | TBD | Post R1 | Christina & Jason | Post R1 | Post R1 | Post R1 | NA? | Post R1 | BIG |  | Post R1 | L3 | OOTB without Customization | Sprint 10 | Sprint 10 | Sprint 99 - Post R1 | #N/A | #N/A | Post R1 | OOTB-R2 | Team 1 | 1900-01-05
SOW298 |  |  | Future Release: Linked to Wires and EFT | Okta Dependency | Authentication | Multi-factor Authentication | Multi-factor Authentication - Post Login Scenarios | Multi-factor authentication and step-up authentication; for example, by using OTP ( phone or email), Facial Authentication, challenge questions, and more | OKTA | Post R1 | NA | NA | Post R1 | Jack V | Post R1 | Post R1 | Bhavesh | Post R1 | Post R1 | Christa | Post R1 | Post R1 | TBD | Post R1 | Christina & Jason | Post R1 | NA | To Do |  | Post R1 | BIG |  | Post R1 | L3 | OOTB with Customization | Sprint 11 | Sprint 10 | Sprint 99 - Post R1 | #N/A | #N/A | Post R1 | OOTB-R2 | Team 1 | 1900-01-07
SOW62 |  |  | Not required |  | Accounts | Transactions | Pending Transactions | Remove pending transactions. They will not be displayed on the transactions dashboard. |  | Post R1 | Naj | Post R1 | Post R1 |  |  | Post R1 | Bhavesh |  | Post R1 | Christa | Post R1 | Post R1 | TBD | Post R1 | Christina & Jason | Post R1 | Post R1 | Post R1 |  | Post R1 | BIG |  | Post R1 | L3 | OOTB with Customization | Sprint 09 | Sprint 06 | Sprint 99 - Post R1 | #N/A | #N/A | Post R1 | OOTB-R2 | Team 4 | 1900-01-05