## Aug 9 - Plan (4)
Temenos | Sprint 21 |  | Sprint 22 (2 weeks) Stabilization/Defect Fixing | [41 empty] | Go Live
| Jun 14 - Jun 25 (2 weeks) (WE ARE HERE) |  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
Last Sprint Development | time axis 2021-06-28 to 2021-08-09
|  |  | Sprint 21 Demo/ Dplymnt | [41 empty] | Go Live
CWB-SIT | CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB SIT/QA02
DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E
| Jun 14 - Jun 25 (WE ARE HERE) |  | 2021-06-28: Jun 28 - Jul 2; 2021-07-03: Weekend; 2021-07-05: Jul 5 - 9; 2021-07-10: Weekend; 2021-07-12: Jul 12 - 16 E2E (Adrian is off); 2021-07-17: Weekend; 2021-07-19: Jul 19 - 23 E2E/Regression; 2021-07-24: Weekend; 2021-07-26: Jul 26 - 30 Regression/Go-No Go Week (Susan is off); 2021-07-31: Weekend; 2021-08-02: Aug 2-6 Go Live Prep Week (Susan is off); 2021-08-09: Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
| DATA MIGRATION Process Testing with Test Profiles/ E2E Test Set Data |  | 2021-06-28: Data Migration Process Testing
| - Sprint 20 Testing - Defects retesting - Test scenario development (E2E) |  | 2021-06-28: E2E Kick Off Sprint 21 Testing Functional with NON-migrated data; 2021-07-05: Successful completion of DM Process testing 1. E2E - with migrated data 2. PCR Testing; 2021-08-02: Go Live Prep Week
2pm
| Defect Triage everyday |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage Fraud Trng | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Go/No Go (PM) | [5 empty] | CAB Approval 2pm
CWB-UAT | CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT
|  |  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
| CWB-UAT environment set up Prep work for BAT and NFR Testing Deploy Sprint 20 and validate |  | 2021-06-28: Validate environment Logon account setup; 2021-07-05: Validate; 2021-07-12: Validate Get it ready for Pen/Security and Performance and BAT; 2021-07-19: BAT Exection Week Pen/Security Testing Performance Testing; 2021-07-26: Pen/Security Testing Performance Testing
Last day of Navaera training
|  |  | 200+ defects | [6 empty] | 300+ defects
Alerts
Other Spillovers
|  | 1. CWB-UAT: week of Jun 21-25, deploy Sprint 20 and validate enviroment, set up accounts, can does SL need to be pointed to CWB-UAT, OKTA? | 2021-07-14: Might need to do deployments Friday afternoon, less interruption/downtime
|  | 2. Schedeul Daily Triage with Christina, Biz Team | 2021-07-14: BAT will need to complete before Regression/Go-No Go week
3. Do we have what we need for E2E? What do we need to prep now?
4. Summary format for defects
minimum requirements for Spotlight configurations to be done so QA Team can start testing
QA Team needs to figure out - what we can test first? Doesn't require spotlight configurations
should cover migrated data, which set of "test data" can we use? We need to set them up.
Sprint 21
Build
Build
Sprint 21
Prod
Candidate
Build

## DM Plan
Data Migration - QA Test Plan/Timeline - SILO, Test Profiles preparation, E2E testing
Task # | Activities | Start Date | End Date | Status | Task Owner | Dependencies (refers to Task #) | Notes
SILO Testing Phase
1 | Cycle 1 | 2021-04-14 | 2021-04-23 | completed | QA Team (Adrian)
2 | Cycle 2 | 2021-04-27 | 2021-05-05 | completed | QA Team (Adrian) |  | •Cycle 2 of DM output files/tables validation complete (C1 and T24) – for OKTA •Cycle 2 of DM audit/reconciliation process validation complete for OKTA/Infinity and C1
3 | Cycle 3/3A | 2021-05-11 | 2021-05-14 | completed | QA Team (Adrian) |  | •Retesting for bugs from Cycle 2
4 | Cycle 4 | 2021-05-13 | 2021-06-16 | not started | QA Team (Adrian) | Infinity finishing development by Jun 16 | •Waiting for code from Infinity •Testing for Infinity
4A | Requirements/Traceability Matrix Review | 2021-06-10 | 2021-06-18 | in progress | Steve Kelcher |  | -Review with DM, QA and Business teams -Findings from review may or may not impact Test Data Preparation, Testing of PCR and E2E activities
5 | Test Data Preparation - Test Profiles | May | 2021-06-25 | in progress
6 | Identified test profiles ("master" profiles) | May | May | completed |  | #4A | QA Team has reviewed test profiles for test coverage (4 profiles, will only test with 2 profiles - Profiles A and B)
7 | Create Master Profiles in STDIG and complete DM process | May | 2021-06-18 | in progress | DM Team | #4A
8 | Perform initial tests with test "master" profile | 2021-06-18 | 2021-06-18 | not started | DM and QA Team | #4A | DM Team and QA Team
9 | Prepare Data for E2E Testing
10 | Select set of test data (profiles from production that match "master" profiles to be used for E2E) | 2021-06-14 | 2021-06-18 | not started | QA Team | #4A, #8 | Adam to provide list accounts from production QA Team to review, select/match, prepare list of test accounts
11 | Create CIF/profiles in T24 for test data (SITDIG) | 2021-06-21 | 2021-06-25 | not started | QA Team | #4A, #10 | Possibly use Automation Team's help
12 | Spotlight configurations and other setup | 2021-06-21 | 2021-06-25 | not started | QA Team | #4A, #11 | QA Team
| Data Migration Process | 2021-06-21 | 2021-06-25 | not started
12A | Prepared Test data going through DM Process | 2021-06-21 | 2021-06-25 | not started |  | #4, #4A, #5 | Coordination QA, OKTA and Infinity Teams (latest morning of Jun 28, or the weekend of Jun 26-27) DM Process: • Request C1 and T24 extracts (C1 need a couple of days notice but delivered with 30 mins…about the same for T24) • Create PAN List (basically a list of the CIFs we want to migrate) – 5 mins • Run DM jobs to process the files – 5 mins • Load file into OKTA – OKTA sends back an audit/log file – 10 mins • Infinity processes the load tables to do its part of the migration (timing unknown) • Run reconciliation and DM process end jobs to complete the process – 5 mins
12B | If 12A does not complete: Manually create test data | 2021-06-21 | 2021-06-25 | TBD (only if needed) |  | #4, #4A, #5 | Coordination QA, OKTA and Infinity Teams -latest morning of Jun 28, -or the weekend of Jun 26-27 - E2E can still happen, but it will not be testing DM E2E process/with migrated data
12 | Testing of PCR 004 (Login for migrated and non-migrated users) | May | 2021-06-25 | in progress
13 | Development for PCR 004 | May | 2021-06-11 | completed | C1/Mark |  | Error message routine completed. Need requirements for final messaging and URL to redirect to.
14 | Requirements to implement correct verbiage and URL to redirect to | TBD | TBD | not started | UX Team | #13
15 | Test case development | TBD | 2021-06-25 | not started | QA Team | #14 |  | 90 days notice for clients Aug 9 - go live - is with the test profiles, to play in prod
16 | Test data | TBD | 2021-06-18 | in progress | QA Team | #5, #9 |  | Eddie, Infinity, C1, Okta, Dapo - timeline
17 | Test environment | TBD | 2021-06-25 | in progress | Andrew | Temenos sprint delivery | CWB-SIT - with latest T24, Infinity, OKTA, Spotlight configurations required for redirection process
18 | Test execution | 2021-06-21 | 2021-06-25 | not started | QA Team | #5, #12-#17
19 | E2E (CWB-SIT) | 2021-06-28 | 2021-07-30 |  |  |  | Start of E2E
20 | PCR 004 implementation in CWB-SIT | 2021-06-18 | 2021-06-25 | completed | Mark | #12
21 | E2E test scenario development | 2021-05-06 | 2021-06-25 | in progress | QA Team |  |  | test profiles - 4 profiles: ret, sb no del/with, staff - "master profile"
22 | Execute E2E with test profiles | 2021-06-28 | 2021-07-23 | not started | QA Team | Temenos sprint delivery #4, #4A, #5, #12
| DM Mock Runs/Dry Run/Dress Rehearsal |  |  |  | DM Team |  | Separate plan and timeline, QA Team will assist where/when needed
23 | Test environment - TBD |  |  |  | Andrew P |  | TBD - pre-prod environment
SILO testing cycle - Validating the output files from C1 and T24 - taking source files/data from C1 and T24 and processing to generate/produce the output files for OKTA and INFINITY to consume Validating the audit/reconciliation process for OKTA and Infinity - reconciliation for OKTA and Infinity - work for OKTA is in progress - using mock-up file for Infinity (as Infinity is not yet complete)
Steve | requirements/traceability matrix review may impact tests
done by end of next week - June 18
PCR 004 | •Overall test approach is as follows: - validate that migrated account will be redirected to Infinity platform, non-migrated account will be redirected to Central1 platform •T24 work is underway to handle migrated users when they log (DB07) • Front-end user journey flow (end-user experience) is TBD - Until we know what the redirection process is for either a migrated or non-migrated user, the QA team will not be able to develop test cases because we need to base our test steps and expected results from the final redirection process. • Redirection process testing will be covered during E2E phase | *C1 successfully disabling alerts
Profile A
a1 - staff
a2 - non-staff
Profile B
business, no delegates

## DM Plan - Revised
Data Migration - QA Test Plan/Timeline - SILO, Test Profiles preparation, E2E testing
Task # | Activities | Start Date | End Date | Status | Task Owner | Dependencies (refers to Task #) | Notes
SILO Testing Phase
1 | Cycle 1 | 2021-04-14 | 2021-04-23 | completed | QA Team (Adrian)
2 | Cycle 2 | 2021-04-27 | 2021-05-05 | completed | QA Team (Adrian) |  | •Cycle 2 of DM output files/tables validation complete (C1 and T24) – for OKTA •Cycle 2 of DM audit/reconciliation process validation complete for OKTA/Infinity and C1
3 | Cycle 3/3A | 2021-05-11 | 2021-05-14 | completed | QA Team (Adrian) |  | •Retesting for bugs from Cycle 2
4 | Cycle 4 (Part 3) | 2021-05-13 | 2021-06-23 | not started | QA Team (Adrian) | Infinity finishing development by Jun 16 | •Waiting for code from Infinity •Testing for Infinity
4A | Requirements/Traceability Matrix Review | 2021-06-10 | 2021-06-18 | in progress | Steve Kelcher |  | -Review with DM, QA and Business teams -Findings from review may or may not impact Test Data Preparation, Testing of PCR and E2E activities
5 | Test Data Preparation - Test Profiles | May | 2021-06-25 | in progress
6 | Identified test profiles ("master" profiles) | May | May | completed |  | #4 | QA Team has reviewed test profiles for test coverage (4 profiles, will only test with 2 profiles - Profiles A and B)
7 | Create Master Profiles in STDIG and complete DM process | May | 2021-06-25 | in progress | DM Team | #4 | need to complete Cycle 4
8 | Perform initial tests with test "master" profile | 2021-06-18 | 2021-06-25 | not started | DM and QA Team | #4 | DM Team and QA Team
9 | Prepare Data for E2E Testing | [5 empty] | This task can be done independently/separately
10 | Select set of test data (profiles from production that match "master" profiles to be used for E2E) | 2021-06-14 | 2021-06-18 | in progress | QA Team | #4A, #8 | Adam has provided list accounts from production QA Team to review, select/match, prepare list of test accounts
11 | Create CIF/profiles in T24 for test data (SITDIG) | 2021-06-21 | 2021-06-25 | not started | QA Team | #4A, #10 | Possibly use Automation Team's help
12 | Spotlight configurations and other setup | 2021-06-21 | 2021-06-25 | not started | QA Team | #4A, #11 | QA Team
| Validate Data Migration Process | 2021-06-21 | 2021-06-25 | not started
12A | Prepared Test data going through DM Process | 2021-06-21 | 2021-06-25 | not started |  | #4, #4A, #5 | Coordination QA, OKTA and Infinity Teams (latest morning of Jun 28, or the weekend of Jun 26-27) DM Process (approximately between 1 and 2 hours to complete): • Request C1 and T24 extracts (C1 need a couple of days notice but delivered with 30 mins…about the same for T24) • Create PAN List (basically a list of the CIFs we want to migrate) – 5 mins • Run DM jobs to process the files – 5 mins • Load file into OKTA – OKTA sends back an audit/log file – 10 mins • Infinity processes the load tables to do its part of the migration (TBD/timing unknown) • Run reconciliation and DM process end jobs to complete the process – 5 mins
12B | Plan B - if 12A does not complete in time Manually create test data | 2021-06-21 | 2021-06-25 | TBD (only if needed) |  | #4, #4A, #5 | Coordination QA, OKTA and Infinity Teams -latest morning of Jun 28, -or the weekend of Jun 26-27 - E2E can still happen, but it will not be testing DM E2E process/with migrated data
13 | Testing of PCR 004 (Login for migrated and non-migrated users) | May | 2021-06-25 | in progress
14 | Development for PCR 004 | May | 2021-06-11 | completed | C1/Mark |  | Error message routine completed. Need requirements for final messaging and URL to redirect to.
15 | Requirements to implement correct verbiage and URL to redirect to | TBD | TBD | not started | UX Team | #14 | Mark has emailed UX team - what do they want will need to iron out how to test this, chat with adrian
16 | Test case development | TBD | 2021-06-25 | not started | QA Team | #15 |  | 90 days notice for clients Aug 9 - go live - is with the test profiles, to play in prod
17 | Test data | TBD | 2021-06-18 | in progress | QA Team | #5, #9 |  | Eddie, Infinity, C1, Okta, Dapo - timeline
18 | Test environment | TBD | 2021-06-25 | in progress | Andrew | Temenos sprint delivery | CWB-SIT - with latest T24, Infinity, OKTA, Spotlight configurations required for redirection process
19 | Test execution | 2021-06-21 | 2021-06-25 | not started | QA Team | #5, #13-#18
20 | E2E (CWB-SIT) | 2021-06-28 | 2021-07-30 |  |  |  | Start of E2E
21 | PCR 004 implementation in CWB-SIT | 2021-06-18 | 2021-06-25 | completed | Mark | #13
22 | E2E test scenario development | 2021-05-06 | 2021-06-25 | in progress | QA Team |  |  | test profiles - 4 profiles: ret, sb no del/with, staff - "master profile"
23 | Execute E2E with test profiles | 2021-06-28 | 2021-07-23 | not started | QA Team | Temenos sprint delivery #4, #4A, #5, #13
| DM Mock Runs/Dry Run/Dress Rehearsal |  |  |  | DM Team |  | Separate plan and timeline, QA Team will assist where/when needed
23 | Test environment - TBD |  |  |  | Andrew P |  | TBD - pre-prod environment
SILO testing cycle - Validating the output files from C1 and T24 - taking source files/data from C1 and T24 and processing to generate/produce the output files for OKTA and INFINITY to consume Validating the audit/reconciliation process for OKTA and Infinity - reconciliation for OKTA and Infinity - work for OKTA is in progress - using mock-up file for Infinity (as Infinity is not yet complete)
Steve | requirements/traceability matrix review may impact tests
done by end of next week - June 18
PCR 004 | •Overall test approach is as follows: - validate that migrated account will be redirected to Infinity platform, non-migrated account will be redirected to Central1 platform •T24 work is underway to handle migrated users when they log (DB07) • Front-end user journey flow (end-user experience) is TBD - Until we know what the redirection process is for either a migrated or non-migrated user, the QA team will not be able to develop test cases because we need to base our test steps and expected results from the final redirection process. • Redirection process testing will be covered during E2E phase | *C1 successfully disabling alerts
Profile A
a1 - staff
a2 - non-staff
Profile B
business, no delegates

## Aug 9 - Template
Temenos | Sprint 21 | Sprint 22 (2 weeks) Stabilization/Defect Fixing | [41 empty] | Go Live
| Jun 14 - Jun 25 (2 weeks) (WE ARE HERE) | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
Last Sprint Development | time axis 2021-06-28 to 2021-08-09
|  |  | Sprint 21 Demo | [40 empty] | Go Live
CWB-SIT | CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB SIT
| DATA MIGRATION | 2021-08-09: Go Live
| Jun 14 - Jun 25 (WE ARE HERE) | 2021-06-28: Jun 28 - Jul 2; 2021-07-03: Weekend; 2021-07-05: Jul 5 - 9; 2021-07-10: Weekend; 2021-07-12: Jul 12 - 16 E2E Adrian is off; 2021-07-17: Weekend; 2021-07-19: Jul 19 - 23 E2E/Regression; 2021-07-24: Weekend; 2021-07-26: Jul 26 - 30 Regression/Go-No Go Week (Susan is off); 2021-07-31: Weekend; 2021-08-02: Aug 2-6 Go Live Prep Week; 2021-08-09: Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
END to END
| Jun 14 - Jun 25 (WE ARE HERE) | 2021-06-28: Jun 28 - Jul 2; 2021-07-03: Weekend; 2021-07-05: Jul 5 - 9; 2021-07-10: Weekend; 2021-07-12: Jul 12 - 16 E2E Adrian is off; 2021-07-17: Weekend; 2021-07-19: Jul 19 - 23 E2E/Regression; 2021-07-24: Weekend; 2021-07-26: Jul 26 - 30 Regression/Go-No Go Week (Susan is off); 2021-07-31: Weekend; 2021-08-02: Aug 2-6 Go Live Prep Week; 2021-08-09: Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
- Sprint 20 Testing - Defects retesting - Test case development (E2E)
CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT
|  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
CWB-UAT environment set up Prep work for BAT Pen/Security Testing Performance Testing
BAT Execution Week
Pen/Security Testing
Performance Testing
minimum requirements for Spotlight configurations to be done so QA Team can start testing
QA Team needs to figure out - what we can test first? Doesn't require spotlight configurations
should cover migrated data, which set of "test data" can we use? We need to set them up.

## Aug 9 - Plan
Temenos | Sprint 21 | Sprint 22 (2 weeks) Stabilization/Defect Fixing | [41 empty] | Go Live
| Jun 14 - Jun 25 (2 weeks) (WE ARE HERE) | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
Last Sprint Development | time axis 2021-06-28 to 2021-08-09
|  |  | Sprint 21 Demo/ Dplymnt | [40 empty] | Go Live
CWB-SIT | CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB SIT
| DATA MIGRATION | 2021-08-09: Go Live
| Jun 14 - Jun 25 (WE ARE HERE) | 2021-06-28: Jun 28 - Jul 2; 2021-07-03: Weekend; 2021-07-05: Jul 5 - 9; 2021-07-10: Weekend; 2021-07-12: Jul 12 - 16 E2E Adrian is off; 2021-07-17: Weekend; 2021-07-19: Jul 19 - 23 E2E/Regression; 2021-07-24: Weekend; 2021-07-26: Jul 26 - 30 Regression/Go-No Go Week (Susan is off); 2021-07-31: Weekend; 2021-08-02: Aug 2-6 Go Live Prep Week; 2021-08-09: Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
|  |  | Sprint 21 Demo/ Dplymnt | DM Process Testing |  |  |  |  | DM Process Testing
DATA MIGRATION and END TO END
| Jun 14 - Jun 25 (WE ARE HERE) | 2021-06-28: Jun 28 - Jul 2; 2021-07-03: Weekend; 2021-07-05: Jul 5 - 9; 2021-07-10: Weekend; 2021-07-12: Jul 12 - 16 E2E Adrian is off; 2021-07-17: Weekend; 2021-07-19: Jul 19 - 23 E2E/Regression; 2021-07-24: Weekend; 2021-07-26: Jul 26 - 30 Regression/Go-No Go Week (Susan is off); 2021-07-31: Weekend; 2021-08-02: Aug 2-6 Go Live Prep Week; 2021-08-09: Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
|  |  | Sprint 21 Demo/ Dplymnt | DM Process Testing |  |  |  |  | DM Process Testing
| - Sprint 20 Testing - Defects retesting - Test case development (E2E) | 2021-06-29: Sprint 21 Demo/ Dplymnt; 2021-06-30: E2E - Functional with non-migrated data; 2021-07-05: E2E - Functional with non-migrated data; 2021-07-07: Successful completion of DM Process testing 1. E2E - with migrated data 2. PCR Testing
|  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage
CWB-UAT | CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT
|  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
| CWB-UAT environment set up Prep work for BAT and NFR Testing | 2021-06-28: Deploy Sprint 20 Validate environment Logon account setup; 2021-07-05: Validate; 2021-07-12: Validate; 2021-07-16: -Deploy latest sprint -validate; 2021-07-19: BAT Exection Week Pen/Secutiry Testing Performance Testing
minimum requirements for Spotlight configurations to be done so QA Team can start testing
QA Team needs to figure out - what we can test first? Doesn't require spotlight configurations
should cover migrated data, which set of "test data" can we use? We need to set them up.

## Aug 9 - Plan (2)
Temenos | Sprint 21 |  | Sprint 22 (2 weeks) Stabilization/Defect Fixing | [41 empty] | Go Live
| Jun 14 - Jun 25 (2 weeks) (WE ARE HERE) |  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
Last Sprint Development | time axis 2021-06-28 to 2021-08-09
|  |  |  | Sprint 21 Demo/ Dplymnt | [40 empty] | Go Live
CWB-SIT | CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB - SIT CWB-SIT CWB-SIT CWB-SIT CWB SIT
DATA MIGRATION and END TO END
| Jun 14 - Jun 25 (WE ARE HERE) |  | 2021-06-28: Jun 28 - Jul 2; 2021-07-03: Weekend; 2021-07-05: Jul 5 - 9; 2021-07-10: Weekend; 2021-07-12: Jul 12 - 16 E2E (Adrian is off); 2021-07-17: Weekend; 2021-07-19: Jul 19 - 23 E2E/Regression; 2021-07-24: Weekend; 2021-07-26: Jul 26 - 30 Regression/Go-No Go Week (Susan is off); 2021-07-31: Weekend; 2021-08-02: Aug 2-6 Go Live Prep Week (Susan is off); 2021-08-09: Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
| Data Migration Process Testing with Test Profiles/ E2E Test Set Data |  | 2021-06-29: Sprint 21 Demo/ Dplymnt; 2021-06-30: DM Process Testing; 2021-07-05: DM Process Testing
| - Sprint 20 Testing - Defects retesting - Test case development (E2E) |  | 2021-06-29: Sprint 21 Demo/ Dplymnt; 2021-06-30: E2E - Functional with non-migrated data; 2021-07-05: E2E - Functional with non-migrated data; 2021-07-07: Successful completion of DM Process testing 1. E2E - with migrated data 2. PCR Testing
2pm
| Defect Triage everyday |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Go/No Go (PM) | [5 empty] | CAB Approval 2pm
CWB-UAT | CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT
|  |  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
| CWB-UAT environment set up Prep work for BAT and NFR Testing Deploy Sprint 20 and validate |  | 2021-06-28: Validate environment Logon account setup; 2021-07-05: Validate; 2021-07-12: Validate; 2021-07-19: BAT Exection Week Pen/Secutiry Testing Performance Testing
|  | 1. CWB-IAT: week of Jun 21-25, deploy Sprint 20 and validate enviroment, set up accounts, can does SL need to be pointed to CWB-UAT, OKTA? | 2021-07-14: Might need to do deployments Friday afternoon, less interruption/downtime
|  | 2. Schedeul Daily Triage with Christina, Biz Team | 2021-07-14: BAT will need to complete before Regression/Go-No Go week
3. Do we have what we need for E2E? What do we need to prep now?
4. Summary format for defects
minimum requirements for Spotlight configurations to be done so QA Team can start testing
QA Team needs to figure out - what we can test first? Doesn't require spotlight configurations
should cover migrated data, which set of "test data" can we use? We need to set them up.
Sprint 21
Build
Build
Sprint 20
Build
Sprint 21
Prod
Candidate

## Aug 9 - Plan (3)
Temenos | Sprint 21 |  | Sprint 22 (2 weeks) Stabilization/Defect Fixing | [41 empty] | Go Live
| Jun 14 - Jun 25 (2 weeks) (WE ARE HERE) |  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
Last Sprint Development | time axis 2021-06-28 to 2021-08-09
|  |  | Sprint 21 Demo/ Dplymnt | [41 empty] | Go Live
CWB-SIT | CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB SIT/QA02
DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E
| Jun 14 - Jun 25 (WE ARE HERE) |  | 2021-06-28: Jun 28 - Jul 2; 2021-07-03: Weekend; 2021-07-05: Jul 5 - 9; 2021-07-10: Weekend; 2021-07-12: Jul 12 - 16 E2E (Adrian is off); 2021-07-17: Weekend; 2021-07-19: Jul 19 - 23 E2E/Regression; 2021-07-24: Weekend; 2021-07-26: Jul 26 - 30 Regression/Go-No Go Week (Susan is off); 2021-07-31: Weekend; 2021-08-02: Aug 2-6 Go Live Prep Week (Susan is off); 2021-08-09: Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
| DATA MIGRATION Process Testing with Test Profiles/ E2E Test Set Data |  | 2021-06-29: DM update ETA EOD; 2021-07-02: Date issue!; 2021-07-05: Data Migration Process Testing Transition from Adrian
| - Sprint 20 Testing - Defects retesting - Test scenario development (E2E) |  | 2021-06-28: E2E Kick Off Sprint 21 Testing Functional with NON-migrated data; 2021-07-05: Sprint 21, Spillover Testing Functional with NON-migrated data; 2021-07-12: Successful completion of DM Process testing 1. E2E - with migrated data 2. PCR Testing; 2021-08-02: Go Live Prep Week
2pm
| Defect Triage everyday |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage Fraud Trng | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Defect Triage |  |  | Defect Triage | Defect Triage | Defect Triage | Defect Triage | Go/No Go (PM) | [5 empty] | CAB Approval 2pm
CWB-UAT | CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT
|  |  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon
 | time axis 2021-06-28 to 2021-08-09
| CWB-UAT environment set up Prep work for BAT and NFR Testing Deploy Sprint 20 and validate |  | 2021-06-28: Validate environment Logon account setup; 2021-07-05: Validate; 2021-07-12: Validate Get it ready for Pen/Security and Performance and BAT; 2021-07-19: BAT Exection Week Pen/Security Testing Performance Testing; 2021-07-26: Pen/Security Testing Performance Testing
Last day of Navaera training
|  |  | 200+ defects | [6 empty] | 300+ defects | [13 empty] | jul 19-29
[10 empty] | Alerts | [13 empty] | jul 21-jul 29
[10 empty] | Other Spillovers | [13 empty] | jul 26-29
jul 12 - partner can access, troubleshoot issues if need be
|  | 1. CWB-UAT: week of Jun 21-25, deploy Sprint 20 and validate enviroment, set up accounts, can does SL need to be pointed to CWB-UAT, OKTA? | 2021-07-14: Might need to do deployments Friday afternoon, less interruption/downtime
|  | 2. Schedeul Daily Triage with Christina, Biz Team | 2021-07-14: BAT will need to complete before Regression/Go-No Go week
3. Do we have what we need for E2E? What do we need to prep now?
4. Summary format for defects
minimum requirements for Spotlight configurations to be done so QA Team can start testing
QA Team needs to figure out - what we can test first? Doesn't require spotlight configurations
should cover migrated data, which set of "test data" can we use? We need to set them up.
Sprint 21
Build
Spill
over
Sprint 21
Prod
Candidate
Build
7/7
Build

## with R1.1 and SBDCO
Temenos | Sprint 21 | Sprint 22 (2 weeks) Stabilization/Defect Fixing | [41 empty] | Go Live
| Jun 14 - Jun 25 (2 weeks) (WE ARE HERE) | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Last Sprint Development | time axis 2021-06-28 to 2021-10-08
|  | Sprint 21 Demo/ Dplymnt | [41 empty] | Go Live
CWB-SIT | CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB - SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB-SIT/QA02 CWB SIT/QA02 | bar: 2021-06-28 to 2021-08-09
DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E DM and E2E | bar: 2021-06-28 to 2021-08-09
| Jun 14 - Jun 25 (WE ARE HERE) | 2021-06-28: Jun 28 - Jul 2; 2021-07-03: Weekend; 2021-07-05: Jul 5 - 9; 2021-07-10: Weekend; 2021-07-12: Jul 12 - 16 E2E (Adrian is off); 2021-07-17: Weekend; 2021-07-19: Jul 19 - 23 E2E/Regression; 2021-07-24: Weekend; 2021-07-26: Jul 26 - 30 Regression/Go-No Go Week (Susan is off); 2021-07-31: Weekend; 2021-08-02: Aug 2-6 Go Live Prep Week (Susan is off); 2021-08-09: Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
 | time axis 2021-06-28 to 2021-10-08
| DATA MIGRATION Process Testing with Test Profiles/ E2E Test Set Data | 2021-06-29: DM update ETA EOD; 2021-07-02: Date issue!; 2021-07-05: Data Migration Process Testing Transition from Adrian
| - Sprint 20 Testing - Defects retesting - Test scenario development (E2E) | 2021-06-28: E2E Kick Off Sprint 21 Testing Functional with NON-migrated data; 2021-07-05: Sprint 21, Spillover Testing Functional with NON-migrated data; 2021-07-12: Successful completion of DM Process testing 1. E2E - with migrated data 2. PCR Testing; 2021-08-02: Go Live Prep Week
2pm
| Defect Triage everyday | 2021-06-28: Defect Triage; 2021-06-29: Defect Triage; 2021-06-30: Defect Triage; 2021-07-01: Defect Triage; 2021-07-02: Defect Triage; 2021-07-05: Defect Triage; 2021-07-06: Defect Triage; 2021-07-07: Defect Triage; 2021-07-08: Defect Triage; 2021-07-09: Defect Triage; 2021-07-12: Defect Triage; 2021-07-13: Defect Triage Fraud Trng; 2021-07-14: Defect Triage; 2021-07-15: Defect Triage; 2021-07-16: Defect Triage; 2021-07-19: Defect Triage; 2021-07-20: Defect Triage; 2021-07-21: Defect Triage; 2021-07-22: Defect Triage; 2021-07-23: Defect Triage; 2021-07-26: Defect Triage; 2021-07-27: Defect Triage; 2021-07-28: Defect Triage; 2021-07-29: Defect Triage; 2021-07-30: Go/No Go (PM); 2021-08-05: CAB Approval 2pm
CWB-UAT | CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT CWB-UAT | bar: 2021-06-28 to 2021-08-09
|  | Jun 28 - Jul 2 |  |  |  |  | Weekend |  | Jul 5 - 9 |  |  |  |  | Weekend |  | Jul 12 - 16 |  |  |  |  | Weekend |  | Jul 19 - 23 |  |  |  |  | Weekend |  | Jul 26 - 30 |  |  |  |  | Weekend |  | Aug 2-6 | [6 empty] | Go Live
|  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
 | time axis 2021-06-28 to 2021-10-08
| CWB-UAT environment set up Prep work for BAT and NFR Testing Deploy Sprint 20 and validate | 2021-06-28: Validate environment Logon account setup; 2021-07-05: Validate; 2021-07-12: Validate Get it ready for Pen/Security and Performance and BAT; 2021-07-19: BAT Exection Week Pen/Security Testing Performance Testing; 2021-07-26: Pen/Security Testing Performance Testing
| R1.1 | 2021-06-28: Sprint 2; 2021-07-07: Sprint 3; 2021-07-21: Sprint 4; 2021-08-04: Sprint 5; 2021-08-18: Sprint 6
| R.1 | 2021-07-07: Sprint 2 testing; 2021-07-21: Sprint 3 testing; 2021-08-04: Sprint 4 testing; 2021-08-18: Sprint 5 testing; 2021-09-01: Sprint 6 testing; 2021-09-15: 3 days extra E2E, Regression; 2021-09-18: Sat; 2021-09-19: Sun; 2021-09-20: E2E, Regression, BAT Performance, Penetration Testing Go/No Go week; 2021-09-25: Sat; 2021-09-26: Sun; 2021-09-27: Go/ No Go - Go Live Prep week; 2021-10-02: Sat; 2021-10-03: Sun; 2021-10-04: Go Live
[34 empty] | infinity upgrade |  |  |  |  | test environment | [12 empty] | Opt 1 | UAT for non-Dashboard components | [13 empty] | UAT continuation - with Dashboard components included
[39 empty] | code merging - regression testing | [12 empty] | Opt 2 | [14 empty] | Compressed UAT
QA resources
[39 empty] | bat | [13 empty] | With options 1 or 2 - are we not going to have E2E?
[39 empty] | performance? | [13 empty] | R1 QA Team will not finish until the week of Aug 2, the earliest they can join R1.1 is Sprint 4
[39 empty] | penetration? | [13 empty] | Will R1.1 included deferred items from R1, will there be a R1.01?
Will CWB-SIT be merged with R1.1, what if we need it for R1.01?
| SBDCO | 2021-06-28: Sprint 17; 2021-07-07: Sprint 18; 2021-07-21: Sprint 19; 2021-08-04: Sprint 20
| SBDCO | 2021-06-28: Sprint 16 testing; 2021-07-07: Sprint 17 testing; 2021-07-21: Sprint 18 testing; 2021-08-04: Sprint 19 testing; 2021-08-18: Sprint 20 testing; 2021-09-01: CWB E2E; 2021-09-15: 3 days extra Regression?; 2021-09-18: Sat; 2021-09-19: Sun; 2021-09-20: Regression BAT Performance, Penetration Testing Go/No Go week; 2021-09-25: Sat; 2021-09-26: Sun; 2021-09-27: Go Live Prep Week; 2021-10-02: Sat; 2021-10-03: Sun; 2021-10-04: Go Live
Sprint 21
Build
Spill
over
Sprint 21
Prod
Candidate
Build
Build

## Sheet2
Exit Criteria (to exit from SIT, to declare SIT is done) | Status | Notes
1. Temenos SIT testing for all development sprints completed | Not met | Temenos has spillover development work from previous sprints
2. At least 95% of CWB’s test cases passed (SIT testing) | Not met | As of this email, please refer to JIRA report (screenshot) 25.30% (from MTM screenshot, from Sprints 8 to 20)
3. All critical and high defects fixed and closed (blockers to be included as well) | Not met | As of this email, please refer to JIRA report (screenshot) Blockers - 8 Critical - 24 High - 185
4. All medium and low defects have resolutions agreed upon by all parties | Not met | -Temenos to deliver plan (how and when defects will be fixed and delivered) -As of this email, please refer to JIRA report (screenshot) Medium - 285 Low - 51
E2E Entry Criteria (to start E2E) | Status | Notes
1. Test Environment
a.CWB-SIT is fully integrated and validated with required integrations for E2E | Not met | DM work and testing not yet completed - completion TBD Fraud configuration will not be completed until July 13
2. Test Data | Not met
a.Test data migration testing has been loaded and ready for validation | Not met | Temenos DM work and testing will not be done until TBD
b.Test data required to complete for E2E | Not met | Temenos DM work and testing will not be done until TBD
3. Temenos has successfully completed their E2E testing | Not applicable | Temenos does not have an E2E cycle, they have a Stabilization cycle to address defects - but it is assumed that their sprint development development and testing have successfully completed and only outstanding defects will be worked of in Stabilization cycle
4. No outstanding critical or high defects from Temenos E2E testing (blockers to be included) | Not met | As of this email, please refer to JIRA report (screenshot) Blockers - 8 Critical - 24 High - 185