## CWB Outstanding Defects
Issue key | Summary | Custom field (Defect Severity) | Business Feedback | Priority | Business Feedback | Function/Area Impacted | Reporter | Assignee | Status | Created | Labels | Labels | Labels | Labels | Custom field (Release Details) | Custom field (Testing Performed By) | Custom field (Desired Due Date)
INFINITY-7202 | OLB - Interac e-Transfer - Add New Recipient - failed in Looping connector service while creating a new etransfer recipient(only happens first time created ADD_SENDER_PROFILE and then tried to create ADD_RECIPIENT) | Critical |  | Highest |  | Move-Money-e-Transfer | Reddy Ganapati | Anil Kesanupalli | To Do | 2021-09-03 19:26 | Move-Money-e-Transfer |  |  |  |  | Customer - Third Party | 2021-09-03
INFINITY-7201 | 186428 OLB - OLB and MOB - Bill Payments - Approval date for current dated txns is one day later than the current date. | High |  | High |  | Billpayment | Susan Bako | Harish Pocharam | To Do | 2021-09-03 17:41 | Billpayment | Billpayment | Biz-Review |  |  | Customer - Third Party | 2021-05-25
INFINITY-7200 | OLB - Performance - Payments -Switching to History tab in Pay Bills taking > 3 seconds | High |  | High |  | CWB-UAT-Environment | Jatinderpal Singh | Satish Kolkunda | IN PROGRESS | 2021-09-02 23:00 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-09-02
INFINITY-7199 | MB Retail -Android - Last 3 digits of the account number is replaced with dots for Line of Credit | High |  | High |  | R1-Hotfix | Efosa Okonkwo | Realvi Boddapati | To Do | 2021-09-02 22:57 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-09-02
INFINITY-7198 | MB Retail - Android Overlap/Squished Account Name/Account Type | High |  | High |  | R1-Hotfix | Efosa Okonkwo | Realvi Boddapati | To Do | 2021-09-02 22:44 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-09-02
INFINITY-7197 | MB Retail - Android Misalignment in Login screens | Low |  | Low |  | R1-Hotfix | Efosa Okonkwo | Satya Pavani | To Do | 2021-09-02 22:09 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-09-02
INFINITY-7196 | MOB Retail - Android - Wrong font on the main menu nav | High |  | High |  | R1-Hotfix | Efosa Okonkwo | Gorantla Sai Kiran | To Do | 2021-09-02 21:35 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-09-02
INFINITY-7194 | OLB - Account Dashboard - Upcoming transactions is not showing Bill Payments | High |  | High |  | Account-Dashboard | Adrian Crisp | lokeswara.rao | IN PROGRESS | 2021-09-02 01:11 | Account-Dashboard |  |  |  |  | Customer - Third Party | 2021-05-25
INFINITY-7193 | OLB_SB_Alerts_Approver did not receive any alert for "to be expired transaction" | Critical |  | High |  | Alerts | Pooja Walia | Pooja Walia | CLIENT REVIEW | 2021-09-02 00:41 | Alerts |  |  |  |  | Customer - Third Party | 2021-09-01
INFINITY-7192 | OLB - CRA Tax History - History in Infinity not displaying user's historical record from C1 prev-comp-test environment. | Critical |  | High |  | CRA | Susan Bako | Mark Doubinin | To Do | 2021-09-01 23:36 | CRA |  | Pay-Biz-Taxes |  |  | Customer - Third Party | 2021-08-13
INFINITY-7189 | OLB_SB_Alerts_Delegate receives notification for pending approval | High |  | High |  | Alerts | Pooja Walia | Anagha Pallen | IN REVIEW | 2021-09-01 19:16 | Alerts |  |  |  |  | Customer - Third Party | 2021-09-01
INFINITY-7188 | 186217 OLB - Statements - Set up statement or cheque images in DOXIM but do not see them in Infinity | Critical |  | High |  | Statements | Susan Bako | Pavan Reddy | IN PROGRESS | 2021-09-01 17:40 | Statements |  |  |  |  | Customer - Third Party | 2021-08-13
INFINITY-7182 | MOB- Retail- Device Registration- text updates | Medium |  | Medium |  | Login | Harish Pocharam | Tilak Barthi | IN PROGRESS | 2021-09-01 05:06 | Login |  |  |  |  | Customer - Third Party | 2021-09-01
INFINITY-7180 | 186150 OLB - Pay Business Taxes - CRA Form added by 1 SB user not seen by all SB users in that business. | Critical |  | High |  | Pay-Biz-Taxes | Susan Bako | Susan Bako | To Do | 2021-08-31 22:12 | Pay-Biz-Taxes | Biz-Review | CRA |  |  | Customer - Third Party | 2021-08-13
INFINITY-7166 | 186001 OLB - FT and BP - SB - Approvals field is displaying "0 of 2 Approved" as a value when the Approval Rule in the Approval matrix is set to "Any one approval". | High |  | High |  | Unscheduled-Backlog | Anil Kumar | Harish Pocharam | IN PROGRESS | 2021-08-30 23:10 | Unscheduled-Backlog | SMB-BP |  |  | Build 28 | Customer - Third Party | 2021-08-30
INFINITY-7164 | MOB-UAT-INFINITY- Jmeter not able to capture traffic from Mobile Cwb App after recent deployment | Blocker |  | Highest |  | CWB-UAT-Environment | Jatinderpal Singh | Jatinderpal Singh | To Do | 2021-08-30 19:58 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-30
INFINITY-7152 | Fraud/Navaera - ORT032 New Same IP E-Transfer Rule â€“ Failed - Client Care Issue Logged: NOD-33371 | Critical |  | High |  | Navaera-to-Fix | Reddy Ganapati | Reddy Ganapati | To Do | 2021-08-30 01:47 | Navaera-to-Fix |  |  |  |  | Customer - Third Party | 2021-08-29
INFINITY-7151 | Fraud/Navaera - ORTXXX Access to Service from Known Proxy IP to be developed post R1 | Low |  | Low |  | postR1 | Reddy Ganapati | Reddy Ganapati | To Do | 2021-08-30 00:21 | postR1 |  |  |  |  | Customer - Third Party | 2021-08-29
INFINITY-7150 | Fraud/Navaera - ORT033 failed on 2 conditions - Client Care Issue Logged: NOD-33369 | Critical |  | High |  | Navaera-to-Fix | Reddy Ganapati | Reddy Ganapati | To Do | 2021-08-29 23:04 | Navaera-to-Fix |  |  |  |  | Customer - Third Party | 2021-08-29
INFINITY-7149 | Fraud/Navaera - Same transaction ID is sent twice to Navaera Transaction id = 8f99ba84-f40b-4a18-9a8f-707b5482a41a | Critical |  | Highest |  | Fraud-Navaera | Reddy Ganapati | Reddy Ganapati | CLIENT REVIEW | 2021-08-29 21:56 | Fraud-Navaera |  |  |  |  | Customer - Third Party | 2021-08-29
INFINITY-7147 | 185945 - Fraud/Navaera - ORT021 Mobile Device Usage Rule â€“ not working for Android Logins - Client Care Issue Logged: NOD-33367 | High |  | High |  | Navaera-to-Fix | Reddy Ganapati | Reddy Ganapati | To Do | 2021-08-28 21:26 | Navaera-to-Fix | Fraud-Navaera |  |  |  | Customer - Third Party | 2021-08-28
INFINITY-7145 | Fraud/Navaera - ORT021 is firing for an Events which are triggered from Desktop channel Client Care Issue Logged: NOD-33360 | Critical |  | High |  | Navaera-to-Fix | Reddy Ganapati | Reddy Ganapati | To Do | 2021-08-27 23:34 | Navaera-to-Fix |  |  |  |  | Customer - Third Party | 2021-08-27
INFINITY-7142 | OLB - User Management - User name is not prepopulated from the activation email | High |  | High |  | R1-Hotfix | Adrian Crisp | Harish Pocharam | To Do | 2021-08-27 19:25 | R1-Hotfix |  | User-Management |  |  | Customer - Third Party | 2021-06-23
INFINITY-7141 | OLB - Stop Cheque Requests hint text on sort icon for chq # and reason are wrong and when no accounts you see a bad message. | Medium |  | Medium |  | R1-Hotfix | Susan Bako | Jerry Naraine | To Do | 2021-08-27 18:09 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-06-23
INFINITY-7135 | OLB - Retail - Pay Bills - History - Repeat Transaction field width is not consistent | Medium |  | Medium |  | R1.2 | Scott Sharp | Jerry Naraine | To Do | 2021-08-26 18:51 | R1.2 | UI-Issue |  |  | 2021-08-26 | Customer - Third Party | 2021-08-17
INFINITY-7129 | OLB-UAT-Performance-Clicking on Transfer tab in Account Summary taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Andy LePage | IN PROGRESS | 2021-08-26 15:59 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-26
INFINITY-7128 | OLB - Messages - UI issues - Scrollbar | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-26 15:40 | R1-Hotfix |  | UI-Issues |  | 2021-08-26 | Customer - Third Party | 2021-08-17
INFINITY-7122 | OLB - Stop PAP Confirmation - Font size is too large | Medium |  | Medium |  | R1-Hotfix | Scott Sharp | Harish Pocharam | To Do | 2021-08-25 23:58 | R1-Hotfix | UI-Issues |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-7108 | 185789 OLB - Contact details were not displayed for the migrated user to verify/confirm after initial login - RETAIL users | Critical |  | High |  | R1-Hotfix | Adrian Crisp | Harish Pocharam | Reopened | 2021-08-25 00:57 | R1-Hotfix | Biz-Review | DM |  |  | Customer - Third Party | 2021-02-18
INFINITY-7105 | OLB - Campaign images not displaying properly in Infinity | High |  | Medium |  | Biz-Review-SS | Scott Sharp | raineesh shaik | IN REVIEW | 2021-08-24 19:13 | Biz-Review-SS | UI-Issues |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-7097 | Fraud/Navaera - EnView Page Details tab - IP Location Details fields are not populated Client Care Issue Logged: NOD-33288 | High |  | High |  | Navaera-to-Fix | Reddy Ganapati | Reddy Ganapati | To Do | 2021-08-24 07:44 | Navaera-to-Fix |  |  |  |  | Customer - Third Party | 2021-08-24
INFINITY-7094 | Settings - Alert Settings - UI issues (2) | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:56 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7093 | Settings - Alert Settings - UI issues (1) | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:55 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7092 | Settings - Alert Settings - message | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:50 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7091 | OLB - Settings - Account settings - UI issues | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:46 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7090 | OLB - Settings - Profile settings - change password - UI issues | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:42 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7089 | OLB - Accounts details - UI Issues (2) | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:39 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7088 | OLB - Accounts details - UI Issues (1) | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:36 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7087 | OLB - Dashboard - Accounts - UI Issues | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:31 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7086 | OLB - Stop Payments - column alignment | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:27 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7085 | OLB - Stop Cheque requests - Acknowledgement form - UI issues | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:14 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7084 | OLB - Stop Cheque requests - Confirmation form - UI issues | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:12 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7081 | OLB - Stop Cheque requests - Terms & Conditions UI issues | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 02:02 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7080 | OLB - Stop Cheque requests - entry form UI issues | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 01:58 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7079 | OLB - Stop Cheque requests - UI issues | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-24 01:52 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-23
INFINITY-7078 | OLB - Stop Cheque requests - dropdown displaying savings accounts when it shouldn't | High |  | Medium |  | Stop-Cheque | Chix Dela Luna | Scott Sharp | Reopened | 2021-08-24 01:46 | Stop-Cheque |  |  |  | 2021-09-01 | Customer - Third Party | 2021-08-23
INFINITY-7076 | 185618 OLB & MOB - Pay Bills - User is unable to cancel the same day scheduled recurring bill payment. | High |  | Highest |  | Payments-Pay-Bills | Anil Kumar | SRAVANTHI TALARI | IN PROGRESS | 2021-08-24 00:20 | Payments-Pay-Bills |  |  |  | Sprint 25 | Customer - Third Party | 2021-08-23
INFINITY-7065 | OLB-UAT-Performance- Addition of New parameter 'X-Kony-Integrity' cause failure to Performance Scripts | Medium |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Jatinderpal Singh | IN PROGRESS | 2021-08-23 16:52 | CWB-UAT-Environment |  |  |  | Build 26 | Customer - Third Party | 2021-08-23
INFINITY-7051 | Fraud/Navaera - Unable to filter using the newly added columns in the Enview Events page Client Care Issue Logged: NOD-33264 | High |  | High |  | Navaera-to-Fix | Reddy Ganapati | Reddy Ganapati | To Do | 2021-08-21 22:42 | Navaera-to-Fix |  |  |  |  | Customer - Third Party | 2021-08-21
INFINITY-7043 | OLB-UAT-Performance-Clicking on 'View Activity' button under CWB Recipient taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Jatinderpal Singh | IN PROGRESS | 2021-08-20 16:25 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7042 | OLB-UAT-Performance-In Manage Recipient, Click on Send Money link in Interac e-Transfer tab is taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Ryan Slack | IN PROGRESS | 2021-08-20 16:09 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7040 | OLB-UAT-Performance-After sending Money to CWB Acc in Manage Recipients, Return to Account page is taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-20 15:20 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7039 | OLB-UAT-Performance-Repeat Transaction Process is taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-20 15:15 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7038 | OLB-UAT-Performance-Switching to 'Completed Transfers Tab' in Manage Transfers is taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Andy LePage | IN PROGRESS | 2021-08-20 15:09 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7037 | OLB-UAT-Performance-After Clicking on Manage Recipients link, it is taking >3 seconds to Display page | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-20 15:03 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7036 | OLB-UAT-Performance-After successfully Requesting Interac e-Transfer, when we click on 'Send Another Money Request', it is taking > 3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-20 14:54 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7035 | OLB-UAT-Performance-Return to Accounts Page after sending Interac e-Transfer is taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-20 14:48 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7034 | OLB-UAT-Performance-After Clicking on Interac e-Transfer link, it is taking >3 seconds to Display page | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-20 14:40 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-20
INFINITY-7025 | 185422 OLB - Interac e-Transfer - Autodeposit fails for recipient where the method of transfer is Mobile Number | High |  | High |  | Move-Money-e-Transfer | Alka Patnaik | Alka Patnaik | IN PROGRESS | 2021-08-20 06:03 | Move-Money-e-Transfer |  |  |  | Build 25 | Customer - Third Party | 2021-08-20
INFINITY-7023 | OLB - Retail - Pay Bills - Manage Payees - Drawer UI Issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-20 04:57 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-7022 | OLB - Retail - Pay Bills - Manage Payees - UI Issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-20 04:56 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-7020 | OLB - Retail - Pay Bills - History - Unable to process bill with same amount | High |  | Medium |  | R1.2 | Scott Sharp | Jerry Naraine | To Do | 2021-08-20 04:46 | R1.2 |  |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-7019 | OLB - Retail - Pay Bills - History - Repeat transaction acknowlegement page UI issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-20 04:37 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-7018 | OLB - Retail - Pay Bills - History - Hamburger menu on repeat transaction confirmation page issue | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-20 04:29 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-7016 | OLB - Retail - Pay Bills - History - Hamburger menu on repeat transaction page issue | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-20 04:18 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-7004 | OLB-UAT-Performance-Return to AccountsPage taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-19 23:24 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-19
INFINITY-7003 | OLB-UAT-Performance-Transfer Between Accounts process taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-19 23:18 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-19
INFINITY-7002 | OLB-UAT-Performance-Clicking on Transfer Between Link taking >3 seconds | High |  | Medium |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-19 22:54 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-19
INFINITY-6989 | OLB - Pay Bills - Manage Payee - UI Issues, item #3 | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | To Do | 2021-08-19 16:24 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6988 | OLB - Retail - Pay Bills - Recurring Payment - Confirmation Page UI Issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 16:24 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6987 | OLB - Pay Bills - Manage Payee - UI Issues, item #2 | Medium |  | Medium |  | Unscheduled-Backlog | Chix Dela Luna | Chix Dela Luna | To Do | 2021-08-19 16:21 | Unscheduled-Backlog |  |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6986 | OLB - Retail - Pay Bills - Recurring Payment - Input Page UI Issue | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 16:19 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6983 | OLB - Retail - Pay Bills - Recurring Payment - Input Page UI Issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 16:06 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6979 | OLB - Retail - Pay Bills - One-Time Payment - Acknowledgement Page Menu (hmenu) | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 15:50 | R1-Hotfix | UI-Issues |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6978 | OLB - Retail - Pay Bills - One-Time Payment - Confirmation Page Menu (hmenu) | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 15:44 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6977 | OLB - Retail - Pay Bills - One-Time Payment - Input Page Drawer UI Issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 15:42 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6976 | OLB - Retail - Pay Bills - One-Time Payment - Input Page UI Issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 15:41 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6971 | OLB - Retail - Same Day Transfer - UI Issues 02 | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 07:34 | R1-Hotfix | UI-Issues |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6970 | OLB - Retail - Same Day Transfer - CAD Issue | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 07:26 | R1-Hotfix | UI-Issues |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6969 | OLB - Retail - Same Day Transfer - UI Issues 01 | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 07:13 | R1-Hotfix | UI-Issues |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6968 | OLB - Alerts and Messages - Deleted Messages Tab - UI Issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 06:59 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6966 | OLB - Alerts and Messages - Messagess Tab - UI Issues | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 06:49 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6965 | OLB - Alerts and Messages - Alerts Tab - Scrollbar moves upwards | Medium |  | Medium |  | Defer | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 06:44 | Defer | R1.1 | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6964 | OLB - Alerts and Messages - Alerts Tab - Scrollbar twitch and resize | Medium |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 06:37 | R1-Hotfix | UI-Issues |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6963 | OLB - Alerts and Messages - Alerts Tab - Search Results Loading | Medium |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 06:28 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6962 | OLB - Alerts and Messages - Alerts Tab - Info icon shouldn't be there | Medium |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 06:24 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6961 | OLB - Alerts and Messages - Alerts Tab - Dismiss Info UI | Medium |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 06:17 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6960 | OLB - Alerts and Messages - Alerts Tab - Scrollbar handle changes size | Medium |  | Medium |  | R1.1 | Scott Sharp | Chix Dela Luna | To Do | 2021-08-19 06:14 | R1.1 |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6959 | OLB - Alerts and Messages - Alerts Tab - UI issues - misalignment | High |  | Medium |  | R1-Hotfix | Scott Sharp | Jerry Naraine | To Do | 2021-08-19 05:05 | R1-Hotfix |  | UI-Issues |  |  | Customer - Third Party | 2021-08-17
INFINITY-6957 | Fraud/Navaera - Bill Payment - local machine time field is logging a different time | Critical |  | High |  | R1-Hotfix | Chix Dela Luna | sundharesan sangaranarayanan | To Do | 2021-08-19 01:41 | R1-Hotfix | Post-R1 |  |  |  | Customer - Third Party | 2021-07-14
INFINITY-6953 | OLB - Move Money - Manage Recipients | Medium |  | Medium |  | UI-Issues | Chix Dela Luna | Priyanka | IN PROGRESS | 2021-08-18 22:58 | UI-Issues |  |  |  | 2021-08-26 | Customer - Third Party | 2021-08-17
INFINITY-6952 | OLB - Pay Bills - Manage Payee - UI Issues, item #1 | Medium |  | Medium |  | UI-Issues | Chix Dela Luna | Chix Dela Luna | Reopened | 2021-08-18 22:42 | UI-Issues |  |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6950 | OLB-UAT-Performance-Logout takes more than 3 seconds | High |  | High |  | CWB-UAT-Environment | Jatinderpal Singh | Satish Kolkunda | IN PROGRESS | 2021-08-18 22:08 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-18
INFINITY-6949 | OLB-UAT-Performance-Launching Application takes >3 seconds | High |  | High |  | CWB-UAT-Environment | Jatinderpal Singh | Jatinderpal Singh | IN PROGRESS | 2021-08-18 22:01 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-18
INFINITY-6948 | OLB-UAT-Performance-Security Question step taking >3 seconds | Critical |  | High |  | CWB-UAT-Environment | Jatinderpal Singh | Satya Pavani | IN PROGRESS | 2021-08-18 21:56 | CWB-UAT-Environment |  |  |  |  | Customer - Third Party | 2021-08-18
INFINITY-6946 | OLB - Pay Business Taxes - Provincial - AB Template - Payment Amount error message not as per spec | High |  | High |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | Reopened | 2021-08-18 20:07 | R1-Hotfix |  |  |  | 2021-08-26 | Customer - Third Party | 2021-06-03
INFINITY-6931 | 185180 OLB - MOB - Login - App behaviour gives 400 error message if you don't remove app from phone after logout. | Medium |  | Medium |  | Login | Susan Bako | Gorantla Sai Kiran | IN PROGRESS | 2021-08-17 23:18 | Login |  |  |  |  | Customer - Third Party | 2021-08-13
INFINITY-6925 | OLB - Stop PAP - SS - Acknowledgement form | Medium |  | Medium |  | UI-Issues | Chix Dela Luna | Chix Dela Luna | Reopened | 2021-08-17 19:02 | UI-Issues |  |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6923 | OLB - Stop PAP - SS - Text inside input fields is not aligned | Medium |  | Medium |  | UI-Issues | Chix Dela Luna | Chix Dela Luna | Reopened | 2021-08-17 18:55 | UI-Issues |  |  |  |  | Customer - Third Party | 2021-08-17
INFINITY-6921 | 185065 OLB - e-transfers - MOB - SMS not received when recipient set up for both email and mobile | High |  | High |  | Move-Money-e-Transfer | Susan Bako | Mark Doubinin | Reopened | 2021-08-17 16:39 | Move-Money-e-Transfer |  |  |  |  | Customer - Third Party | 2021-07-26
INFINITY-6892 | 184883 OLB_SB and Retail_Alerts_No SMS/Text and push notification are received after adding a new Interac e-Transfer recipient | Critical |  | High |  | Alerts | Pooja Walia | Harish Pocharam | Reopened | 2021-08-14 03:27 | Alerts |  |  |  | 2021-09-01 | Customer - Third Party | 2021-08-14
INFINITY-6885 | 184847 OLB Inconsistent email and text sent for sender reminder vs system generated e-Transfer reminder | High |  | Medium |  | Move-Money-e-Transfer | Janice Casey | Janice Casey | To Do | 2021-08-13 20:17 | Move-Money-e-Transfer | e-Mail |  | Unscheduled-Backlog |  | Customer - Third Party | 2021-08-13
INFINITY-6869 | 184781 OLB Transaction output different when downloaded from different areas | Medium |  | Medium |  | Biz-Review | Janice Casey | Chix Dela Luna | To Do | 2021-08-12 23:21 | Biz-Review | Download |  |  |  | Customer - Third Party | 2021-08-12
INFINITY-6867 | 184760 OLB - CRA Direct Deposit for Businesses : Date of Birth allows Corporate Officer to be under 18 | High |  | High |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | To Do | 2021-08-12 21:35 | R1-Hotfix | CRA |  |  |  | Customer - Third Party | 2021-05-25
INFINITY-6855 | OLB - Spotlight - Customer Request and Messages being disabled doesn't remove menu options/input from clients | Critical |  | High |  | Spotlight | Chix Dela Luna | Realvi Boddapati | IN REVIEW | 2021-08-12 04:05 | Spotlight |  |  |  | 2021-09-01 | Customer - Third Party | 2021-08-12
INFINITY-6847 | 184707 OLB - Feedback - Feedback cannot be found and viewed in Spotlight | Medium |  | Medium |  | Feedback | Chix Dela Luna | Jerry Naraine | IN PROGRESS | 2021-08-11 22:02 | Feedback |  |  |  |  | Customer - Third Party | 2021-08-11
INFINITY-6834 | 184655 OLB e-Transfer "Request" declined AC needs to be revised | Medium |  | Medium |  | UI-Issues | Janice Casey | Janice Casey | To Do | 2021-08-11 00:20 | UI-Issues |  |  |  |  | Customer - Third Party | 2021-08-10
INFINITY-6828 | 184631 OLB - Pay Business Taxes - The Provincial tax acknowledgement screen for future dated txns has incorrect success message; calls it a transfer not a payment. | Medium |  | Medium |  | R1-Hotfix | Susan Bako | Jerry Naraine | To Do | 2021-08-10 18:59 | R1-Hotfix | R1.1 |  |  |  | Customer - Third Party | 2021-06-03
INFINITY-6817 | OLB Retail - MOB - Log in - returning user - cropped features and blue line issue | High |  | High |  | UI-Issues | Pooja Walia | Tony Fang | IN PROGRESS | 2021-08-10 01:17 | UI-Issues |  |  |  |  | Customer - Third Party | 2021-08-09
INFINITY-6804 | OLB - MOB - The fields on Payee details screen are not aliged correctly | Medium |  | Medium |  | UI-Issues | rajsanghamreddy | rajsanghamreddy | IN PROGRESS | 2021-08-09 06:13 | UI-Issues |  |  |  |  | Customer - Third Party | 2021-08-09
INFINITY-6765 | 184454 OLB - OLB and MOBILE - Bill Payment - Scheduled Payments screen - sort order defaults to date descending when ascending makes more sense | Medium |  | Medium |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | To Do | 2021-08-05 21:49 | R1-Hotfix | Payments-Pay-Bills | R1.1 |  |  | Customer - Third Party | 2021-07-27
INFINITY-6740 | 184310 OLB e-Transfer History Calendar pop up for "From" appears below "To" | Medium |  | Medium |  | R1-Hotfix | Janice Casey | Jerry Naraine | To Do | 2021-08-03 22:46 | R1-Hotfix | R1.1 |  | UI-Issues |  | Customer - Third Party | 2021-08-03
INFINITY-6733 | 184440 OLB - Direct Deposit for Businesses - Wrong requirements for Business Number - CR required | Critical |  | Highest |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | To Do | 2021-08-03 19:59 | R1-Hotfix | R1.1 |  |  |  | Customer - Third Party | 2021-05-25
INFINITY-6726 | OLB - Performance - iPad - From hamburger menu Move Money e-transfer option to going back to the Dashboard | High |  | Medium |  | CWB-Performance | Chix Dela Luna | Carmela Pucci | IN PROGRESS | 2021-08-02 22:49 | CWB-Performance |  |  |  | 2021-08-06 | Customer - Third Party | 2021-08-02
INFINITY-6725 | OLB - iPad - From the Top Bar menu, Move Money, Payments and Settings selections not available | Critical |  | Medium |  | Navigation | Chix Dela Luna | Susan Bako | Blocked | 2021-08-02 22:40 | Navigation |  |  |  | 2021-08-10 | Customer - Third Party | 2021-08-02
INFINITY-6722 | OLB - Performance - Interace-Tranfser - from loading Send form and going back to the Dashboard | High |  | High |  | CWB-Performance | Chix Dela Luna | Chix Dela Luna | IN PROGRESS | 2021-08-02 05:51 | CWB-Performance |  |  |  | 2021-08-06 | Customer - Third Party | 2021-08-02
INFINITY-6721 | OLB - Performance - Payments - Pay Business Taxes, going back to the Dashboard, and selecting/opening Form | High |  | High |  | CWB-Performance | Chix Dela Luna | Jatinderpal Singh | IN PROGRESS | 2021-08-02 05:38 | CWB-Performance |  |  |  |  | Customer - Third Party | 2021-08-02
INFINITY-6719 | OLB - Retail - Mobile - Support & About Us - empty phone number and email address, not assigned phone numbers | Medium |  | Medium |  | Support-About-Us | Pooja Walia | Adam Skoreyko | To Do | 2021-08-02 02:05 | Support-About-Us | Biz-Review |  |  |  | Customer - Third Party | 2021-08-02
INFINITY-6662 | OLB/MOB - Contact Us Page Content | Medium |  | Medium |  | Support-About-Us | Jerry Naraine | Adam Skoreyko | To Do | 2021-07-28 05:41 | Support-About-Us |  |  |  |  | Customer - Third Party | 2021-07-28
INFINITY-6654 | OLB - Spotlight - There needs to be an option to globally propagate changes to limits | Medium |  | Medium |  | R1.2 | Adrian Crisp | Jerry Naraine | To Do | 2021-07-27 23:28 | R1.2 |  |  |  |  | Customer - Third Party | 2021-06-03
INFINITY-6595 | 183627 OLB - Requests - Transfers - Payee is not relevant in transfer searches - this needs to be updated to Recipient | Medium |  | High |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | To Do | 2021-07-21 23:16 | R1-Hotfix | R1.1 |  |  |  | Customer - Third Party | 2021-03-08
INFINITY-6594 | OLB - Requests - Transfers - Payee is not relevant for transfers - this should be Account Number or Recipient | Medium |  | High |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | To Do | 2021-07-21 22:43 | R1-Hotfix | R1.1 |  |  |  | Customer - Third Party | 2021-03-08
INFINITY-6571 | Fraud/Navaera - Missing documentation - Mandatory field information per event is not documented | High |  | High |  | Fraud-Navaera | Reddy Ganapati | Reddy Ganapati | IN PROGRESS | 2021-07-19 22:58 | Fraud-Navaera |  |  |  |  | Customer - Third Party | 2021-07-19
INFINITY-6433 | 183120 OLB - User Management - Activation Security Code received is 3 digits not 6 digits. | Medium |  | Medium |  | BAT | Susan Bako | Susan Bako | Blocked | 2021-07-14 00:35 | BAT |  | User-Management |  |  | Customer - Third Party | 2021-06-23
INFINITY-6286 | 182801 OLB - Pay Business Taxes - The GST34 Netfile does not display the "I wish to make my GST34 NETFILE tax payment" on a new screen. | High |  | Medium |  | R1-Hotfix | Susan Bako | Jerry Naraine | To Do | 2021-07-08 01:47 | R1-Hotfix |  |  | Zooming | sprint 20 | Customer - Third Party | 2021-06-03
INFINITY-6074 | OLB - One-Time Payment display - scrollbar should be taken out, should display all records | Medium |  | Medium |  | R1.2 | Chix Dela Luna | Jerry Naraine | IN PROGRESS | 2021-07-01 00:02 | R1.2 |  |  |  | 2021-07-02 | Customer - Third Party | 2021-06-30
INFINITY-6051 | OLB and SBB_Contact US_Design issues | Medium |  | Medium |  | Support-About-Us | Pooja Walia | Adam Skoreyko | To Do | 2021-06-30 00:52 | Support-About-Us |  | Future-Sprint |  |  | Customer - Third Party | 2021-06-29
INFINITY-5729 | 181505 OLB_RB_Feedback_Survey pop up displays on session timeout and log out screens | Medium |  | Medium |  | Feedback | Pooja Walia | Jerry Naraine | To Do | 2021-06-21 23:52 | Feedback |  |  |  |  | Customer - Third Party | 2021-06-21
INFINITY-5723 | 181420 OLB Retail_Menu Navigation_Feedback_Survey link is not available | Medium |  | Medium |  | Feedback | Pooja Walia | Jerry Naraine | To Do | 2021-06-21 20:05 | Feedback |  |  |  |  | Customer - Third Party | 2021-06-21
INFINITY-5515 | OLB - Validation for Date fields when manually entered | Medium |  | Medium |  | R1-Hotfix | Chix Dela Luna | Jerry Naraine | IN PROGRESS | 2021-06-17 00:24 | R1-Hotfix | R1.1 |  |  |  | Customer - Third Party | 2021-06-16
INFINITY-5370 | OLB - Transfer Email - formatting - CWB Logo display is too small | Medium |  | Medium |  | UI-Issues | Chix Dela Luna | Mark Doubinin | To Do | 2021-06-12 01:14 | UI-Issues |  |  |  |  | Customer - Third Party | 2021-06-11
INFINITY-5276 | 185045 OLB - Unable to access QA02 URL from a tablet or mobile phone - get 403 error | Blocker |  | High |  | Fraud-Navaera | Susan Bako | Susan Bako | IN PROGRESS | 2021-06-10 01:14 | Fraud-Navaera | Access |  |  | R1 Build 26 | Customer - Third Party | 2021-02-19
INFINITY-5062 | OLB - Bill Payment -Pay Bills - Daily limit on Bill payment - No Alert/Warning message to the customer when they exceed | High |  | Medium |  | R1-Hotfix | Alka Patnaik | Jerry Naraine | IN PROGRESS | 2021-06-04 19:41 | R1-Hotfix | Payments-Pay-Bills |  |  | Sprint 19 | Customer - Third Party | 2021-06-04
INFINITY-5027 | 179667 OLB - Stop PAP Request : Cancel button on the initial Stop PAP Request doesn't have a confirmation modal | Medium |  | Medium |  | R1.2 | Adrian Crisp | Jerry Naraine | IN PROGRESS | 2021-06-03 18:20 | R1.2 |  |  |  |  | Customer - Third Party | 2021-05-25
INFINITY-4951 | 179549 OLB - Bill Payments - Recurring - Clicking cancel on the 1st entry page does not bring up cancel dialogue. | Medium |  | High |  | R1-Hotfix | Susan Bako | Jerry Naraine | To Do | 2021-06-01 18:38 | R1-Hotfix | R1.1 |  |  |  | Customer - Third Party | 2021-04-29
INFINITY-4950 | 179550 OLB - Bill Payments - One Time Payment - Clicking cancel on the 1st entry page does not bring up cancel dialogue. | Medium |  | High |  | R1-Hotfix | Susan Bako | Jerry Naraine | IN REVIEW | 2021-06-01 18:28 | R1-Hotfix | R1.1 |  |  |  | Customer - Third Party | 2021-04-29
INFINITY-4945 | 179534 OLB - Stop Cheque Request : Cancel button on the initial Stop Cheque Request doesn't have a confirmation modal | Medium |  | Medium |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | IN PROGRESS | 2021-06-01 18:02 | R1-Hotfix | R1.1 |  |  |  | Customer - Third Party | 2021-05-25
INFINITY-4899 | 179404 OLB & MOB - Statements - Statements are shown for every year and month going back 7 years prior to the customer even being created | High |  | Medium |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | IN PROGRESS | 2021-05-31 20:02 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-05-25
INFINITY-4739 | 179081 OLB - Stop Cheques Requests page - Usability - Need to display all stop cheques at once and have a filter. | Low |  | Medium |  | R1.2 | Susan Bako | Jerry Naraine | To Do | 2021-05-26 18:59 | R1.2 |  | Stop-Cheque | Usabilty |  | Customer - Third Party | 2021-04-29
INFINITY-4735 | 179066 OLB - Desktop Useability - Right click is disabled in all browsers. | Medium |  | Medium |  | R1.2 | Susan Bako | Jerry Naraine | To Do | 2021-05-26 18:02 | R1.2 |  |  |  |  | Customer - Third Party | 2021-04-29
INFINITY-4470 | 178691 OLB - Interac e-Transfer - Add New Recipient - The Request an Interac e-Transfer button is highlighted on the Acknowledgement screen of Add Recipient. | Medium |  | Medium |  | R1.2 | Alka Patnaik | patricia.begley-nelson | To Do | 2021-05-17 22:43 | R1.2 |  |  |  | Sprint 18 | Customer - Third Party | 2021-05-17
INFINITY-4310 | 178339 OLB - BP - One time current dated BP process does not match AC or Mockup stories for retail customer. | Medium |  | Medium |  | R1-Hotfix | Susan Bako | Jerry Naraine | To Do | 2021-05-10 23:59 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-05-10
INFINITY-3696 | Feedback -Should show full acnt numbers when spacing allows it (mobile) | Medium |  | Medium |  | R1-Hotfix | Venayak Rajahrajaswaran | Chix Dela Luna | To Do | 2021-04-13 23:38 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-04-13
INFINITY-2790 | 173764 OLB - SOW17/174 - MOB - E2E - Fund Transfers - Until screen for monthly should open at the following month from the Start Date | Medium |  | Medium |  | R1.2 | Susan Bako | Jerry Naraine | To Do | 2021-03-11 22:55 | R1.2 |  |  |  |  | Customer - Third Party | 2021-03-11
INFINITY-2693 | 173645 - OLB - Incorrect screen behaviour when Zooming on a browser | High |  | High |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | To Do | 2021-03-09 21:08 | R1-Hotfix |  | Zooming-Fixed |  |  | Customer - Third Party | 2021-02-18
INFINITY-2688 | SOW190 - OLB - Stop Cheque - AC/MU mismatch leading to Management and Request page problems. | Medium |  | Medium |  | Stop-Cheque | Susan Bako | Susan Bako | To Do | 2021-03-09 18:28 | Stop-Cheque |  |  |  |  | Customer - Third Party | 2021-01-12
INFINITY-2605 | OLB - Add CWB Account (add recipient) - Duplicate recipients can be added | High |  | Medium |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | IN PROGRESS | 2021-03-05 23:45 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-02-17
INFINITY-2597 | 173354 SOW216 - OLB - Alert Settings - Field disappears from screen when you resize the page. | Medium |  | Medium |  | R1-Hotfix | Susan Bako | Jerry Naraine | IN REVIEW | 2021-03-05 19:12 | R1-Hotfix |  | UI-Issues | Zooming-Fixed |  | Customer - Third Party | 2021-03-05
INFINITY-2199 | 172358 OLB - Pay Business Taxes - FAQ link goes to page not found | Medium |  | Medium |  | FAQ | Susan Bako | Susan Bako | Blocked | 2021-02-18 17:07 | FAQ |  | Future-Sprint |  |  | Customer - Third Party | 2021-02-18
INFINITY-2197 | OLB - Add CWB Account (add recipient) - No validation on account number validity | High |  | High |  | R1-Hotfix | Adrian Crisp | Jerry Naraine | IN PROGRESS | 2021-02-18 16:33 | R1-Hotfix |  |  |  |  | Customer - Third Party | 2021-02-17

## Pivot
Count of Status | Column Labels
Row Labels | Blocker | Critical | High | Low | Medium | Grand Total
Account-Dashboard |  |  | 1 |  |  | 1
Alerts |  | 2 | 1 |  |  | 3
BAT |  |  |  |  | 1 | 1
Billpayment |  |  | 1 |  |  | 1
Biz-Review |  |  |  |  | 1 | 1
Biz-Review-SS |  |  | 1 |  |  | 1
CRA |  | 1 |  |  |  | 1
CWB-Performance |  |  | 3 |  |  | 3
CWB-UAT-Environment | 1 | 1 | 16 |  | 1 | 19
Defer |  |  |  |  | 1 | 1
FAQ |  |  |  |  | 1 | 1
Feedback |  |  |  |  | 3 | 3
Fraud-Navaera | 1 | 1 | 1 |  |  | 3
Login |  |  |  |  | 2 | 2
Move-Money-e-Transfer |  | 1 | 3 |  |  | 4
Navaera-to-Fix |  | 3 | 3 |  |  | 6
Navigation |  | 1 |  |  |  | 1
Pay-Biz-Taxes |  | 1 |  |  |  | 1
Payments-Pay-Bills |  |  | 1 |  |  | 1
postR1 |  |  |  | 1 |  | 1
R1.1 |  |  |  |  | 1 | 1
R1.2 |  |  | 1 | 1 | 7 | 9
R1-Hotfix |  | 3 | 30 | 1 | 34 | 68
Spotlight |  | 1 |  |  |  | 1
Statements |  | 1 |  |  |  | 1
Stop-Cheque |  |  | 1 |  | 1 | 2
Support-About-Us |  |  |  |  | 3 | 3
UI-Issues |  |  | 1 |  | 7 | 8
Unscheduled-Backlog |  |  | 1 |  | 1 | 2
Grand Total | 2 | 16 | 65 | 3 | 64 | 150