## Digital Banking
CWB QA Test Status Report
Notes: 1. QA Team will start working on: - Sprint 10 test cases - E2E test structure and test scenarios 2. Continuing to work on test cases for Sprints 1-7 - refer to issue item #6 Issues: 1. Blocked test cases are related to the defects logged by the Temenos team - will follow up with Temenos as to what their plan is for the defects they have logged for Sprint 8/9 (48 defects) 2. Logging defects - disprepancies with texts - some actual test results are not matching both the AC (acceptance criteria/expected results) and mock ups - some actual test results are matching the AC but not the mock up - some actual test results are matching the mock up but not the AC - will review/confirm with CWB Business Team which one to refer to to address issue - which is the "one source of truth" 3. Incomplete/ambigous ACs for approved user stories - examples: AC says "click on info icon" to confirm text, but there is no information about text, no mock up is available either - issues listed under item #1 4. Release Notes (RN) - cannot reconcile completed SOWs/Epics with user stories - The RN we receive lists which SOWs have been completed for the sprint delivered but when we check in JIRA/Confluence: a. some SOWs have stories that are not yet DONE b. some SOWs have no stories attached to them - have informed Temenos, will follow up 5. Test cases that Temenos have completed provide no evidence of actual test results - it just has a pass/fail result, no screenshot or other form of evidence of their actual test result is provided - passed tests that should have been failed - have informed Temenos, will follow up 6. Completed user stories from Sprints 1 to 7: cannot reconcile user stories that are set to DONE with the associated supposedly completed Sprints in JIRA or Confluence - some user stories under Sprint 1 to 7 are not yet set to DONE - it will be helpful to have a list of which user stories are attached to which SOW, to know which ones we can prioritize, this will also help in monitoring progress - have informed Temenos, will follow up
As of | 2021-01-14
Project Name: Digital Program - Digital Banking stream - SIT Phase - Sprints 8/9
Test Execution
Total Tests created | 53
Passed Tests | 17
Failed Tests | 14
Blocked Tests | 22
Remaining % Tests | 0
% Passed | 32
% Failed | 26
% Blocked | 42
# of defects active | 10
# of defects deferred | -
Defects (logged by CWB QA Team)
ID | Summary | Assigned To | Status | Severity
INFINITY-1552 | OLB - MOB - Device Registration - selecting Touch ID when it isn't already enabled on the phone causes app to freeze | Janardhan | TO DO/NEW | High
INFINITY-1467 | MOB - Device deregistration screen - Text below button doesn't match AC. | Anil Kesanupalli | TO DO/NEW | Low
INFINITY-1469 | MOB - Device deregistration - Logged out screen text doesn't match AC or mock up. | Anil Kesanupalli | TO DO/NEW | Low
INFINITY-1545 | MOB - Account Dashboard Retail - No advertising banner displays. | Janardhan | TO DO/NEW | Low
INFINITY-1547 | MOB - Account Dashboard Retail - CDIC logo is NOT a link. | Janardhan | TO DO/NEW | Low
INFINITY-1548 | OLB - MOB - Account Dashboard Retail - Incorrect capitalisation in header | Janardhan | TO DO/NEW | Low
INFINITY-1549 | MOB - Account Details - Account summary section heading on screen doesn't match AC. | Janardhan | TO DO/NEW | Low
INFINITY-1550 | MOB - Account Details - Interest detail section heading on screen doesn't match AC. | Janardhan | TO DO/NEW | Low
INFINITY-1551 | OLB - MOB - Device Registration - Verify Unregistered Device - ACs are wrong on user story INFINITY-564 | Janardhan | TO DO/NEW | Low
INFINITY-1590 | MOB - Account Details - AC heading for balance on Chequing Accounts doesn't match screen. | Janardhan | TO DO/NEW | Low