## Digital Banking - Test Summary
CWB QA Test Status Report
Notes: 1. From Sprint 10 Release notes: only two stories are ready for CWB QA Team to test 2. Continuing to work on test cases for Sprints 1-7 - E2E test structure and test scenarios Issues: 1. Completed user stories from Sprints 1 to 7: cannot reconcile user stories that are set to DONE with the associated supposedly completed Sprints in JIRA or Confluence - Daman informed us that stories from previous sprints will be updated accordingly - ETA Jan 19 2. At least 5 stories were moved from Sprit 10 to Sprint 11 - Daman will provide us which stories are planned for Sprint 11 - ETA Jan 22
As of | 2021-01-22
Project Name: Digital Program - Digital Banking stream - SIT Phase - Sprint 10
Test Execution
Total Tests created | 7
Passed Tests | 2
Failed Tests | 0
Blocked Tests | 0
Remaining % Tests | 5
% Passed | 29
% Failed | 0
% Blocked | 0
# of defects active | 15
# of defects deferred | -

## Defect Summary Report
CWB QA Team - Defect Summary Report - as of Jan 22, 2021
| Issue key | Summary | Priority | Reporter | CWB Assignee | Temenos Assignee | Status | Notes
1 | INFINITY-1722 | MOB - Quick Balance - ACs do not match Mock Ups or do not have enough details in them. | Medium | susan.bako | chix |  | To Do | Issue with AC and mock-up not being the same. Chix needs to review with business team, which one should we follow?
2 | INFINITY-1717 | MOB Account Details - inconsistencies in ACs | Medium | susan.bako | chix |  | To Do
3 | INFINITY-1716 | MOB - Device Registration - ACs do not match Mock Ups or do not have enough details in them. | Medium | susan.bako | chix |  | To Do
4 | INFINITY-1715 | OLB Account Details - inconsistencies in ACs | Medium | adrian.crisp | chix |  | To Do
5 | INFINITY-1548 | OLB - MOB - Account Dashboard Retail - Incorrect capitalisation in header | Medium | adrian.crisp | chix |  | To Do
6 | INFINITY-1590 | MOB - Account Details - AC heading for balance on Chequing Accounts doesn't match screen. | Medium | susan.bako |  | Janardhan | To Do | Issue with AC and mock-up not being the same. Assigned to Temenos. Temenos is reviewing.
7 | INFINITY-1551 | OLB - MOB - Device Registration - Verify Unregistered Device - ACs are wrong on user story INFINITY-564 | Medium | adrian.crisp |  | Janardhan | To Do
8 | INFINITY-1550 | MOB - Account Details - Interest detail section heading on screen doesn't match AC. | Medium | susan.bako |  | Janardhan | To Do
9 | INFINITY-1549 | MOB - Account Details - Account summary section heading on screen doesn't match AC. | Medium | susan.bako |  | Janardhan | To Do
10 | INFINITY-1469 | MOB - Device deregistration - Logged out screen text doesn't match AC or mock up. | Medium | susan.bako |  | Anil Kesanupalli | To Do
11 | INFINITY-1545 | MOB - Account Dashboard Retail - No advertising banner displays. | Medium | susan.bako |  | Janardhan | To Do
12 | INFINITY-1467 | MOB - Device deregistration screen - Text below button doesn't match AC. | Medium | susan.bako |  | Anil Kesanupalli | To Do
Functional / Text issues (misspelling)
13 | INFINITY-1552 | OLB - MOB - Device Registration - selecting Touch ID when it isn't already enabled on the phone causes app to freeze | High | adrian.crisp |  | Janardhan | To Do | Assigned to Temenos. Temenos is reviewing.
14 | INFINITY-1663 | OLB - SPOTLIGHT - Initial login page display issue | Medium | adrian.crisp |  | Janardhan | To Do | Assigned to Temenos. Temenos is reviewing.
15 | INFINITY-1547 | MOB - Account Dashboard Retail - CDIC logo is NOT a link. | Medium | susan.bako |  | Janardhan | To Do | Review feedback from Temenos with business team
Additional notes:
1. Report is just for defects the CWB QA Team has logged
2. Defects logged so far just uses the default Priority of "Medium" - final priorization will need to be done/reviewed with business team.
2. CWB's Defect Triage is scheduled twice a week (Wednesdays and Fridays - 3pm-4pm).
- Damanpreet Singh and Dino are both attendees to the triage session

## Sheet2
Sprint 8-9
Notes: 1. QA Team will start working on: - Sprint 10 test cases - E2E test structure and test scenarios 2. Continuing to work on test cases for Sprints 1-7 - refer to issue item #6 Issues: 1. Blocked test cases are related to the defects logged by the Temenos team - will follow up with Temenos as to what their plan is for the defects they have logged for Sprint 8/9 (48 defects) 2. Logging defects - disprepancies with texts - some actual test results are not matching both the AC (acceptance criteria/expected results) and mock ups - some actual test results are matching the AC but not the mock up - some actual test results are matching the mock up but not the AC - will review/confirm with CWB Business Team which one to refer to to address issue - which is the "one source of truth" 3. Incomplete/ambigous ACs for approved user stories - examples: AC says "click on info icon" to confirm text, but there is no information about text, no mock up is available either - issues listed under item #1 4. Release Notes (RN) - cannot reconcile completed SOWs/Epics with user stories - The RN we receive lists which SOWs have been completed for the sprint delivered but when we check in JIRA/Confluence: a. some SOWs have stories that are not yet DONE b. some SOWs have no stories attached to them - have informed Temenos, will follow up 5. Test cases that Temenos have completed provide no evidence of actual test results - it just has a pass/fail result, no screenshot or other form of evidence of their actual test result is provided - passed tests that should have been failed - have informed Temenos, will follow up 6. Completed user stories from Sprints 1 to 7: cannot reconcile user stories that are set to DONE with the associated supposedly completed Sprints in JIRA or Confluence - some user stories under Sprint 1 to 7 are not yet set to DONE - it will be helpful to have a list of which user stories are attached to which SOW, to know which ones we can prioritize, this will also help in monitoring progress - have informed Temenos, will follow up