## Digital Banking - Test Summary
CWB QA Test Status Report
Notes: 1. QA Team continuing to work on: - test cases for Sprints 1-9 - E2E test structure and test scenarios Issues: 1. Completed user stories from Sprints 1 to 9: cannot reconcile user stories that are set to DONE with the associated supposedly completed Sprints in JIRA or Confluence a. Daman informed us that stories from previous sprints will be updated accordingly - ETA Jan 29 2. Test cases that Temenos have completed provide no evidence of actual test results a. it just has a pass/fail result, no screenshot or other form of evidence of their actual test result is provided b. have informed Temenos, will follow up 3. Blocked CWB test cases are related to: - defects logged by the Temenos team - defects logged by CWB QA Team 4. CWB defects Logging defects - disprepancies with texts a. some actual test results are not matching both the AC (acceptance criteria/expected results) and mock ups b. some actual test results are matching the AC but not the mock up c. some actual test results are matching the mock up but not the AC d. QA Lead to review these issues/defects during BA and UX Team's "DBX Internal User Stories Review" session e. The goal for future sprints is to have lesser issues related to mismatch AC and mock-ups to avoid wasting time logging defects for such issues. - BA and UX Teams are expected to review and ensure stories are not approved until both AC and mock-up are reviewed and confirmed correct and matching. 5. Release Notes (RN) - cannot reconcile completed SOWs/Epics with user stories - The RN we receive lists which SOWs have been completed for the sprint delivered but when we check in JIRA/Confluence: a. some SOWs have stories that are not yet DONE b. some SOWs have no stories attached to them - This has been done for Sprint 10 (delivered Jan 22), will need to do the same for Release notes for Sprints 8/9
As of | 2021-01-25
Project Name: Digital Program - Digital Banking stream - SIT Phase - Sprint 10
Test Case Development
Stories planned for Sprint 10 | 14 | Notes: 1. CWB QA Team is only able to write/develop test cases for 4 stories - 8 more test cases added from last report 2. Test case development is not yet complete, more test cases will be added to cover all 4 stories. 3. Refer to Defect Summary Report tab for information on defects. - 2 more defects added from last report
Stories delivered in Sprint 10 build | 6
Stories with defects | 2
Stories that can be tested by CWB QA Team | 4
Stories moved from Sprint 10 to Sprint 11 | 8
Test Execution
Total Tests created | 12
Passed Tests | 6
Failed Tests | 0
Blocked Tests | 6
Remaining % Tests | 0
% Passed | 50
% Failed | 0
% Blocked | 50
# of defects active | 17
# of defects deferred | -

## Defect Summary Report
CWB QA Team - Defect Summary Report - as of Jan 25, 2021
| Issue key | Summary | Priority | Reporter | CWB Assignee | Temenos Assignee | Status | Date Created | Notes
1 | INFINITY-1776 | OLB - Account Dashboard Retail - AC/MU mismatch. | Medium | susan.bako | chix |  | To Do | 2021-01-12 | Issue with AC and mock-up not being the same. Chix needs to review with business team, which one should we follow?
2 | INFINITY-1736 | MOB - Secure Msg and Notfcn_Mobile_017 (2.1.17) - incorrect ACs - INFINITY-85 | Medium | adrian.crisp | chix |  | To Do | 2021-01-22
3 | INFINITY-1722 | MOB - Quick Balance - ACs do not match Mock Ups or do not have enough details in them. | Medium | susan.bako | chix |  | To Do | 2021-01-11
4 | INFINITY-1717 | MOB Account Details - inconsistencies in ACs | Medium | susan.bako | chix |  | To Do | 2021-01-21
5 | INFINITY-1716 | MOB - Device Registration - ACs do not match Mock Ups or do not have enough details in them. | Medium | susan.bako | chix |  | To Do | 2021-01-11
6 | INFINITY-1715 | OLB Account Details - inconsistencies in ACs | Medium | adrian.crisp | chix |  | To Do | 2021-01-21
7 | INFINITY-1590 | MOB - Account Details - AC heading for balance on Chequing Accounts doesn't match screen. | Medium | susan.bako | chix |  | To Do | 2021-01-12
8 | INFINITY-1551 | OLB - MOB - Device Registration - Verify Unregistered Device - ACs are wrong on user story INFINITY-564 | Medium | adrian.crisp | chix |  | To Do | 2021-01-12
9 | INFINITY-1550 | MOB - Account Details - Interest detail section heading on screen doesn't match AC. | Medium | susan.bako | chix |  | To Do | 2021-01-12
10 | INFINITY-1549 | MOB - Account Details - Account summary section heading on screen doesn't match AC. | Medium | susan.bako | chix |  | To Do | 2021-01-12
11 | INFINITY-1548 | OLB - MOB - Account Dashboard Retail - Incorrect capitalisation in header | Medium | adrian.crisp | chix |  | To Do | 2021-01-12
12 | INFINITY-1467 | MOB - Device deregistration screen - Text below button doesn't match AC. | Medium | susan.bako | chix |  | To Do | 2021-01-11
13 | INFINITY-1545 | MOB - Account Dashboard Retail - No advertising banner displays. | Medium | susan.bako | chix |  | To Do | 2021-01-11
14 | INFINITY-1469 | MOB - Device deregistration - Logged out screen text doesn't match AC or mock up. | Medium | susan.bako | susan |  | To Do | 2021-01-11
15 | INFINITY-1663 | OLB - SPOTLIGHT - Initial login page display issue | Medium | adrian.crisp |  | Anil Kesanupalli | To Do | 2021-01-19 | Assigned to Temenos.
16 | INFINITY-1552 | OLB - MOB - Device Registration - selecting Touch ID when it isn't already enabled on the phone causes app to freeze | High | adrian.crisp |  | Anil Kesanupalli | To Do | 2021-01-12 | Assigned to Temenos.
17 | INFINITY-1547 | MOB - Account Dashboard Retail - CDIC logo is NOT a link. | Medium | susan.bako |  | Anil Kesanupalli | To Do | 2021-01-12 | Assigned to Temenos.
Additional notes:
1. Report is just for defects the CWB QA Team has logged
2. Defects logged so far just uses the default Priority of "Medium" - final priorization will need to be done/reviewed with business team.
3. CWB's Defect Triage is scheduled twice a week (Wednesdays and Fridays - 3pm-4pm).
- Damanpreet Singh and Dino are both attendees to the triage session

## Sheet2
Sprint 8-9
Notes: 1. QA Team will start working on: - Sprint 10 test cases - E2E test structure and test scenarios 2. Continuing to work on test cases for Sprints 1-7 - refer to issue item #6 Issues: 1. Blocked test cases are related to the defects logged by the Temenos team - will follow up with Temenos as to what their plan is for the defects they have logged for Sprint 8/9 (48 defects) 2. Logging defects - disprepancies with texts - some actual test results are not matching both the AC (acceptance criteria/expected results) and mock ups - some actual test results are matching the AC but not the mock up - some actual test results are matching the mock up but not the AC - will review/confirm with CWB Business Team which one to refer to to address issue - which is the "one source of truth" 3. Incomplete/ambigous ACs for approved user stories - examples: AC says "click on info icon" to confirm text, but there is no information about text, no mock up is available either - issues listed under item #1 4. Release Notes (RN) - cannot reconcile completed SOWs/Epics with user stories - The RN we receive lists which SOWs have been completed for the sprint delivered but when we check in JIRA/Confluence: a. some SOWs have stories that are not yet DONE b. some SOWs have no stories attached to them - have informed Temenos, will follow up 5. Test cases that Temenos have completed provide no evidence of actual test results - it just has a pass/fail result, no screenshot or other form of evidence of their actual test result is provided - passed tests that should have been failed - have informed Temenos, will follow up 6. Completed user stories from Sprints 1 to 7: cannot reconcile user stories that are set to DONE with the associated supposedly completed Sprints in JIRA or Confluence - some user stories under Sprint 1 to 7 are not yet set to DONE - it will be helpful to have a list of which user stories are attached to which SOW, to know which ones we can prioritize, this will also help in monitoring progress - have informed Temenos, will follow up