## Digital Banking - Test Summary
CWB QA Test Status Report
Notes: 1. QA Team continuing to work on: - test cases for Sprints 1-7 (113 stories) - E2E test structure and test scenarios - to provide statistics in next report 2. Next report will also include defects delivered in a sprint to help track defects logged by both Temenos and CWB teams. Issues: 1. Lack of traceability between JIRA and Confluence (between stories/SOWs/epics and sprint deliverables) a. Impact on test planning for future sprints - CWB QA Team is unable to plan and prepare test cases for future sprints because there is no consistent way for us to identify or trace back which stories are planned for which sprint. b. Impact on test execution for sprint delivered for CWB QA Team's testing - CWB QA Team only knows which stories are included in a sprint after the sprint demo and when we receive a copy of their Sprint Release notes. We have to use time to write test cases first then execute instead of using the whole time for test execution. b. Impact on test case development for stories - Because of the issue above (1.a), it is not easy to confirm which story we can write test cases for. 2. Discrepancies between acceptance criteria (AC) and mock-up (AC and mock-up not matching) a. Impacts test case development and test execution - not sure which to base our expected results on: AC or mock-up? Which one is the source of truth? b. For current defects logged (17 as of this reporting, relating to AC/mock-up mismatch issue): QA Lead to review these issues/defects during BA and UX Team's "DBX Internal User Stories Review" daily session - to review and get decision on how to address. - QA Team will continue to review these issues with the BA and UX teams for stories from previous sprints (1-7) and future sprints 3. Blocked CWB test cases are related to: - defects logged by the Temenos team - defects logged by CWB QA Team 4. Test cases that Temenos have completed provide no evidence of actual test results a. it just has a pass/fail result, no screenshot or other form of evidence of their actual test result is provided b. have informed Temenos, will follow up
As of | 2021-01-27
Project Name: Digital Program - Digital Banking stream - SIT Phase - Sprint 10
Test Case Development
Stories planned for Sprint 10 | 14 | Notes: 1. CWB QA Team is only able to complete test case development for 4 stories 2. Test case development for the rest will continue and will be tracked along with the test case development for stories from Sprints 1-7. 3. Refer to "CWB - Defect Summary Report" tab for information on defects. - 4 more defects added from last report
Stories delivered in Sprint 10 build | 6
Stories with defects | 2
Stories that can be tested by CWB QA Team | 4
Stories moved from Sprint 10 to Sprint 11 | 8
Test Execution
Total Tests created | 12
Passed Tests | 6
Failed Tests | 0
Blocked Tests | 6
Remaining % Tests | 0
% Passed | 50
% Failed | 0
% Blocked | 50
# of defects active | 24
# of defects deferred | -

## Created vs. Resolved Defects
Status of Defects managed by Temenos Team |  |  | Status of Defects logged CWB QA Team
- includes defects logged by CWB QA Team |  |  | - only includes defects reported/logged by CWB Team (QA and UX Team)
| 633 | created/opened defects |  | 24 | created/opened defects
| 569 | closed defects |  | 0 | closed defects
| 64 | outstanding defects |  | 24 | outstanding defects
| 47 | Mobile defects |  | 4 | UX issues, for Temenos address
| 17 | OLB defects |  | 5 | For Temenos to address (functional, non-UX items)
|  |  |  | 15 | AC/Mock-up mismatch issues, CWB Team to review and address

## CWB - Defect Summary Report
CWB QA Team - Defect Summary Report - as of Jan 27, 2021 (Total - 24)
| Issue key | Summary | Priority | Reporter | CWB Assignee | Temenos Assignee | Status | Date Created | Notes | Additional notes:
1 | INFINITY-1803 | UX - "sign in" should be "log in" | Medium | Chix |  | Anil | To Do | 2021-01-27 | UX issues, logged for the UX Team, observed from Jan 19 Demo for Sprint 10 | 1. Report is just for defects the CWB QA Team has logged
2 | INFINITY-1802 | UX - Missing grey background | Medium | Chix |  | Anil | To Do | 2021-01-27 |  | 2. Defects logged so far just uses the default Priority of "Medium" - final priorization will be done/reviewed with business team.
3 | INFINITY-1794 | UX - "Remember me" switch - Password page - "on" looks different from mock up | Medium | Chix |  | Anil | To Do | 2021-01-27 |  | 3. CWB's Defect Triage is scheduled twice a week (Wednesdays and Fridays - 3pm-4pm). - Damanpreet Singh and Dino are both attendees to the triage session
4 | INFINITY-1793 | UX - Font used is not CWB's font | Medium | Chix |  | Anil | To Do | 2021-01-27
5 | INFINITY-1781 | MOB - Feedback_001 - ACs don't match mockups - INFINITY-227 (Confluence 3.2.1) | Medium | Adrian | Chix |  | To Do | 2021-01-26 | Issue with AC and mock-up not being the same. Chix needs to review with business team, which one should we follow? - reviewed daily during "BA and UX Review session"
6 | INFINITY-1780 | MOB - Stop Cheque - AC/MU mismatch. | Medium | Susan | Chix |  | To Do | 2021-01-26
7 | INFINITY-1779 | Business Banking: User Management - SOW 309, SOW 31 - incorrect and incomplete ACs - INFINITY-1059 | Medium | Adrian | Chix |  | To Do | 2021-01-26
8 | INFINITY-1776 | OLB - Account Dashboard Retail - AC/MU mismatch. | Medium | Susan | Chix |  | To Do | 2021-01-12
9 | INFINITY-1736 | MOB - Secure Msg and Notfcn_Mobile_017 (2.1.17) - incorrect ACs - INFINITY-85 | Medium | Adrian | Chix |  | To Do | 2021-01-22
10 | INFINITY-1722 | MOB - Quick Balance - ACs do not match Mock Ups or do not have enough details in them. | Medium | Susan | Chix |  | To Do | 2021-01-11
11 | INFINITY-1717 | MOB Account Details - inconsistencies in ACs | Medium | Susan | Chix |  | To Do | 2021-01-21
12 | INFINITY-1716 | MOB - Device Registration - ACs do not match Mock Ups or do not have enough details in them. | Medium | Susan | Chix |  | To Do | 2021-01-11
13 | INFINITY-1715 | OLB Account Details - inconsistencies in ACs | Medium | Adrian | Chix |  | To Do | 2021-01-21
14 | INFINITY-1590 | MOB - Account Details - AC heading for balance on Chequing Accounts doesn't match screen. | Medium | Susan | Chix |  | To Do | 2021-01-12
15 | INFINITY-1551 | OLB - MOB - Device Registration - Verify Unregistered Device - ACs are wrong on user story INFINITY-564 | Medium | Adrian | Chix |  | To Do | 2021-01-12
16 | INFINITY-1550 | MOB - Account Details - Interest detail section heading on screen doesn't match AC. | Medium | Susan | Chix |  | To Do | 2021-01-12
17 | INFINITY-1549 | MOB - Account Details - Account summary section heading on screen doesn't match AC. | Medium | Susan | Chix |  | To Do | 2021-01-12
18 | INFINITY-1548 | OLB - MOB - Account Dashboard Retail - Incorrect capitalisation in header | Medium | Adrian | Chix |  | To Do | 2021-01-12
19 | INFINITY-1469 | MOB - Device deregistration - Logged out screen text doesn't match AC or mock up. | Medium | Susan | Susan |  | To Do | 2021-01-11
20 | INFINITY-1467 | MOB - Device deregistration screen - Text below button doesn't match AC. | Medium | Susan |  | Santiago | To Do | 2021-01-11 | Assigned back to Temenos, confirmed by CWB Business Team - AC needs to be corrected to match the mock up.
21 | INFINITY-1545 | MOB - Account Dashboard Retail - No advertising banner displays. | Medium | Susan |  | Anil | To Do | 2021-01-11 | Assigned back to Temenos, confirmed by CWB Business Team - needs to be fixed.
22 | INFINITY-1663 | OLB - SPOTLIGHT - Initial login page display issue | Medium | Adrian |  | Anil | To Do | 2021-01-19 | Assigned to Temenos.
23 | INFINITY-1552 | OLB - MOB - Device Registration - selecting Touch ID when it isn't already enabled on the phone causes app to freeze | High | Adrian |  | Anil | To Do | 2021-01-12 | Assigned to Temenos.
24 | INFINITY-1547 | MOB - Account Dashboard Retail - CDIC logo is NOT a link. | Medium | Susan |  | Anil | To Do | 2021-01-12 | Assigned to Temenos.