## Digital Banking - Test Summary
CWB QA Test Status Report - As of Jan 29, 2021
Project Name: Digital Program - Digital Banking stream - SIT Phase
USER STORIES
User Stories for CURRENT Sprint - Sprint 10 |  |  |  | User Stories for PREVIOUS prints - Sprint 1 - 9
Stories originally planned for Sprint 10 | TBD | Temenos original plan for Sprint 10 |  | Stories completed by Temenos | TBD | Dev Status=Dev completed and QA Status=Done (passed), CWB QA Team can write test cases for
Stories delivered in Sprint 10 build | 12 | As per Temenos' Sprint 10 Release Notes |  | Stories CWB QA Team has developed test cases for | TBD
Stories with defects | 8 | Stories with outstanding defects at the end of Sprint 10 |  | - Stories CWB QA Team cannot write test cases for | TBD | Issues with Acceptance Criteria (associated defect logged)
Stories that can be tested by CWB QA Team | 4 | Dev Status=Dev completed and QA Status=Done (passed) |  | Stories CWB QA Team has completed test execution for | TBD
Stories moved from Sprint 10 to Sprint 11 | 8 | Stories not delivered as planned, need to move to another sprint |  | - Stories CWB QA Team has logged defects for | TBD
Test Case Development
Test Case Development for CURRENT Sprint - Sprint 10 |  |  |  | Test Case Development for PREVIOUS Sprints 1-9
Total Test Cases Developed | 12 |  |  | Total Test Cases Developed | TBD | CWB QA Team in the process of reviewing with Temenos
Test Cases Impacted Due to AC/Mock issue | TBD | Defects logged by CWB QA Team - items being reviewed with CWB BA and UX Teams |  | Test Cases Impacted Due to AC/Mock issue | TBD | Defects logged by CWB QA Team - items being reviewed with CWB BA and UX Teams
Test Cases impacted Due Temenos Defect | TBD | CWB QA Team to confirm |  | Test Cases impacted Due Temenos Defect | TBD | CWB QA Team in the process of reviewing with Temenos
Test Execution
Test Execution for CURRENT Sprint - Sprint 10 |  |  |  | Test Execution for PREVIOUS Sprints 1 to 9
Total Tests Cases Developed | 12 |  |  | Total Tests Cases Developed | TBD
Passed Tests | 6 | % Passed | 50 | Passed Tests | 0 | % Passed | 0
Failed Tests | 0 | % Failed | 0 | Failed Tests | 0 | % Failed | 0
Blocked Tests | 6 | % Blocked | 50 | Blocked Tests | 0 | % Blocked | 0
Active/Unexecuted | 0 | % Unexecuted | 0 | Active/Unexecuted | 0 | % Unexecuted | 0
Total # of defects logged | 25
Total # of defects deferred | -
Note on J7: Chix Dela Luna: Started with Sprints 1 to 9 1. This is to quantify catch up work for CWB QA Team - for test case development and execution 2. Will increase after a Sprint 10 is done, it will increase after every sprint
Note on K9: Chix Dela Luna: Goal is to match count completed by Temenos
Note on K11: Chix Dela Luna: Goal is to match stories with developed test cases
Note on B17: Chix Dela Luna: Number will change every reporting time. We are writing test cases and executin at the same time.
Note on B25: Chix Dela Luna
Note on K25: Chix Dela Luna

## Created vs. Resolved Defects
Status of Defects logged/managed by Temenos Team - as of Jan 29, 2021 |  |  | Status of Defects logged CWB QA Team - as of Jan 29, 2021
- includes defects logged by CWB QA Team |  |  | - only defects reported/logged by CWB Team (QA and UX Team)
| 669 | created/opened defects |  | 25 | created/opened defects
| 604 | closed defects |  | 0 | closed defects
| 65 | outstanding defects |  | 25 | outstanding defects
| 52 | Mobile defects |  | 4 | UX issues, for Temenos address
| 13 | OLB defects |  | 5 | For Temenos to address (functional, non-UX items)
| -14 | from last report |  | 16 | AC/Mock-up mismatch issues, CWB Team to review and address
|  |  |  | 0 | no change from last report
|  |  |  | 1 | Issue resolved needs to be validated by CWB QA Team in Sprint 11

## CWB - Defect Summary Report
CWB QA Team - Defect Summary Report - as of Jan 29, 2021 (Total - 25)
| Issue key | Summary | Priority | Reporter | CWB Assignee | Temenos Assignee | Status | Date Created | Notes/Updates
1 | INFINITY-1803 | UX - "sign in" should be "log in" | Medium | Chix | Chix |  | To Do | 2021-01-27 | UX issues, logged for the UX Team, observed from Jan 19 Demo for Sprint 10 | Known issue, Temenos has logged a bug for it as well assigned back to chix
2 | INFINITY-1793 | UX - Font used is not CWB's font | Medium | Chix |  | Satya | To Do | 2021-01-27 |  | Review Anil's comment about OKTA/fonts with UX Team
3 | INFINITY-1844 | OLB - Feedback_001 and 002 - ACs don't match mockups - INFINITY-230/231 (Confluence 3.2.4 and 3.2.5) | Medium | Adrian | Chix |  |  | 2021-01-28 | Issue with AC and mock-up not being the same. Chix needs to review with business team, which one should we follow? - reviewed daily during "BA and UX Review session" - each issue is reviewed and the team decides on how to address discrepancy (either AC is corrected/update or mock-up is updated). | need to review with Sandra/Nolan
4 | INFINITY-1781 | MOB - Feedback_001 - ACs don't match mockups - INFINITY-227 (Confluence 3.2.1) | Medium | Adrian | Chix |  | To Do | 2021-01-26 |  | noted in issue #2
5 | INFINITY-1780 | MOB - Stop Cheque - AC/MU mismatch. | Medium | Susan | Chix |  | To Do | 2021-01-26 |  | noted in issue #3
6 | INFINITY-1779 | Business Banking: User Management - SOW 309, SOW 31 - incorrect and incomplete ACs - INFINITY-1059 | Medium | Adrian | Chix |  | To Do | 2021-01-26 |  | noted in issue #1
7 | INFINITY-1776 | OLB - Account Dashboard Retail - AC/MU mismatch. | Medium | Susan | Chix |  | To Do | 2021-01-12 |  | check with susan what is actual result does it match MU? If results match MU then assign to Temenos CWB UX team needs to update mock-up
8 | INFINITY-1736 | MOB - Secure Msg and Notfcn_Mobile_017 (2.1.17) - incorrect ACs - INFINITY-85 | Medium | Adrian | Chix |  | To Do | 2021-01-22 |  | check with adrian what is actual result, does it match MU? If results match MU then assign to Temenos
9 | INFINITY-1722 | MOB - Quick Balance - ACs do not match Mock Ups or do not have enough details in them. | Medium | Susan | Chix |  | To Do | 2021-01-11 |  | review again with susan sample: "Available Balance" vs "Current Balance"
10 | INFINITY-1717 | MOB Account Details - inconsistencies in ACs | Medium | Susan | Chix |  | To Do | 2021-01-21 |  | What is actual result - matches MU, not AC?
11 | INFINITY-1716 | MOB - Device Registration - ACs do not match Mock Ups or do not have enough details in them. | Medium | Susan | Chix |  | To Do | 2021-01-11 |  | Need to review with Sandra/BA, refer to Susan's description Also, AC in JIRA doesn't match AC in Confluence noted in issues #2
12 | INFINITY-1715 | OLB Account Details - inconsistencies in ACs | Medium | Adrian | Chix |  | To Do | 2021-01-21 |  | OLB - Account Summary MB - Account Details Headings - all words in Capital should "My Accounts" not "My accounts"
13 | INFINITY-1590 | MOB - Account Details - AC heading for balance on Chequing Accounts doesn't match screen. | Medium | Susan | Chix |  | To Do | 2021-01-12 |  | OLB - Account Summary MB - Account Details Headings - all words in Capital should "My Accounts" not "My accounts"
14 | INFINITY-1551 | OLB - MOB - Device Registration - Verify Unregistered Device - ACs are wrong on user story INFINITY-564 | Medium | Adrian | Adrian |  | To Do | 2021-01-12 |  | confirm with adrian - temenos have linked their bug, is it the same issue?
15 | INFINITY-1550 | MOB - Account Details - Interest detail section heading on screen doesn't match AC. | Medium | Susan | Chix |  | To Do | 2021-01-12 |  | OLB - Account Summary MB - Account Details Headings - all words in Capital should "My Accounts" not "My accounts"
16 | INFINITY-1549 | MOB - Account Details - Account summary section heading on screen doesn't match AC. | Medium | Susan | Chix |  | To Do | 2021-01-12 |  | OLB - Account Summary MB - Account Details Headings - all words in Capital should "My Accounts" not "My accounts"
17 | INFINITY-1469 | MOB - Device deregistration - Logged out screen text doesn't match AC or mock up. | Medium | Susan | Susan |  | To Do | 2021-01-11 |  | Known issue, Temenos has logged a bug for it as well assigned back to susan
Assigned to Temenos
18 | INFINITY-1467 | MOB - Device deregistration screen - Text below button doesn't match AC. | Medium | Susan |  | Santiago | To Do | 2021-01-11 | Assigned back to Temenos, confirmed by CWB Business Team - AC needs to be corrected to match the mock up. | assigned to Temenos
19 | INFINITY-1545 | MOB - Account Dashboard Retail - No advertising banner displays. | Medium | Susan |  | Anil | To Do | 2021-01-11 | Assigned back to Temenos, confirmed by CWB Business Team - needs to be fixed. | assigned to Temenos
20 | INFINITY-1663 | OLB - SPOTLIGHT - Initial login page display issue | Medium | Adrian |  | Anil | To Do | 2021-01-19 | Assigned to Temenos. | assinged to Temenos
21 | INFINITY-1552 | OLB - MOB - Device Registration - selecting Touch ID when it isn't already enabled on the phone causes app to freeze | High | Adrian |  | Anil | To Do | 2021-01-12 | Assigned to Temenos. | assinged to Temenos
22 | INFINITY-1547 | MOB - Account Dashboard Retail - CDIC logo is NOT a link. | Medium | Susan |  | Anil | To Do | 2021-01-12 | Assigned to Temenos. | assinged to Temenos
23 | INFINITY-1548 | OLB - MOB - Account Dashboard Retail - Incorrect capitalisation in header | Medium | Adrian | Chix |  | To Do | 2021-01-12 | Assigned to Temenos. | assigned to Temenos
24 | INFINITY-1802 | UX - Missing grey background | Medium | Chix |  | Anil | To Do | 2021-01-27 |  | assigned to Temenos, no comment just yet from them
25 | INFINITY-1794 | UX - "Remember me" switch - Password page - "on" looks different from mock up | Medium | Chix |  | Anil | To Do | 2021-01-27 |  | assigned to Temenos, no comment just yet from them
Additional notes:
1. Report is just for defects the CWB QA Team has logged
2. Defects logged so far just uses the default Priority of "Medium" - final priorization will be done/reviewed with business team.
3. CWB's Defect Triage is scheduled twice a week (Wednesdays and Fridays - 3pm-4pm). - Damanpreet Singh and Dino are both attendees to the triage session