## Digital
Digital Online Banking
Team Project Hierarchy | Core Banking
Area Path | \Core Banking\Digital
Test Plan Name | DIGITAL
Point Count Trend | Column Labels | [10 empty] | Digital Online Banking
Row Labels | Blocked | Failed | In Progress | Never Run | Passed | Grand Total | %Passed | %Failed | %Never Run | Blocked |  | AREA | CREATED | EXECUTED | BLOCKED | NEVER RUN/IN PROGRESS | % EXECUTED | % BLOCKED | %NEVER RUN/IN PROGRESS
Core Banking | 87 | 42 | 10 | 0 | 709 | 848 | 83.61% | 4.953% | 1.179% | 10.26% |  | Retail | 243 | 0 | 2 | 0 | 0% | 0.823% | 0%
Core Banking | 87 | 42 | 10 | 0 | 709 | 848 | 83.61% | 4.953% | 1.179% | 10.26% |  | Business | 426 | 0 | 49 | 0 | 0% | 11.5% | 0%
DIGITAL | 87 | 42 | 10 | 0 | 709 | 848 | 83.61% | 4.953% | 1.179% | 10.26% |  | Fraud | 176 | 130 | 36 | 10 | 73.86% | 20.45% | 5.682%
5 - Digital Online Banking | 87 | 42 | 10 | 0 | 709 | 848 | 83.61% | 4.953% | 1.179% | 10.26% |  | Data Migration | 3 | 3 | 0 | 0 | 100% | 0% | 0%
15 - E2E - Ret - Bld 23 - 08/10/21 | 2 | 11 | 0 | 0 | 230 | 243 | 94.65% | 4.527% | 0% | 0.823% | Retail
Account Dashboard/Accounts | 2 | 0 | 0 | 0 | 1 | 3 | 33.33% | 0% | 0% | 66.67%
Alerts | 0 | 3 | 0 | 0 | 13 | 16 | 81.25% | 18.75% | 0% | 0%
Bill Payments |  |  | 0 | 0 | 4 | 4 | 100% | 0% | 0% | 0%
COB-Ret-MOB-runs | 0 | 0 | 0 | 0 | 21 | 21 | 100% | 0% | 0% | 0% |  | Total | 848 | 133 | 87 | 10 | 15.68% | 10.26% | 1.179%
COB-Ret-OLB-runs | 0 |  |  | 0 | 15 | 15 | 100% | 0% | 0% | 0%
CRA Direct Deposit | 0 | 0 |  | 0 | 5 | 5 | 100% | 0% | 0% | 0%
e-Transfers | 0 | 2 | 0 | 0 | 29 | 31 | 93.55% | 6.452% | 0% | 0% |  |  |  |  | % EXECUTED | REMAINING
Feedback |  | 2 | 0 | 0 |  | 2 | 0% | 100% | 0% | 0% |  |  |  |  | 15.68% | 1.179%
Fund Transfer | 0 | 0 | 0 | 0 | 16 | 16 | 100% | 0% | 0% | 0%
Login-Logout | 0 | 2 | 0 | 0 | 2 | 4 | 50% | 50% | 0% | 0%
Pay Business Taxes | 0 | 2 | 0 | 0 | 120 | 122 | 98.36% | 1.639% | 0% | 0%
RDC-Ret-MOB | 0 | 0 | 0 | 0 | 2 | 2 | 100% | 0% | 0% | 0%
Stop Cheques |  | 0 | 0 | 0 | 2 | 2 | 100% | 0% | 0% | 0%
15 - E2E - SB - Bld 23 - 08/10/21 | 49 | 20 | 0 | 0 | 357 | 426 | 83.8% | 4.695% | 0% | 11.5% | Business
Acct Dbrd-SB-MOB | 2 | 3 | 0 | 0 | 17 | 22 | 77.27% | 13.64% | 0% | 9.091%
Alerts | 12 | 1 | 0 | 0 | 19 | 32 | 59.38% | 3.125% | 0% | 37.5%
Bill Payments | 7 | 1 | 0 | 0 | 42 | 50 | 84% | 2% | 0% | 14%
COB-SB-MOB runs | 0 | 0 | 0 | 0 | 26 | 26 | 100% | 0% | 0% | 0%
COB-SB-OLB runs | 0 | 2 | 0 | 0 | 23 | 25 | 92% | 8% | 0% | 0%
CRA Direct Deposit | 1 | 1 | 0 | 0 | 17 | 19 | 89.47% | 5.263% | 0% | 5.263%
e-Transfers | 1 | 6 | 0 | 0 | 31 | 38 | 81.58% | 15.79% | 0% | 2.632%
Feedback | 2 | 0 |  | 0 |  | 2 | 0% | 0% | 0% | 100%
Fund Transfer | 8 | 2 | 0 | 0 | 36 | 46 | 78.26% | 4.348% | 0% | 17.39%
Login-Logout | 0 | 0 | 0 | 0 | 8 | 8 | 100% | 0% | 0% | 0%
Pay Business Taxes | 15 | 3 | 0 | 0 | 128 | 146 | 87.67% | 2.055% | 0% | 10.27%
RDC-SB-MOB | 1 |  | 0 | 0 | 1 | 2 | 50% | 0% | 0% | 50%
Stop Cheques | 0 | 0 | 0 | 0 | 7 | 7 | 100% | 0% | 0% | 0%
Stop PAP |  | 0 |  | 0 | 2 | 2 | 100% | 0% | 0% | 0%
User Mgmt SB-OLB |  | 1 | 0 | 0 |  | 1 | 0% | 100% | 0% | 0%
4 - Fraud (Navaera) | 36 | 10 | 10 | 0 | 120 | 176 | 68.18% | 5.682% | 5.682% | 20.45% | Fraud
Event Testing | 2 | 2 | 0 | 0 | 102 | 106 | 96.23% | 1.887% | 0% | 1.887% |  |  |  | Digital Online Banking
ORT004 Multi-Time Zones per User per Day | 2 | 1 | 0 | 0 | 1 | 4 | 25% | 25% | 0% | 50% |  |  |  | AREA | PASSED | FAILED | % PASSED | % FAILED
ORT005 Inverse IP Geo Mismatch | 4 |  | 0 | 0 |  | 4 | 0% | 0% | 0% | 100% |  |  |  | Personal DCO | 0 | 0 | #DIV/0! | #DIV/0!
ORT006 Login from Multiple Countries | 0 | 0 | 0 | 0 | 4 | 4 | 100% | 0% | 0% | 0% |  |  |  | Business DCO | 0 | 0 | #DIV/0! | #DIV/0!
ORT017 High Velocity ATO EMT Rule | 0 | 0 | 0 | 0 | 8 | 8 | 100% | 0% | 0% | 0% |  |  |  | Fraud | 120 | 10 | 92.31% | 7.692%
ORT021 Mobile Device Usage Rule | 0 | 0 | 5 | 0 | 1 | 6 | 16.67% | 0% | 83.33% | 0% |  |  |  | Data Migration | 2 | 1 | 66.67% | 33.33%
ORT025 EMT Account Take Over Rule | 0 | 0 | 4 | 0 | 3 | 7 | 42.86% | 0% | 57.14% | 0%
ORT028 Online IP Blacklist |  |  | 1 | 0 | 1 | 2 | 50% | 0% | 50% | 0%
ORT029 High Risk eTransfers | 9 | 3 | 0 | 0 |  | 12 | 0% | 25% | 0% | 75%
ORT030 High Risk Outbound Specified Transaction Party Rule | 3 | 1 |  | 0 |  | 4 | 0% | 25% | 0% | 75%
ORT031 Money Request E-Transfer Rule | 7 | 1 | 0 | 0 |  | 8 | 0% | 12.5% | 0% | 87.5% |  |  |  | Total | 122 | 11 | 91.73% | 8.271%
ORT032 New Same IP E-Transfer Rule | 3 | 1 | 0 | 0 |  | 4 | 0% | 25% | 0% | 75%
ORT033 Bill Beneficiary Rule | 3 | 1 |  | 0 |  | 4 | 0% | 25% | 0% | 75%
ORTXXX Access to Service from Known Proxy IP | 3 | 0 |  | 0 |  | 3 | 0% | 0% | 0% | 100% | [5 empty] | % PASS | % FAIL
DM E2E - Cycle 3 | 0 | 1 | 0 | 0 | 2 | 3 | 66.67% | 33.33% | 0% | 0% | Data Migration |  |  |  |  | 91.73% | 8.271%
(DM E2E - Cycle 3) | 0 | 1 | 0 | 0 | 2 | 3 | 66.67% | 33.33% | 0% | 0%
Grand Total | 87 | 42 | 10 | 0 | 709 | 848 | 83.61% | 4.953% | 1.179% | 10.26%
AS of 12:51pm Aug 28
DO NOT USE BELOW
Team Project Hierarchy | Core Banking
Area Path | \Core Banking\User Acceptance Testing
Test Plan Name | T24 User Acceptance Testing - Execution
Point Count Trend | Column Labels
Row Labels | Never Run | Grand Total
Core Banking | 30 | 30
Core Banking | 30 | 30
T24 User Acceptance Testing - Execution | 30 | 30
2021 | 30 | 30
2. Projects | 17 | 17
2.2 Cash Deposits Form-AML01_FINTRAC | 17 | 17
3. Digital Banking Enhancements | 13 | 13
Grand Total | 30 | 30

## Defets to Test Cases
JIRA ID | TFS | Status | Test Cases ID | Title | Tester | Work Item Type | Created by | Priority
|  | Blocked | 180328 | OLB-E2E-AD-12 - V1 - Accounts - Verify cheque images can be displayed | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 180436 | MOB-E2E-AD-12 - V1 - Accounts - Verify cheque images can be displayed | Adrian Crisp | Test Case | Adrian Crisp | 2
| 184883 | Blocked | 181919 | MOB-E2E-AL-01 - V1 - Alerts - Verify Alert can be configured and received - "Interac e-Transfers Recipient Added" - SMS/Text | Adrian Crisp | Test Case | Adrian Crisp | 2
| 184883 | Blocked | 181930 | MOB-E2E-AL-03 - V1 - Alerts - Verify Alert can be configured and received - "Interac e-Transfers Recipient Added" - Push Notification | Adrian Crisp | Test Case | Adrian Crisp | 2
| 185580 | Blocked | 181944 | MOB-E2E-AL-05 - V1 - Alerts - Verify Alert can be configured and received - "Registered Bill Payee Added" - SMS/Text | Adrian Crisp | Test Case | Adrian Crisp | 2
| 185580 | Blocked | 181946 | MOB-E2E-AL-07 - V1 - Alerts - Verify Alert can be configured and received - "Registered Bill Payee Added" - Push Notification | Adrian Crisp | Test Case | Adrian Crisp | 2
| 184883 | Blocked | 181866 | OLB-E2E-AL-01 - V1 - Alerts - Verify Alert can be configured and received - "Interac e-Transfers Recipient Added" - SMS/Text | Alka Patnaik
|  | Blocked | 181883 | OLB-E2E-AL-07 - V1 - Alerts - Verify Alert can be configured and received - "Registered Bill Payee Added" - Push Notification | Alka Patnaik | Test Case | Adrian Crisp | 2
|  | Blocked | 182268 | OLB-E2E-CRADD-01 - V1 - CRA Direct Deposit for Individuals - Verify Direct Deposit can be setup and processed by CRA | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 180436 | MOB-E2E-AD-12 - V1 - Accounts - Verify cheque images can be displayed | Adrian Crisp | Test Case | Adrian Crisp | 2
7071, 6892 | 184883 | Blocked | 181919 | MOB-E2E-AL-01 - V1 - Alerts - Verify Alert can be configured and received - "Interac e-Transfers Recipient Added" - SMS/Text | Adrian Crisp
7071, 6892 | 184883 | Blocked | 181930 | MOB-E2E-AL-03 - V1 - Alerts - Verify Alert can be configured and received - "Interac e-Transfers Recipient Added" - Push Notification | Adrian Crisp | Test Case | Adrian Crisp | 2
7071, 6892 | 184883 | Blocked | 181948 | MOB-E2E-AL-09 - V1 - Alerts - Verify Alert can be configured and received - "Transaction Pending Approval" - SMS/Text - SB ONLY | Adrian Crisp | Test Case | Adrian Crisp | 2
7071, 6892 | 184883 | Blocked | 181950 | MOB-E2E-AL-11 - V1 - Alerts - Verify Alert can be configured and received - "Transaction Pending Approval" - Push Notification - SB ONLY | Adrian Crisp
7071, 6892 | 184883 | Blocked | 181953 | MOB-E2E-AL-13 - V1 - Alerts - Verify Alert can be configured and received - "Transaction Due to Expire" - SMS/Text - SB ONLY | Adrian Crisp
7071, 6892 | 184883 | Blocked | 181956 | MOB-E2E-AL-15 - V1 - Alerts - Verify Alert can be configured and received - "Transaction Due to Expire" - Push Notification - SB ONLY | Adrian Crisp
7071, 6892 | 184883 | Blocked | 181883 | OLB-E2E-AL-07 - V1 - Alerts - Verify Alert can be configured and received - "Registered Bill Payee Added" - Push Notification | Adrian Crisp | Test Case | Adrian Crisp | 2
7071, 6892 | 184883 | Blocked | 181907 | OLB-E2E-AL-11 - V1 - Alerts - Verify Alert can be configured and received - "Transaction Pending Approval" - Push Notification - SB ONLY | Adrian Crisp | Test Case | Adrian Crisp | 2
7071, 6892 | 184883 | Blocked | 181910 | OLB-E2E-AL-13 - V1 - Alerts - Verify Alert can be configured and received - "Transaction Due to Expire" - SMS/Text - SB ONLY | Adrian Crisp | Test Case | Adrian Crisp | 2
7071, 6892 | 184883 | Blocked | 181912 | OLB-E2E-AL-15 - V1 - Alerts - Verify Alert can be configured and received - "Transaction Due to Expire" - Push Notification - SB ONLY | Adrian Crisp | Test Case | Adrian Crisp | 2
7071, 6892 | 184883 | Blocked | 181915 | OLB-E2E-AL-16 - V1 - Alerts - Verify Alert can be configured and received - "Transaction Due to Expire" - Email - SB ONLY | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 176888 | MOB - E2E - BP - 17 - V1 - Verify bill payment - Once - Current date - SB - One Approval | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 176919 | MOB - E2E - BP - 18 - V1 - Verify bill payment - Once - Future date - SB - One Approval | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 176969 | MOB - E2E - BP - 18 - V1 - Verify bill payment - Once - Future date - Existing Payees - 1 Approval | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 176973 | MOB - E2E - BP - 19 - V1 - Verify bill payment - Reject - SB - One Approval | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 175601 | OLB - E2E - BP - 24 - V1 - Verify bill payment - Once - Current date - SB - 1 Approval | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 175620 | OLB - E2E - BP - 24 - V1 - Verify bill payment - Once - Future date - SB - 1 Approval | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 175833 | OLB - E2E - BP - 25 - V1 - Bill Payment - Recall - 1 Approver | Adrian Crisp | Test Case | Susan Bako | 2
|  | Blocked | 182269 | OLB-E2E-CRADD-02 - V1 - CRA Direct Deposit for Businesses - Verify Direct Deposit can be setup and processed by CRA | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 182019 | OLB-E2E-IeT-12 - V1 - Verify user can send an Interac e-Transfer to a recipient (email and mobile number) - New recipient with Autodeposit | Alka Patnaik | Test Case | Alka Patnaik | 2
6847 |  | Blocked | 181813 | MOB-E2E-FB-01 - V1 - Feedback - Verify Feedback can be entered, submitted by the client and viewable by CWB | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 181811 | OLB-E2E-FB-01 - V1 - Feedback - Verify Feedback can be entered, submitted by the client and viewable by CWB | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 174382 | MOB-E2E-FT-02b - V1 - Fund Transfer - Beneficiary management - Setup account recipients - View Activity - SB | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 174531 | MOB-E2E-FT-23 - V1 - Fund Transfer - Transfer with 1 approval | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 175835 | MOB-E2E-FT-26 - V1 - Fund Transfer - Recall - 1 Approver | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 180431 | OLB-E2E-PBT-68 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Today - One Approval Required - Forms (RC159, T1191, T305A-P, PD7D, RC155, PD67A, NR92, T305A_PQ, RC159-Q) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180453 | OLB-E2E-PBT-69 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Today - One approval required - Forms (RC158, RC160, RC177, NR93, PD10, PD101, RC160-Q, RC158-Q) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180454 | OLB-E2E-PBT-70 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Today - One approval required - Forms (GST 34, GST 34-2, GST 34 NETFILE, GST 62 -1, GST 62 -2, GST 62 -3, GST 62 -4, GST 62 -5, GST 62 - 6) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180456 | OLB-E2E-PBT-71 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Today - One approval required - Forms (PD7A, RC107, W1, PD7A-TM, PD7A-RB, W1-B, W1-RB) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180460 | OLB-E2E-PBT-72 - V1 - Pay CRA Taxes - Verify user can file only - Today - Amount Owing - Payment - One approval required - Form GST34 NETFILE | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180468 | OLB-E2E-PBT-73 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Future - One Approval Required - Forms (RC159, T1191, T305A-P, PD7D, RC155, PD67A, NR92, T305A_PQ, RC159-Q) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180470 | OLB-E2E-PBT-74 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Future - One approval required - Forms (RC158, RC160, RC177, NR93, PD10, PD101, RC160-Q, RC158-Q) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180471 | OLB-E2E-PBT-75 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Future - One approval required - Forms (GST 34, GST 34-2, GST 34 NETFILE, GST 62 -1, GST 62 -2, GST 62 -3, GST 62 -4, GST 62 -5, GST 62 - 6) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180472 | OLB-E2E-PBT-76 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Future - One approval required - Forms (PD7A, RC107, W1, PD7A-TM, PD7A-RB, W1-B, W1-RB) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180473 | OLB-E2E-PBT-77 - V1 - Pay CRA Taxes - Verify user can file only - Future - Amount Owing - Payment - One approval required - Form GST34 NETFILE | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180478 | OLB-E2E-PBT-78 - V1 - Pay CRA Taxes - Verify user can pay the amount owing - Today - Two Approvals Required - Forms (RC159, T1191, T305A-P, PD7D, RC155, PD67A, NR92, T305A_PQ, RC159-Q) | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180706 | OLB-E2E-PBT-29 - V1 - Pay PROV Taxes - Verify user can pay the amount owing - Today - One approval required - Form(s) AT1 , AT2054 , AT2059 , AT2095 , AT252 , AT300 , AT317 , AT360 , AT362 , AT363 , AT4990 , AT5100 , ATCLID | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180713 | OLB-E2E-PBT-30 - V1 - Pay PROV Taxes - Verify user can pay the amount owing - Future - One approval required - Form(s) AT1 , AT2054 , AT2059 , AT2095 , AT252 , AT300 , AT317 , AT360 , AT362 , AT363 , AT4990 , AT5100 , ATCLID | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180714 | OLB-E2E-PBT-31 - V1 - Pay PROV Taxes - Verify user can pay the amount owing - Today - Two approvals required - Form(s) AT1 , AT2054 , AT2059 , AT2095 , AT252 , AT300 , AT317 , AT360 , AT362 , AT363 , AT4990 , AT5100 , ATCLID | Susan Bako | Test Case | Adrian Crisp | 2
|  | Blocked | 180715 | OLB-E2E-PBT-32 - V1 - Pay PROV Taxes - Verify user can pay the amount owing - Future - Two approvals required - Form(s) AT1 , AT2054 , AT2059 , AT2095 , AT252 , AT300 , AT317 , AT360 , AT362 , AT363 , AT4990 , AT5100 , ATCLID | Susan Bako | Test Case | Adrian Crisp
|  | Blocked | 180652 | MOB-E2E-RDC-01 - V1 - Remote Data Capture - Verify cheque can be scanned - successful scan | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Blocked | 183503 | OLB-FRAUD-23 - V12 - Navera Field Validation - Small Business Customer - OLB - Validate Navera field transferReferenceNumber = Infinity field MONEY MOVEMENT REFID | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 183523 | OLB-FRAUD-43 - V12 - Navaera Field Validation - Small Business Customer - Mobile iOS - Validate Navaera field HTTP_LOCAL_TIME = Infinity field To be mapped | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182617 | OLB-FRAUD-01 - V10 - ORT005 - Personal Customer - OLB - Login from India - Triggering the rule Positive Scenario 1 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182621 | OLB-FRAUD-02 - V10 - ORT005 - Small Business Customer - Mobile IOS - Login from India - Triggering the rule Positive Scenario 2 | Reddy Ganapati
|  | Blocked | 182624 | OLB-FRAUD-03 - V10 - ORT005 - Personal Customer - OLB - Login from Seatle MST - False positive Scenario 3 | Reddy Ganapati
|  | Blocked | 182625 | OLB-FRAUD-02 - V10 - ORT005 - Small Business Customer - Mobile IOS - Login from Vancouver - False Positive Scenario 2 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182627 | OLB-FRAUD-01 - V10 - ORT006 - Personal Customer - OLB - Triggering the rule Positive Scenario 1 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182631 | OLB-FRAUD-03 - V10 - ORT006 - Personal Customer - OLB - Only transaction in last 24 hours - False Positive Scenario 1 | Reddy Ganapati
|  | Blocked | 182632 | OLB-FRAUD-01 - V10 - ORT006 - Personal Customer - OLB - 2 transactions are more than 24 hours apart - False Positive Scenario 1 | Reddy Ganapati
|  | Blocked | 182676 | OLB-FRAUD-02 - V10 - ORT029 - Small Business Customer - Mobile IOS - Flow 1(Login-Benificiary added for Etransfer + Etransfer within 70mins) Triggering the rule Positive Scenario 2 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182679 | OLB-FRAUD-03 - V10 - ORT029 - Personal Customer - OLB - Flow 1(Login-Benificiary added for eTransfer + Bill payment within 70mins)- Triggering the rule Positive Scenario 3 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182681 | OLB-FRAUD-04 - V10 - ORT029 - Small Business Customer - Mobile Android - Flow 1(Login-Benificiary added for Bill Payment + Etransfer within 70mins) Triggering the rule Positive Scenario 4 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182703 | OLB-FRAUD-06 - V10 - ORT029 - Small Business Customer - OLB - Flow 2(Login from new Ip – Modify or add etransfer recipient in past 48 hours – Etransfer Payment for Transaction Amt > $805 Then Event Score 150)- Triggering the rule Positive Scenario 2 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182709 | OLB-FRAUD-07 - V10 - ORT029 - Personal Customer - MOB IOS - Flow 2(Login from new Ip – Modify or add etransfer recipient in past 48 hours – Etransfer or Bill Payment for Transaction Amt > $805 Then Event Score 150)- Triggering the rule Positive Scenario 3 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182711 | OLB-FRAUD-08 - V10 - ORT029 - Small Business Customer - MOBAndroid- Flow 2(Login from new Ip – Modify or add etransfer recipient in past 48 hours – Etransfer Payment for Transaction Amt > $805 Then Event Score 150)- Triggering the rule Positive Scenario 4 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182735 | OLB-FRAUD-10 - V10 - ORT029 - Small Business Customer - OLB - Flow 3(Login Existing Ip – No eTransfer recipient in past 48 hours – No Err - 3 Etransfer Sum > $4500 Then Event Score 120)- Triggering the rule Positive Scenario 2 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182736 | OLB-FRAUD-09 - V10 - ORT029 - Personal Customer - MOB IOS - Flow 3(Login Existing Ip – No eTransfer recipient in past 48 hours – No Err - 3 Etransfer Sum > $4500 Then Event Score 120)- Triggering the rule Positive Scenario 3 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182737 | OLB-FRAUD-09 - V10 - ORT029 - Small Business Customer - MOB Android- Flow 3(Login Existing Ip – No eTransfer recipient in past 48 hours – No Err - 3 Etransfer Sum > $4500 Then Event Score 120)- Triggering the rule Positive Scenario 4 | Reddy Ganapati
|  | Blocked | 185620 | OLB-FRAUD-02 - V10 - ORT030 - Personal Customer - OLB - Triggering the rule Positive Scenario 1 condition 2 | Reddy Ganapati
|  | Blocked | 185621 | OLB-FRAUD-03 - V10 - ORT030 - Personal Customer - OLB - Triggering the rule Positive Scenario 1 condition 3 | Reddy Ganapati
|  | Blocked | 185622 | OLB-FRAUD-04 - V10 - ORT030 - Personal Customer - OLB - Triggering the rule Positive Scenario 4 | Reddy Ganapati
|  | Blocked | 183084 | OLB-FRAUD-02 - V10 - ORT031 - Small Business - OLB - Logic TBD Triggering the rule Positive Scenario 1 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 183085 | OLB-FRAUD-03 - V10 - ORT031 - Personal Customer - IOS- Logic TBD Triggering the rule Positive Scenario 1 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 183086 | OLB-FRAUD-04 - V10 - ORT031 - Small Business - Android - Logic TBD Triggering the rule Positive Scenario 1 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 183087 | OLB-FRAUD-05 - V10 - ORT031 - Personal Customer - OLB - Logic False Positive Scenario 2 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 183088 | OLB-FRAUD-06 - V10 - ORT031 - Small Business - OLB - Logic false Positive Scenario 3 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 183089 | OLB-FRAUD-03 - V10 - ORT031 - Personal Customer - IOS- Logic false Positive Scenario 4 | Reddy Ganapati
|  | Blocked | 183090 | OLB-FRAUD-08 - V10 - ORT031 - Small Business - Android - Logic TBD Triggering the rule Positive Scenario 5 | Reddy Ganapati
|  | Blocked | 182795 | OLB-FRAUD-01 - V10 - ORT032 - Small Business Customer - Mobile IOS - Triggering the rule Positive Scenario 1 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182798 | OLB-FRAUD-03 - V10 - ORT032 - Small Business Customer - OLB - Triggering the rule Positive Scenario 3 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 182799 | OLB-FRAUD-04 - V10 - ORT032 - Small Business Customer - Mobile Android- Triggering the rule Positive Scenario 4 | Reddy Ganapati
|  | Blocked | 183092 | OLB-FRAUD-02 - V10 - ORT033 - Personal Customer - OLB - Logic Triggering the rule Positive Scenario 2 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 183093 | OLB-FRAUD-03 - V10 - ORT033 - Small Business - MOB IOS- Logic Triggering the rule Positive Scenario 1 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Blocked | 183094 | OLB-FRAUD-02 - V10 - ORT033 - Small Business - Android- Logic Triggering the rule Positive Scenario 2 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
6847 |  | Failed | 181813 | MOB-E2E-FB-01 - V1 - Feedback - Verify Feedback can be entered, submitted by the client and viewable by CWB | Adrian Crisp | Test Case | Adrian Crisp | 2
6847 | 184707 | Failed | 181811 | OLB-E2E-FB-01 - V1 - Feedback - Verify Feedback can be entered, submitted by the client and viewable by CWB | Adrian Crisp | Test Case | Adrian Crisp | 2
6921 | 185065 | Failed | 181881 | MOB-E2E-IeT-06 - V1 - Verify user can send an Interac e-Transfer to a recipient (email and mobile number) - existing recipient with Autodeposit. | Alka Patnaik | Test Case | Alka Patnaik
6921 | 185065 | Failed | 182006 | MOB-E2E-IeT-11 - V1 - Verify user can send an Interac e-Transfer to a recipient (Mobile Number) - New recipient with Autodeposit. | Alka Patnaik | Test Case | Alka Patnaik | 2
7108 |  | Failed | 181761 | MOB-E2E-Login - 01 - V1 - Verify first time login | Susan Bako | Test Case | Susan Bako | 2
|  | Blocked | 180714 | OLB-E2E-PBT-32 - V1 - Pay PROV Taxes - Verify user can pay the amount owing - Future - Two approvals required - Form(s) AT1 , AT2054 , AT2059 , AT2095 , AT252 , AT300 , AT317 , AT360 , AT362 , AT363 , AT4990 , AT5100 , ATCLID | Susan Bako | Test Case | Adrian Crisp
no test cases |  | Blocked | 180714 |  | Susan Bako | Test Case | Adrian Crisp
no test cases |  | Blocked | 180714 |  | Susan Bako | Test Case | Adrian Crisp
|  | Failed | 182023 | OLB-E2E-Login - 01 - V2 - Verify first time login | Alka Patnaik | Test Case | Susan Bako | 2
6887 | 184866 | Failed | 180403 | OLB-E2E-PBT-56 - V1 - Pay CRA Taxes - Verify user can File and Remit - Future - No approvals - Form GST62-3 | Susan Bako | Test Case | Susan Bako | 2
6828 | 184631 | Failed | 180635 | OLB-E2E-PBT-18 - V1 - Pay PROV Taxes - Verify user can pay the amount owing - Future - No approvals - Form AT4990 | Susan Bako | Test Case | Susan Bako | 2
| 185793 | Failed | 180415 | MOB-E2E-AD-05 - V1 - Accounts - Verify Account Details - Mortgage | Adrian Crisp | Test Case | Adrian Crisp | 2
| 184718 | Failed | 180023 | OLB-E2E-AD-01 - V1 - Account Dashboard - Verify all accounts for the client from T24 are displayed with the correct balances | Adrian Crisp | Test Case | Adrian Crisp | 2
| 185580 | Failed | 181944 | MOB-E2E-AL-05 - V1 - Alerts - Verify Alert can be configured and received - "Registered Bill Payee Added" - SMS/Text | Adrian Crisp
| 185580 | Failed | 181946 | MOB-E2E-AL-07 - V1 - Alerts - Verify Alert can be configured and received - "Registered Bill Payee Added" - Push Notification | Adrian Crisp
| 184883 | Failed | 181866 | OLB-E2E-AL-01 - V1 - Alerts - Verify Alert can be configured and received - "Interac e-Transfers Recipient Added" - SMS/Text | Adrian Crisp | Test Case | Adrian Crisp | 2
7076 | 185618 | Failed | 183072 | MOB - E2E - BP - 20 - V1 - Verify bill payment - Cancel - Once - Current date - No Approvals | Susan Bako | Test Case | Susan Bako | 2
| 185211 | Failed | 171930 | OLB-E2E-FT-05 - V1 - Fund Transfer - Transfer between own and other CWB account - same currency - recurring - future dated - no approvals | Adrian Crisp | Test Case | Susan Bako | 2
| 185211 | Failed | 175007 | OLB - E2E - BP - 12 - V1 - Verify bill payment - Recurring - Monthly - Number of Recurrences - No Approvals | Susan Bako | Test Case | Susan Bako | 2
6866 | 184753 | Failed | 183641 | OLB-CRADD-11 - V1 - CRA Direct Deposit for Businesses - Verify Date of Birth field | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 181878 | MOB-E2E-IeT-05 - V1 - Verify user can send an Interac e-Transfer to a recipient (mobile number) - existing recipient with Autodeposit. | Alka Patnaik | Test Case | Alka Patnaik | 2
|  | Failed | 181881 | MOB-E2E-IeT-06 - V1 - Verify user can send an Interac e-Transfer to a recipient (email and mobile number) - existing recipient with Autodeposit. | Alka Patnaik | Test Case | Alka Patnaik | 2
|  | Failed | 182006 | MOB-E2E-IeT-11 - V1 - Verify user can send an Interac e-Transfer to a recipient (Mobile Number) - New recipient with Autodeposit. | Alka Patnaik | Test Case | Alka Patnaik | 2
6921 | 185065 | Failed | 175545 | OLB-E2E-IeT-05 - V1 - Verify user can send an Interac e-Transfer to a recipient (mobile number) - existing recipient with auto deposit | Susan Bako | Test Case | Alka Patnaik | 2
6921 | 185065 | Failed | 175548 | OLB-E2E-IeT-06 - V1 - Verify user can send an Interac e-Transfer to a recipient (email and mobile number) - existing recipient with auto deposit | Susan Bako | Test Case | Alka Patnaik | 2
6921 | 185065 | Failed | 182018 | OLB-E2E-IeT-11 - V1 - Verify user can send an Interac e-Transfer to a recipient (mobile number) - New recipient with Autodeposit | Alka Patnaik | Test Case | Alka Patnaik | 2
7075 | 185612 | Failed | 171989 | MOB-E2E-FT-02a - V1 - Fund Transfer - Beneficiary management - Setup account recipients - valid account - SB | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 174534 | MOB-E2E-FT-24 - V1 - Fund Transfer - Transfer with 2 approvals | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 174542 | MOB-E2E-FT-25 - V1 - Fund Transfer - Transfer with rejection | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 171916 | OLB-E2E-FT-04 - V1 - Fund Transfer - Transfer between own and other CWB account - same currency - once - future dated - no approvals | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 171937 | OLB-E2E-FT-07 - V1 - Fund Transfer - Transfer between own and other CWB account - cross currency - once - future dated - no approvals | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 171940 | OLB-E2E-FT-09 - V1 - Fund Transfer - Transfer between own accounts - same currency - recurring - future dated - no approvals | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 171942 | OLB-E2E-FT-12 - V1 - Fund Transfer - Transfer between own accounts - cross currency - recurring - future dated - no approvals | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 171975 | OLB-E2E-FT-15 - V1 - Fund Transfer - Ensure user can't transfer when there are customer restrictions - retail | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 171977 | OLB-E2E-FT-17 - V1 - Fund Transfer - Ensure user can't transfer when there are customer restrictions - Ret | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 172267 | OLB-E2E-FT-26 - V1 - Fund Transfer - Recall - 1 Approver | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 174462 | OLB-E2E-FT-23 - V1 - Fund Transfer - Transfer with 1 approval | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 174464 | OLB-E2E-FT-24 - V1 - Fund Transfer - Transfer with 2 approvals | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 174482 | OLB-E2E-FT-25 - V1 - Fund Transfer - Transfer with rejection | Adrian Crisp | Test Case | Adrian Crisp | 2
|  | Failed | 174522 | OLB-E2E-FT-19 - V1 - Fund Transfer - Ensure transfer can't occur to an invalid account | Adrian Crisp | Test Case | Adrian Crisp | 2
7117 | 185783 | Failed | 185663 | OLB-E2E-PBT-115 - V1 - Pay CRA Taxes - Verify user can pay current year - Future - No approvals - Form PD4R - Payroll Tax | Susan Bako | Test Case | Susan Bako | 2
| 185221 | Failed | 174570 | SOW3 - OLB - 710 - Pay Business Taxes - AB Template - Verify form's filing fields - AT4990, AT362, AT363, AT360, AT300, AT317, AT5100 | Adrian Crisp | Test Case | Susan Bako | 2
6958 | 185281 | Failed | 180634 | OLB-E2E-PBT-17 - V1 - Pay PROV Taxes - Verify user can pay the amount owing - Future - No approvals - Form ATCLID | Susan Bako | Test Case | Susan Bako | 2
| 184750 | Failed | 171873 | OLB-E2E-SC-04 - V1 - Stop Cheque Payment - Verify Series of Cheques Stop Request - Without payee - no approvals | Alka Patnaik | Test Case | Susan Bako | 2
|  | Failed | 183549 | OLB-FRAUD-69 - V12 - Navaera Field Validation - Personal Customer - Android - Validate Navaera field HTTP_LOCAL_TIME = Infinity field To be mapped | Reddy Ganapati | Test Case | Reddy Ganapati | 2
| 185657 | Failed | 183555 | OLB-FRAUD-75 - V12 - Navaera Field Validation - Personal Customer - Android - Validate Navaera field transferReferenceNumber = Infinity field MONEY MOVEMENT REFID | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Failed | 182630 | OLB-FRAUD-02 - V10 - ORT006 - Small Business Customer - OLB/MOB - Triggering the rule Positive Scenario 2 | Reddy Ganapati
|  | Failed | 182644 | OLB-FRAUD-01 - V10 - ORT029 - Personal Customer - OLB - Flow 1(Login-Benificiary added for Bill Payment + Bill payment within 70mins)- Triggering the rule Positive Scenario 1 | Reddy Ganapati
|  | Failed | 182695 | OLB-FRAUD-05 - V10 - ORT029 - Personal Customer - OLB - Flow 2(Login from new Ip – Modify or add etransfer recipient in past 48 hours – Etransfer or Bill Payment for Transaction Amt > $805 Then Event Score 150)- Triggering the rule Positive Scenario 1 | Reddy Ganapati
| 185423 | Failed | 182732 | OLB-FRAUD-09 - V10 - ORT029 - Personal Customer - OLB - Flow 3(Login Existing Ip – No eTransfer recipient in past 48 hours – No Err - 3 Etransfer Sum > $4500 Then Event Score 120)- Triggering the rule Positive Scenario 1 | Reddy Ganapati
|  | Failed | 185619 | OLB-FRAUD-01 - V10 - ORT030 - Personal Customer - OLB - Triggering the rule Positive Scenario 1 condition 1 | Reddy Ganapati
7073 |  | Failed | 182773 | OLB-FRAUD-01 - V10 - ORT031 - Personal Customer - OLB - Logic Triggering the rule Positive Scenario 1 | Reddy Ganapati
|  | Failed | 182797 | OLB-FRAUD-01 - V10 - ORT032 - Personal Customer - OLB - Triggering the rule Positive Scenario 2 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
|  | Failed | 183091 | OLB-FRAUD-01 - V10 - ORT033 - Personal Customer - OLB - Logic Triggering the rule Positive Scenario 1 | Reddy Ganapati | Test Case | Reddy Ganapati | 2
6705 | 184348 | Failed | 178088 | OLB - DM - E2E-02 - V1 - Verify successful data migration - SB | Adrian Crisp
6909 | 185049 | Failed | 178112 | OLB - DM - E2E-03 - V1 - Verify successful data migration - Consolidated 1 retail and 1 SB | Adrian Crisp

## Outstanding defects
TFS | JIRA | # Blocked Tests | Title | Severity | Assigned To | State | Created Date
185789 | INFINITY-7108 |  | OLB - Contact details were not displayed for the migrated user to verify/confirm after initial login - RETAIL users | 1 - Critical | Adrian Crisp | New | 2021-08-25 11:31
185783 | INFINITY-7117 | 1F | INFINITY-7117 OLB - Pay Business Taxes - Unable to submit PD4R tax form payment for both current and future date. | 1 - Critical | Azfar Karimuddin | In Progress | 2021-08-25 10:55
185506 | INFINITY-7063 | Linked to 8 bugs | OLB - Interac e-Transfer - SEND_MONEY - Unsuccessful Etransfer events are contributing towards a P2P daily limit | 1 - Critical | Reddy Ganapati | New | 2021-08-23 03:48
185505 | INFINITY-7062 |  | OLB - Interac e-Transfer - SEND_MONEY - Send an Interac e-Transfer® page Date field timezone is not equivalent to MST | 1 - Critical | Reddy Ganapati | New | 2021-08-23 01:19
185480 | INFINITY-7052 |  | Fraud/Navaera - Successful Transactions made during the night(may be COB time) are not sent to Navaera - Money is deducted from the accounts | 1 - Critical | Reddy Ganapati | New | 2021-08-22 00:55
185281 | INFINITY-6958 |  | INFINITY-6958 OLB - Pay Business Taxes - Provincial and CRA - When Payment Date is next year an error message is displayed upon submit | 1 - Critical | Azfar Karimuddin | In Progress | 2021-08-18 17:45
185194 | INFINITY-6937 |  | INFINITY-6937 Fraud/Navaera - ORT021 Mobile Device Usage Rule – not working as expected - Client Care Issue Logged: NOD-33208 | 1 - Critical | Azfar Karimuddin | In Progress | 2021-08-17 16:48
185049 | INFINITY-6909 |  | INFINITY-6909 OLB - DM - Business CIF with a combined Personal CIF not created | 1 - Critical | Adrian Crisp | Not fixed | 2021-08-16 17:58
184883 | 7071, 6892 | 14B | OLB_SB_Alerts_No SMS/Text is recived after adding a new recipient | 1 - Critical | Pooja Walia | New | 2021-08-13 19:16
185618 | INFINITY-7076 |  | INFINITY-7076 OLB & MOB - Pay Bills - User is unable to cancel the same day scheduled recurring bill payment. | 2 - High | Anil Kumar | New | 2021-08-23 16:12
185444 | INFINITY-7047 |  | MOB - IOS - Bill Payments - REGISTERED_BILL_PAYMENT - Bill payment confirmation page made using IOS does not have payee account number | 2 - High | Reddy Ganapati | New | 2021-08-20 13:29
185424 | INFINITY-7031 |  | OLB - Etransfer - Add Etransfer Recipient - After Adding the etransfer recipient, send money in the create etransfer wizard and we cannot find the added recipient | 2 - High | Reddy Ganapati | New | 2021-08-20 01:54
185422 | INFINITY-7025 |  | INFINITY-7025 OLB - Interac e-Transfer - Autodeposit fails for recipient where the method of transfer is Mobile Number | 2 - High | Mark Doubinin | In Progress | 2021-08-19 21:57
185221 |  |  | OLB - Pay Business Taxes - Provincial - AB Template - Payment Amount error message not as per spec | 2 - High | Adrian Crisp | New | 2021-08-18 11:39
185211 | INFINITY-6945 |  | OLB - FT and BP - SB - The Effective Date on the Transaction Approval Acknowledgement page is backdated by 1 day. | 2 - High | Alka Patnaik | New | 2021-08-18 09:58
185065 | Infinity-6921 | 5F | Infinity-6921 OLB - e-transfers - MOB - SMS not received when recipient set up for both email and mobile. | 2 - High | Susan Bako | In Progress | 2021-08-17 08:34
185045 | INFINITY-5276 |  | INFINITY-5276 OLB - MOB - Unable to access QA02 URL from a tablet or mobile phone - get 403 error | 2 - High | Harish Pocharam | In Progress | 2021-08-16 16:09
184760 | INFINITY-6867 |  | INFINITY-6867 OLB - CRA Direct Deposit for Businesses: Date of Birth allows Corporate Officer to be under 18 | 2 - High | Chix Dela Luna | In Progress | 2021-08-12 13:27
184687 | NOD-33107 |  | Fraud Navaera - Navaera Tuple is accepting duplicates | 2 - High | Reddy Ganapati | New | 2021-08-11 11:20
184623 |  |  | OLB Retail - MOB - Log in - returning user - cropped features and blue line issue | 2 - High | Pooja Walia | New | 2021-08-09 17:22
183695 | INFINITY-6609 |  | INFINITY-6609 OLB - Bill Payment - Recurring Scheduled BP - UI issue on Acknowledgement screen-Overlapping left and right screen panel. | 2 - High | Alka Patnaik | In Progress | 2021-07-22 23:40
182960 | INFINITY-6337 |  | INFINITY-6337 OLB - Account Details – Transactions tab : Mortgage transactions are showing the incorrect Balance | 2 - High | Adrian Crisp | Ready For Release | 2021-07-09 11:55
182801 | INFINITY-6286 |  | INFINITY-6286 OLB - Pay Business Taxes - The GST34 Netfile does not display the "I wish to make my GST34 NETFILE tax payment" on a new screen. | 2 - High | Azfar Karimuddin | In Progress | 2021-07-07 17:44
179735 |  |  | OLB - Pay Business Taxes - File and Remit - Submit doesn't work on acknowledgement page for all tax forms | 2 - High | Susan Bako | New | 2021-06-04 13:03
179734 |  |  | OLB - Pay Business Taxes - File and Remit - Modify doesn't work on acknowledgement page for all tax forms | 2 - High | Susan Bako | New | 2021-06-04 12:59
179733 |  |  | OLB - Pay Business Taxes - File and Remit - Cancel dialogue too wide on acknowledgement page | 2 - High | Susan Bako | New | 2021-06-04 12:56
185850 |  |  | Fraud/Navaera ORT004 is not generated for the two transactions ids. | 3 - Medium | Reddy Ganapati | New | 2021-08-26 15:30
185793 |  |  | OLB MOB - Mortgage Account details is using the Renewal Date as the Maturity Date | 3 - Medium | Janice Casey | New | 2021-08-25 11:41
185787 | INFINITY-7118 |  | INFINITY-7118 OLB - CRA Direct Deposit for Individuals : consentInformationText variable in API payload contains the variable name instead of actual information | 3 - Medium | Azfar Karimuddin | In Progress | 2021-08-25 11:26
185736 | R1.1 |  | OLB - Spotlight - The SL application does not log out and displays a blank error on the bottom of the page. | 3 - Medium | Alka Patnaik | New | 2021-08-24 17:49
185678 |  |  | Fraud/Navaera - ADMIN USER and ADMIN USER ROLE columns are Null | 3 - Medium | Reddy Ganapati | New | 2021-08-24 12:22
185657 | INFINITY-7098 |  | Fraud/Navaera - MONEY MOVEMENT REFID sent is Null for all transaction events Transfer Reference Number | 3 - Medium | Reddy Ganapati | New | 2021-08-24 01:40
185423 | INFINITY-7026 |  | Fraud/Navaera ORT029 High Risk eTransfers – Score 120 failed Client Care Issue Logged: NOD-33244 | 3 - Medium | Reddy Ganapati | New | 2021-08-20 01:01
185196 | INFINITY-6939 |  | INFINITY-6939 Fraud/Navaera - ORT004 Multi-Time Zones per User per Day failed | 3 - Medium | Reddy Ganapati | In Progress | 2021-08-18 00:40
185180 | INFINITY-6931 |  | INFINITY-6931 OLB - MOB - Login - App behaviour gives 400 error message if you don't remove app from phone after logout. | 3 - Medium | Azfar Karimuddin | In Progress | 2021-08-17 15:08
184847 | INFINITY-6885 |  | INFINITY-6885 OLB Inconsistent email and text sent for sender reminder vs system generated e-Transfer reminder | 3 - Medium | Janice Casey | In Progress | 2021-08-13 12:41
184839 |  |  | SBDCO - Resume Business Form' Page - displays an X that is not in latest FS | 3 - Medium |  | New | 2021-08-13 11:32
184827 |  |  | OLB_SB_Mobile_Login Screen_improper display for cards | 3 - Medium | Pooja Walia | New | 2021-08-13 10:41
184786 | INFINITY-6871 |  | INFINITY-6871 Fraud/Navaera - ORT017 High Velocity ATO EMT Rule - Rule failed - Client Care Issue Logged: NOD-33138 | 3 - Medium | Azfar Karimuddin | In Progress | 2021-08-12 16:20
184781 | INFINITY-6869 |  | INFINITY-6869 OLB Transaction output different when downloaded from different areas | 3 - Medium | Janice Casey | Ready For Release | 2021-08-12 15:53
184718 |  |  | OLB - Account Dashboard - Available Balance on Accounts dashboard displays Working Balance | 3 - Medium | Chix Dela Luna | New | 2021-08-11 15:30
184707 | INFINITY-6847 | 1B 2F | INFINITY-6847 OLB - Feedback - Feedback cannot be found and viewed in Spotlight. | 3 - Medium | Azfar Karimuddin | In Progress | 2021-08-11 12:41
184685 |  |  | SBDCO - Authorized Signer - Name & Address - Address field line should be the same as applicant | 3 - Medium |  | New | 2021-08-11 10:34
184658 |  |  | SBDCO - Previously Submitted - Displays extra text, should not | 3 - Medium |  | New | 2021-08-11 08:11
184655 | INFINITY-6834 |  | INFINITY-6834 OLB e-Transfer "Request" declined AC needs to be revised | 3 - Medium | Janice Casey | In Progress | 2021-08-10 16:28
184637 | INFINITY-6829 |  | INFINITY-6829 OLB Interac e-Transfer History Declined transactions are getting set to expired | 3 - Medium | Janice Casey | In Progress | 2021-08-10 12:55
184631 | INFINITY-6828 |  | INFINITY-6828 OLB - Pay Business Taxes - The Provincial tax acknowledgement screen for future dated txns has incorrect success message. | 3 - Medium | Azfar Karimuddin | In Progress | 2021-08-10 10:55
184612 |  |  | SBDCO - Non-Signing Owners - Residential address - Manual - allows special characters - specifically \ | 3 - Medium |  | New | 2021-08-09 14:22
184569 |  |  | OLB - 'Notes' field in Transfer between accounts is limited to only 30 characters. | 3 - Medium | Raj Sanghamreddy | New | 2021-08-06 15:34
184454 | INFINITY-6765 |  | INFINITY-6765 OLB - OLB and MOBILE - Bill Payment - Scheduled Payments screen - sort order defaults to date descending when ascending makes more sense | 3 - Medium | Azfar Karimuddin | In Progress | 2021-08-05 14:04
184412 |  |  | OLB MOB - e-Transfer recipient with "+" in the email address hangs the app and you have to force stop | 3 - Medium | Janice Casey | New | 2021-08-04 14:39
184364 |  |  | OLB - Notes field is displaying default text 'Online Transfer Out followed by To Account Number' | 3 - Medium |  | New | 2021-08-03 21:57
184310 | INFINITY-6740 |  | INFINITY-6740 OLB e-Transfer History Calendar pop up for "From" appears below "To" | 3 - Medium | Janice Casey | In Progress | 2021-08-03 14:55
184225 |  |  | OLB - Retail - Mobile - Support & About Us - empty phone number and email address | 3 - Medium | Pooja Walia | New | 2021-08-01 18:08
184069 |  |  | SBDCO - ID Scan page - Back button - Modal not displayed s per Figma | 3 - Medium |  | New | 2021-07-29 10:47
183492 | PACS00915812 |  | DCO Process causes Error in QADIG T24 Transact Environment | 3 - Medium | Alka Patnaik | New | 2021-07-20 18:28
183120 | INFINITY-6433 |  | INFINITY-6433 OLB - User Management - Activation Security Code received is 3 digits not 6 digits. | 3 - Medium | Azfar Karimuddin | In Progress | 2021-07-13 12:09
182279 |  |  | OLB-FRAUD - QA02 environment is not configured, json request is not sent to mule | 3 - Medium | Chix Dela Luna | New | 2021-06-30 10:21
182266 |  |  | OLB and SBB_Contact US_Design issues | 3 - Medium | Pooja Walia | New | 2021-06-29 16:55
181622 |  |  | OLB Retail_Move Money_FX calculator Widget_Incorrect number formatting at Amount form | 3 - Medium | Pooja Walia | Not fixed | 2021-06-22 12:58
181505 | INFINITY-5729 |  | INFINITY-5729 Survey pop up displays on session timeout and log out screens | 3 - Medium | Azfar Karimuddin | In Progress | 2021-06-21 15:58
181420 | INFINITY-5723 |  | INFINITY-5723 OLB Retail_Menu Navigation_Feedback_Survey link is not available | 3 - Medium | Azfar Karimuddin | In Progress | 2021-06-21 11:55
179667 | INFINITY-5027 |  | INFINITY-5027 OLB - Stop PAP Request : Cancel button on the initial Stop PAP Request doesn't have a confirmation modal | 3 - Medium | Azfar Karimuddin | In Progress | 2021-06-03 10:06
179550 | INFINITY-4950 |  | INFINITY-4950 OLB - Bill Payments - One time payment - Clicking cancel on the 1st entry page does not bring up cancel dialogue. | 3 - Medium | Azfar Karimuddin | In Progress | 2021-06-01 10:27
179549 | INFINITY-4951 |  | INFINITY-4951 OLB - Bill Payments - Recurring - Clicking cancel on the 1st entry page does not bring up cancel dialogue. | 3 - Medium | Azfar Karimuddin | In Progress | 2021-06-01 10:26
179534 | INFINITY-4945 |  | INFINITY-4945 OLB - Stop Cheque Request : Cancel button on the initial Stop Cheque Request doesn't have a confirmation modal | 3 - Medium | Azfar Karimuddin | In Progress | 2021-06-01 09:22
179404 | INFINITY-4899 |  | INFINITY-4899 OLB - Statements - Statements are shown for every year and month going back 7 years prior to the customer even being created | 3 - Medium | Azfar Karimuddin | In Progress | 2021-05-31 11:37
179083 |  |  | NA - for now - need other acct types 1st - OLB - Stop Cheques Requests page - Only chequing or savings accounts can have a stop cheque created but all account types display in dropdown list. | 3 - Medium | Susan Bako | New | 2021-05-26 10:52
179081 | INFINITY-4739 |  | INFINITY-4739 OLB - Stop Cheques Requests page - Usability - Need to display all stop cheques at once and have a filter. | 3 - Medium | Azfar Karimuddin | In Progress | 2021-05-26 10:44
178691 | INFINITY-4470 |  | INFINITY-4470 OLB - Interac e-Transfer - Add New Recipient - The Request anInterac e-Transfer button is highlighted on the Acknowledgement screen of Add Recipient. | 3 - Medium | Alka Patnaik | In Progress | 2021-05-17 14:32
178339 | INFINITY-4310 |  | INFINITY-4310 OLB - BP - One time current dated BP process does not match AC or Mockup stories for retail customer. | 3 - Medium | Azfar Karimuddin | In Progress | 2021-05-10 15:45