## Slide 1
Adam Skoreyko, Senior Manager – Digital Delivery & Management
CWB.digital Readiness

## Slide 2
CWB.digital Readiness Plan
Digital business team will lead the readiness activities for each release
  The Digital team will validate all functionality and configurations within both CWB.digital and CWB Backstage environments
  Upon completion of the shakedown and confirmation of all functionality/settings sign-off will be provided to proceed to either BAT or production migration
  Utilizing the same process for BAT as production will allow for a dress rehearsal of the readiness plan and process
CWB.digital readiness has three distinct phases
  Exit Criteria for the testing phase must be satisfied
  Shakedown of each environment to determine suitability
  Evaluation of the results with approval/sign-off to proceed into the next stage

## Slide 3
CWB.digital Readiness Process Overview
Exit Criteria – defined at each stage of release
  Achieve 95% pass rate for defects, performance and pen/security testing
  Availability of required environments, integrations & services
  Data migration data load is identified and prepped
Implementation Checklist – defined at each stage of release
  Shakedown of CWB.digital environment with prod test accounts
  Shakedown of CWB Backstage with prod test accounts
Risk Assessment Report
  Output from all Shakedown activities for evaluation by leadership
  Go/No-Go decision for Migration of production accounts

## Slide 4
Exit Criteria - Detailed
Achieve min pass rates for defects, performance and pen/security testing
  Current requirements state no critical/high bugs outstanding for
    Any deferred bugs must have mitigation plans associated with them
  Performance testing for high priority NFRs must meet ~1000 users with screen response times of <3 seconds
  Penetration & Security testing must not present any unmanageable risks
Availability of required environments and integrations (stage dependent)
  CWB.digital & CWB Backstage environment with required interfaces connected
    Mulesoft, Navaera, Okta, Central1 API, X.Ai, CODAT, Brim, DOXIM
Data Migration load is identified and prepped
  Production test accounts will be manually migrated

## Slide 5
Implementation Checklist - Detailed
Shakedown of CWB.digital
  Confirm Okta login and MFA process
  Availability of required menu options, per role type
    Each defined role type has different menu options
  Confirmation of required features & functionality with per role type
    Each defined role type has different features & functionality
  Required interfaces are connected and functioning
    Test account access to Okta, Central1 API, X.Ai, CODAT, Brim, Celero
Shakedown of CWB Backstage
  Validate configurations for:
    Menu options and access per role type
    Customer Management, Employee Management, Security & Authentication, Application Content Management, Master Data Management & Engagements

## Slide 6
Risk Assessment Report - Detailed
Output from all Shakedown activities for evaluation by leadership
  Master configuration files for CWB.digital and CWB Backstage are used to compare environment values to expected values
  Function & feature test list will be produced with pass/fail results
  Shakedown deficiencies will be highlighted for review and acceptance/remediation
Go/No-Go decision for Migration of production accounts
  Program leadership to review Shakedown summary report and provide approval for migration activities to begin as needed