## CWB.digital Readiness Plan
Task ID | Task Name | Task Owner | Duration (Days) | Start | Finish | Dependency | Status
1 | Preliminary Work (pre requisites to readiness activities) |  | 40 | 2021-07-16 | 2021-08-25
1.01 | Creation of CWB.digital readiness plan | Adam Skoreyko | 10 | 2021-07-16 | 2021-07-30 | None | Completed
1.02 | Definition of minimum pass rates for defects, performance and pen/security testing | Program Leadership | 1 | 2021-08-20 | 2021-08-23 | None
1.03 | Approval and Sign-off of readiness plan | Program Leadership | 1 | 2021-08-02 | 2021-08-03 | None
1.04 | Distribution and socialization of CWB.digital readiness plan to rest of program | QA Team, CAS, DM Team, People1 | 1 | 2021-08-24 | 2021-08-25 | None
2 | R1 BAT/UAT Testing Readiness |  | 4 | 2021-08-16 | 2021-08-20 | Task ID 1.00
2.01 | 95% of E2E test scenarios passed, regression completed and critical/high defects resovled | QA | 4 | 2021-08-16 | 2021-08-20 | None
2.02 | Approval and Sign-off E2E exit criteria | Program Leadership | 0 | 2021-08-20 | 2021-08-20 | Task ID 2.01
2.03 | CWB.digital and CWB Backstage UAT environments are prepped and stood up with required integrations | CAS | 2 | 2021-08-04 | 2021-08-06 | Task ID 2.02 | Completed
2.04 | Production test accounts are migrated into the UAT environment | DM Team | 1 | 2021-08-17 | 2021-08-18 | Task ID 2.03
2.05 | Shakedown of CWB.digital | Chix | 0.5 | 2021-08-18 | 2021-08-18 | Task ID 2.04
2.06 | Shakedown of CWB Backstage | Chix | 0.5 | 2021-08-13 | 2021-08-13 | Task ID 2.04 | Completed
2.07 | Shakedown report with pass/fail results and deficiencies identified is presented to program leadership | Adam Skoreyko, Program Leadership | 0 | 2021-08-20 | 2021-08-20 | Task ID 2.05 & 2.06
2.08 | Sign-off of Shakedown report with approval to begin BAT/UAT testing | Program Leadership | 0 | 2021-08-20 | 2021-08-20 | Task ID 2.07
3 | R1 BAT/UAT Testing | Tranche 1 | 8 | 2021-08-17 | 2021-08-25 | Task ID 2.00
3.01 | BAT Testing | QA | 4 | 2021-08-17 | 2021-08-20 | Task ID 2.00
3.02 | Performance Testing | QA | 5 | 2021-08-13 | 2021-08-17 | Task ID 2.00
3.03 | Pentration Testing | QA | 6 | 2021-08-18 | 2021-08-23 | Task ID 2.00
3.04 | Testing status report with pass/fail results and deficiencies identified is presented to program leadership | QA, Program Leadership | 0.5 | 2021-08-25 | 2021-08-25 | Task ID 3.01
3.05 | Sign-off of BAT/UAT testing report with acceptance to move to production | Program Leadership | 0.5 | 2021-08-25 | 2021-08-25 | Task ID 3.04
4 | Production Readiness | Tranche 2 | 19 | 2021-08-24 | 2021-09-12 | Task ID 3.00
4.01 | CWB.digital and CWB Backstage UAT environments are prepped and stood up with required integrations | CAS | 4 | 2021-08-24 | 2021-08-29 | Task ID 3.00
4.02 | Production test accounts are migrated into the production environment (4 test accounts) | DM Team | 1 | 2021-08-29 | 2021-08-29 | Task ID 4.01
4.03 | Shakedown of CWB.digital | Adam Skoreyko | 0.5 | 2021-08-29 | 2021-08-29 | Task ID 4.02
4.04 | Shakedown of CWB Backstage | Adam Skoreyko | 0.5 | 2021-08-29 | 2021-08-29 | Task ID 4.02
4.05 | Shakedown report with pass/fail results and deficiencies identified is presented to program leadership | Adam Skoreyko, Program Leadership | 0 | 2021-08-29 | 2021-08-29 | Task ID 4.03 & 4.04
4.06 | Sign-off of Shakedown report with approval to begin Production migration | Program Leadership | 0 | 2021-08-29 | 2021-08-18 | Task ID 4.05
4.07 | Production Go-Live | All Program Members | 0 | 2021-08-30 | 2021-08-23 | Task ID 4.06
4.08 | DM of Tranche 1 - Program Team clients (~10) into production environment | DM Team | 1 | 2021-09-12 | 2021-09-12 | Task ID 4.07
Formulas:
Duration (Days) = DAYS([Finish], [Start])
Start = [Start, row below]
Start = [Finish, row above]
Finish = WORKDAY([Start],[Duration (Days)])
Finish = WORKDAY([Start],[Duration (Days)])-3