## Baseline
CWB tunl.chat Phase 1 Implementation Schedule
Task | Responsible | Start | End | Notes
Charter review & sign | FICANEX, CWB |  | 2020-12-04 | Gating requirement
Packing for tunl.chat | CWB |  | 2020-12-04 | Gating requirement
Bot Objectives | CWB |  | 2020-12-04
Bot Manager assigned | CWB |  | 2020-12-04 | Gating requirement
Kick off | FICANEX, CWB |  | 2020-12-11
CWB Risk Assessment | CWB | 2020-12-07 | 2020-12-18 | FICANEX to complete vendor questionnaire
Flow Mapping | FICANEX | 2020-12-07 | 2020-12-11 | Recommendations to be presented in kick off
Standard Flow recommendations, Custom Flow topics sign off | CWB | 2020-12-14 | 2020-01-08 | Gating requirement
Bot Blueprint | CWB | 2020-01-11 | 2020-02-05 | Gating requirement
Marketing & Content Plan | CWB | 2020-01-25 | 2020-02-26
Bot build | FICANEX | 2020-01-11 | 2020-01-15
Custom Flow design | FICANEX | 2020-01-18 | 2020-03-05
ACX Academy, Training Sessions | CWB | 2020-01-18 | 2020-03-19 | 3-hour ACX Academy & 3 Q&A training sessions; gating requirement
Flow Revisions | CWB | 2020-01-25 | 2020-03-19 | Ordered List - 8 weeks
CSA review & sign | CWB |  | 2020-03-19 | Gating requirement
UAT Prep | FICANEX | 2020-03-22 | 2020-03-26
UAT | CWB | 2020-03-29 | 2020-04-09 | Gating requirement
Go Live |  |  | 2020-04-12