## Legends
Available today/Must have
Not available today but should be there (Basic needs or available OOTB with Navaera) / Nice to have
Items not part of digital/MVP scope/ OUT OF SCOPE

## Scope
S.No. | Transaction/Service | CURRENT | Additional Details | FUTURE | Additional Details
1 | Interac e-transfers outgoing | Yes | Done in real time by Interac | Yes | We should do our own risk scoring as well – as we rely only on interac today
2 | Interac e-transfers incoming | Yes | Done in real time by Interac | Yes | We should do our own risk scoring as well – as we rely only on interac today
3.a | Bill payments – Case management | Yes | Cases are identified manually through EDW reports and FAS is only being used to log them | Yes | Same functionality will be provisioned
3.b | Bill payments – fraud analysis | No |  | No | Will continue to do manual analysis and use the new system for case/alert management – out of scope for fraud analysis by Navaera
4 | Fund transfers between accounts | No |  | No | Out of scope for Navaera
5 | Wire/ACH transfers | No | Being done outside FAS system | No | Existing process will remain in effect – out of scope for Navaera
6 | Onboarding | Yes | Being done using FAS system | Yes | Existing process will remain in effect – out of scope for Navaera MVP
7 | Other transactions – cheque deposits, atm/pos transactions | Yes | Being done outside FAS system | Yes | Existing process will remain in effect – out of scope for Navaera MVP

## Business Requiremnts
Requirement ID | Category | Business Requirements Description | Exists today? | Part of Fraud Solution? | Additional Notes
BR001 | Module | Fraud module must be separated from the AML module. | Y | Y
BR002 | CASE Management | Must be able to assign alerts to Fraud Investigators. | Y | Y
BR003 | CASE Management | Must be able to manually bulk assign (all case types or selected case types) to a user ( i.e. if someone leaves need to be able to reassign to a new person | ? | Y
BR004 | CASE Management | A user Must be able to escalate a case at any point to Fraud Supervisor for secondary review but still maintain the original case assignment | Y | Y
BR005 | CASE Management | Any trigger event i.e. Interact alerts, cheque fraud, watch-list hits, FDD List must be categorized by there input type for proper case assignment | N | Y
BR006 | CASE Management | Must have the ability to reopen a previously closed case. | Y | Y
BR007 | CASE Management | Must be able to attach documents to a case, including files, emails, internet search results, and screenshots/images (This functionality must include the ability to bulk upload). | ? | Y
BR008 | CASE Management | User Must have the ability to enter the notes in a case. | ? | Y
BR009 | CASE Management | Must be able to escalate a case task to people leader when cases are not actioned | ? | Y
BR010 | CASE Management | Should have the ability to create a manual case- when a branch initites a request a fraud request using a FAR report. | N | Y
BR011 | CASE Management | Should have the ability to integrate with the current tool created by the FSIS team to investigate Bill payment fraud. | N | Y
BR012 | CASE Management | Should have the capability to manually create an alert when a bill payment fraud is identified by the FSIS team (BI reports triggers the bill payment fraud) | Y | Y | Reports are provided by EDW system- They use the reports to identify new frauds in Bill Payments (manually) and then post them to C1 for creating alerts/cases (manually) for tracking
BR013 | Audit | Should provide a detailed audit of an alert from the point an alert is generated to closure and detail all actions taken by a user. | Y | Y
BR014 | Audit | Supervisors should be able to audit and review the comments and actions for each alert | Y | Y
BR015 | Audit | Cases that have been reviewed need to have a flag on the case indicating the case has been subject to review | Y | Y
BR016 | Alerts | User must have the ability to bulk assign the alerts to themselves. | N | Y
BR017 | Alerts | User should be able to notify the vendor of fraudulent e-transfers that have been identified by the client with the details such as transaction #, date and time and the vendor should be capable to create an alert notifying the other FI involved. | Y | ? | @Ravi -Do we have this capability in Navaera? Can Navaera take CWB requests and generate alerts to other FIs?
BR018 | Alerts | FSIS team should receive emails from the system notifying them of potentially fraudulent e-transfers that have not yet been confirmed fraudulent by the sending FI. | Y | Y | If we want to analyse incoming transfers for frauds with Navaera we have to establish its connection with C1's gateway for incoming transfers
BR019 | Alerts | System must sends email alerts notifying the fraud team that an etransfer recipient of our client was involved in fraudulent e-transfers (scam related) previously. | Y | Y | Being done through interac
BR020 | Alerts | Vendor/System in all cases should reach out to other FI for confirmation of funds | Y | ? | @Ravi -Do we have this capability in Navaera? Does Navaera provide the operations support needed for this?
BR021 | Alerts | System should provide a unique identifier for the flagged e- transfer for the FSIS team to communicate with other FI using that identifier. | Y | Y
BR022 | Alerts | System must have Real-time Fraud detection and Real-time analytics. | N | Y
BR023 | Alerts | User must have the ability to create a case using an alert. | N | Y
BR024 | Alerts | User must be able to add comments/ notes before closing an alert. | Y | Y
BR025 | Alerts | Must be able to prioritize alerts based on an alert risk score | N | Y
BR026 | Alerts | System must create alerts for all the transactions flagged as fraud by Interac. (Replacing central-1's FAS sytem) | Y | Y
BR027 | Alerts | System must provide a risk scoring for the flagged transactions. | Y | Y
BR028 | Alerts | All the details pretaining the transaction history and client details should be accessable from within the alert. | N | Y
BR029 | Alerts | Must provide the detailed information regarding the customer, their e-transfer history (incoming/outgoing) and the state of their specified limits (Replace Central-1's current- OAS system) | N | Y | @Ravi -Do we have this capability in Navaera? Following information has to be fetched from Interac 1. Transfer limits - this will become a problem for MVP timelines 2. etransfer history for a customer 3. other info about customer
BR030 | Alerts | Alert should contain the Equifax and threat matrix details/scores categorized by the source. (this would save investigators time of signing in to different systems and searching for the information) | Y | Y | Contains a deep link to Equifax and Threatmatrix within the alert today.
BR031 | Alerts | Investigator must have the ability to close the alerts once the investigation is finished. | Y | Y
BR032 | Alerts | Must have the ability to select multiple alerts and close them all at once. | Y | Y
BR033 | Alerts | The system must record the number of days a new alert is available in the system before it has been actioned by a member of the FSIS team. | N | Y
BR034 | Alerts | Must provide a user with different Fraud dropdown selections, to action an alert. | N | Y | They want more options in the drop down which potentially mean more workflow options for each fraud alert
BR035 | Alerts | Where an alert has not been actioned beyond a defined number of days, a supervisor must be notified that the alert has not been actioned | ? | Y
BR036 | Alerts | TM alerts must present transactional data in a table based on the following fields: | ? | Y | Incomplete requirement
BR037 | Alerts | The fraud alert must have the analytics side to it and it should explain why this alert is generated and provides a logic and the information that triggered the alert (e.g., cheque fraud, digital fraud, etc.) | N | Y | Navaera already has this OOTB
BR038 | Alerts | FSIS team should not have to go to different systems to find details. | N | Y | Following are the systems they go to today to fetch the information they need - Equifax - for onboarding only - Threat matrix - for onboarding only - Interac
BR039 | Alerts | Alerts must include why the alert has been generated and the information that triggered the alert (e.g., cheque fraud, digital fraud, etc.) | N |  | DUPLICATE BR37 - merged
BR040 | Alerts | Should contain the full demographic information on the client involved in the transaction. | Y | Y | They get the information provided by Interac (as well as Equifax and threat matrix for onboarding)
BR041 | Alerts | Alert information should contain connected parties to an account. Connected party information should include the full demographic information of the connected party | N | Y | What do you mean by connected parties - Recipient/Sender for MVP Connected party - Joint accoutn holders for MMP
BR042 | Alerts | Must be able to review all previous cases from the same entity when a new case is generated from an alert. | N | Y
BR043 | Alerts | Must have the ability to screen against the CWB internal data & internal lists and have results returned to verify screening results at the case review time. - FDD List - Watch list/List of undesirable customers (created and maintained by the FSIS) - FSIS name scrubbing list and create a log of matches | N | Y
BR044 | Workflow Mangement | Should have the ability to notify the AML department and transfer all the information to the AML department from the Fraud module. | N | Y | Email to see if this can be red - Q6
BR045 | Workflow Management | Must allow the director to assign the alerts to the investigators and investigators must be allowed to assign the alerts/case to the supervisors for the review/approvals. | duplicate(BR002) | Y | Yes it’s a duplicate
BR046 | Workflow Management | When an alert is assigned, the user must be notified of an assignment. | Y | Y
BR047 | Integration | Must be Integrated with CWB internal data, FDD list, watch list. | N | Y | DUPLICATE BR43- merged
BR048 | Integration | Must Integrate FSIS name scrubbing list, create a log for the matches | N | Y | DUPLICATE BR43- merged
BR049 | Reporting | Must provide the data report for the bill payments (e.g. # of bill payments) | Y | N | C1 does not provide this info as FAS vendor rather they provide this as they are the gateway for Bill payments. So This should continue to come from C1 in future too.
BR050 | Reporting | Must provide the data report for the online transactions (e.g. remitted not posted, posted not remitted, total # of transactions-incoming & outgoing) | Y | N | C1 does not provide this info as FAS vendor rather they provide this as they are the gateway for Bill payments. So This should continue to come from C1 in future too.
BR051 | Dashboard | System must provide intutive dashboard capability for user's to customize the dashboard as per their needs/roles. | N | Y
Note on D1: Faizan Ahmed: Y: Yes FSIS has it N: No FSIS do not have it ?: Andy not sure
Note on E1: Faizan Ahmed: Some of the offerings from C1 are as a vendor for online banking and payment gateway. Those are marked with N. ? Where we are not sure
Note on A30: Faizan Ahmed: Andy feels we can easily fulfil this so should be included in MVP
Note on B30: Faizan Ahmed: This will require a separate interface with Interac to fetch the limits - which might become a problem for MVP timelines
Note on B50: Faizan Ahmed: Should be fulfilled by C1 or Infinity as our new online banking vendor